## Cover
RAIDD Log — Beacon Index Advantage
Lighthouse Financial Services Company
Status as at 16 October 2026
Risks | 12
Assumptions | 8
Issues | 6
Dependencies | 7
Decisions | 11
Gate Conditions (own register) | 5
Gate Conditions carry their own full register (owner, verification method, evidence, post-closure efficacy) in gate-conditions-register.html — the Gate Conditions tab here is a status summary only.

## Risks
ID | Risk | Owner | Status | Response
R-01 | IIPRC review extends past the standard clock over a non-standard GLWB rider feature | P. Hollingsworth | Open | Monitor
R-02 | Non-Compact state approvals (CA, FL) land later than Compact states, forcing a phased rollout | P. Hollingsworth | Open | Monitor
R-03 | Option budget compresses if index option costs rise, pushing the illustrated cap below competitive | S. Ravichandran | Open | Monitor
R-04 | Cordelane cannot support the participation-rate strategy without custom development | V. Sandoval | Closed by scope cut | Retired — absorbed into GC-01 / D-03
R-05 | Hedging readiness (ISDA, derivatives ops, daily rebalance) lags launch | M. Delacroix | Open — elevated | Active — drives GC-05
R-06 | Pricing assumptions (lapse, GLWB utilization) prove unsupportable under external peer review | S. Ravichandran | Open | Active — drives GC-03
R-07 | Distribution partners deprioritize against competitor launches in the same quarter | R. Castellanos | Open — elevated | Active — linked to I-06
R-08 | Illustration engine cannot produce compliant hypothetical illustrations inside the filing window | E. Kowalczyk | Open — reduced | Active, lower severity after GC-01 scope cut
R-09 | Statutory reserve and capital treatment is heavier than modeled, degrading product IRR | T. Brennan | Open | Monitor
R-10 | Single credentialed pricing actuary sits on the critical path | S. Ravichandran | Realized, closed | Realized as I-03; vacancy filled 08 Sep 2026
R-11 | Advisor appointment/licensing throughput limits producing agents at launch | H. Kirkpatrick | Open | Monitor
R-12 | Post-launch sales concentrate in one crediting strategy, creating hedging concentration | M. Delacroix | Open | Monitor — raised as dissent at Gate 1

## Assumptions
ID | Assumption | Owner
A-01 | Licensed and in good standing across all 46 target states through launch | P. Hollingsworth
A-02 | The Compact accepts the product under existing uniform standards; no new standard needed | P. Hollingsworth
A-03 | New York is out of launch scope | A. Nkemelu
A-04 | The existing admin platform is extended, not replaced | V. Sandoval
A-05 | Distribution runs through existing IMO/broker-dealer relationships; no new channel | R. Castellanos
A-06 | Hedging is executed by the in-house Investments desk | M. Delacroix
A-07 | Rates stay inside the Gate 1 pricing corridor | S. Ravichandran
A-08 | No competing internal launch draws the same actuarial and IT people in 2027 | G. Marchetti

## Issues
ID | Issue | Owner | Status | Resolution / Note
I-01 | Gate 1 recycled 30 Apr 2026 — distribution volume assumptions never validated with the wholesaler channel, and the hurdle-rate calc used a superseded capital charge | C. Tyrrell | Closed | 6-week loop, $232,000; see Gate 1 Recycle Memorandum
I-02 | Brightpath's hypothetical-performance module can't support 2 of the 5 proposed crediting strategies | E. Kowalczyk | Closed by scope cut | Resolved via GC-01 / D-03 — 2 strategies removed, not built around
I-03 | Lead pricing actuary vacancy — 11 weeks open | G. Marchetti | Closed | Filled 08 Sep 2026 (realization of R-10)
I-04 | Config environment shared with an in-flight servicing release → test-window contention | V. Sandoval | Open | Being scheduled around in Stage 3 planning
I-05 | GLWB contract form language returned twice by outside counsel over free-look / death-benefit interaction | A. Nkemelu | Open | Third redraft with counsel; see Gate 2 Readiness Assessment
I-06 | Plan assumed 6 field wholesalers; Distribution can commit 4 at launch | R. Castellanos | Open | Linked to the GC-04 efficacy finding and the $17,000,000 uncommitted Year 1 gap

## Dependencies
ID | Dependency | Owner | Status
DEP-01 | IIPRC review clock — external regulator, cannot be compressed | P. Hollingsworth | Ongoing
DEP-02 | California and Florida department review, separate SERFF filings | P. Hollingsworth | Ongoing
DEP-03 | Cordelane's quarterly configuration windows | V. Sandoval | Ongoing
DEP-04 | Calder index licensing agreement | D. Falkner | Executed
DEP-05 | Halverson Re term sheet for GLWB risk transfer | M. Delacroix | Executed
DEP-06 | ISDA/CSA execution with two derivatives counterparties | M. Delacroix | One executed, one not yet begun — drives GC-05
DEP-07 | Corporate Actuarial's annual assumption refresh, feeds Gate 2 re-pricing | T. Brennan | Scheduled

## Decisions
ID | Decision | Decided By | Date
D-01 | FIA, not a RILA — keeps the product out of SEC/FINRA and in the state filing lane | Gate Review Board | 05 Feb 2026
D-02 | New York excluded from launch scope (GC-02) | B. Lindqvist | 11 Jun 2026
D-03 | Launch with 3 crediting strategies, not 5 (GC-01) | D. Falkner | 21 Jul 2026
D-04 | Configure the incumbent illustration vendor rather than procure new; 2 strategies deferred | D. Falkner | 21 Jul 2026
D-05 | GLWB offered as an optional rider, not embedded | G. Marchetti | 05 Feb 2026
D-06 | File through the Compact first, with CA/FL in parallel rather than sequentially | B. Lindqvist | 05 Feb 2026
D-07 | Extend the existing admin platform rather than stand up a new product-line system | V. Sandoval | 05 Feb 2026
D-08 | Hedging executed in-house by Investments | M. Delacroix | 05 Feb 2026
D-09 | Contingency is held by the Gate Review Board; release requires a gate decision | Gate Review Board | 05 Feb 2026
D-10 | No full-program EVM baseline; performance reported within the released tranche | J. Whitmore | 05 Feb 2026
D-11 | The gate chair facilitates and does not vote; the five voting seats are functional executives | Gate Review Board | 05 Feb 2026

## Gate Conditions (summary)
ID | Condition | Owner | Status | Due | Closed
GC-01 | Reduce launch crediting strategies from five to three | D. Falkner | Closed | 31 Jul 2026 | 21 Jul 2026
GC-02 | Remove New York from launch scope and issue a deferral memorandum | A. Nkemelu | Closed | 31 Jul 2026 | 03 Jul 2026
GC-03 | Independent external actuarial peer review of GLWB rider pricing before Gate 2 | S. Ravichandran | Open | 26 Feb 2027
GC-04 | Re-validate distribution volume assumptions with the three largest IMO partners | R. Castellanos | Closed | 31 Aug 2026 | 14 Aug 2026
GC-05 | Present a hedging readiness plan with ISDA execution milestones at Gate 2 | M. Delacroix | At-Risk | 12 Mar 2027