Lighthouse Financial Services Company

Requirements Traceability Matrix

Traced to Gate Decisions, Both Ends

Lighthouse Financial Services Company — Every product, regulatory and operational requirement for Beacon Index Advantage, traced to the gate that authorized it and the gate that will verify it. Status as at 16 October 2026.

18

Requirements traced

14

Active

2

Withdrawn, still traceable

1

Excluded by decision

Contents

Why This Matrix Traces to Gates, Not Just to Tests

Active Requirements

Withdrawn and Excluded — Kept Traceable on Purpose

Forward Trace

Verification Coverage by Gate

Traceability Gaps

Document Control

1. Why This Matrix Traces to Gates, Not Just to Tests

A conventional traceability matrix runs one direction: requirement → design → build → test case → result. That is necessary here too, and §4 carries it. But it is not sufficient in a stage-gate program, because a requirement in this program has two decision endpoints, not one.

Authorized at a gate. No requirement exists because someone wrote it down. It exists because a gate released the funding for the stage that builds it. PR-04 through PR-06 were authorized at Gate 1; PR-01 through PR-03 predate it and were authorized at Gate 0.

Verified at a gate. Test evidence is tabled to a specific gate as part of a must-meet certification. A requirement whose verification does not land at a gate is a requirement nobody is obliged to check.

The practical consequence: a requirement can be traced to the exact decision that created it and the exact decision that will close it. That is a stronger claim than "it has a test case," and it is the claim a gate actually needs — because at a gate the question is not "was this tested?" but "is the Board entitled to rely on this being done?"

2. Active Requirements

| ID | Requirement | Source | Auth. | Verified | Status |
| --- | --- | --- | --- | --- | --- |
| PR-01 | Single-premium deferred fixed indexed annuity chassis | Gate 0 concept · D-01 | G0 | G3 | Active |
| PR-02 | Seven-year declining surrender-charge schedule | Gate 0 concept | G0 | G3 | Active |
| PR-03 | Optional GLWB rider (not embedded) | D-05 | G0 | G3 | Active |
| PR-04 | Fixed account crediting strategy | D-03 launch set | G1 | G2 | Active |
| PR-05 | One-year point-to-point on the Calder Balanced 5, capped | D-03 launch set · DEP-04 | G1 | G2 | Active |
| PR-06 | One-year performance-triggered crediting strategy | D-03 launch set | G1 | G2 | Active |
| PR-09 | Compact-route filing across member states | D-06 · A-02 | G1 | G3 | Active |
| PR-10 | Separate SERFF filings for California and Florida | D-06 · DEP-02 | G1 | G3 | Active |
| PR-12 | Compliant hypothetical performance illustrations | NAIC #275 · R-08 | G1 | G2 | Active |
| PR-13 | Suitability and best-interest advisor training | NAIC Model Reg #275 | G1 | G4 | Active |
| PR-15 | Extension of the incumbent admin platform (no new system) | D-07 · A-04 | G1 | G2 | Active |
| PR-16 | GLWB risk transfer via reinsurance | DEP-05 | G1 | G3 | Active |
| PR-17 | New business issue and policyholder servicing capability | Gate 1 scope | G1 | G4 | Active |
| PR-18 | Distribution through existing IMO/BD relationships only | A-05 | G1 | G4 | Active |
| PR-14 | In-house hedging of the GLWB guarantee | D-08 · A-06 | G1 | G4 | At risk |

PR-14 is the only active requirement carrying an at-risk trace. In-house hedging of the GLWB guarantee runs through GC-05 to ISDA execution under DEP-06, where one of two counterparties has not begun negotiation. The requirement is authorized, the design exists, and the verification chain is incomplete at a point outside the program's control. Every other document in this suite flags the same item from a different angle — which is the register agreement you want, not duplication.

3. Withdrawn and Excluded — Kept Traceable on Purpose

Two crediting strategies were cut at Gate 1 under GC-01, recorded as decision D-03. They remain in this matrix as withdrawn rows rather than being deleted from it.

| ID | Requirement | Source | Auth. | Verified | Status |
| --- | --- | --- | --- | --- | --- |
| PR-07 | Participation-rate crediting strategy | Gate 0 concept (5-strategy set) | G0 | — | Withdrawn |
| PR-08 | Monthly-averaged crediting strategy | Gate 0 concept (5-strategy set) | G0 | — | Withdrawn |
| PR-11 | New York excluded from launch scope | A-03 · D-02 · GC-02 | G1 | — | Excluded by decision |

An RTM that deletes cut requirements cannot answer the most common question asked of a launched product: “why doesn't it do X?” With PR-07 and PR-08 retained, the answer is a citation rather than an argument: withdrawn at Gate 1 on 11 June 2026 under GC-01, recorded as D-03, because the incumbent platform and illustration engine could not support them (R-04, I-02) and their forecast contribution did not justify building the capability. The build allocation returned to reserve.

The distinction between withdrawn and excluded is deliberate and is not cosmetic. PR-07 and PR-08 were in scope and were removed. PR-11 — New York — was never in launch scope; it is an exclusion with a deferral memorandum recording the conditions under which it would be revisited. Collapsing the two would make a considered scope decision look like a cut, and a cut look like a considered scope decision.

4. Forward Trace

The conventional chain, requirement through to the evidence that closes it.

| ID | Trace |
| --- | --- |
| PR-01 | Product spec → contract form filing → Compact submission → issue testing |
| PR-02 | Product spec → contract form → illustration engine → admin platform config |
| PR-03 | Rider spec → pricing basis → GC-03 external review → contract form → hedging |
| PR-04 | Product spec → admin platform config → illustration validation |
| PR-05 | Index license → pricing → illustration validation → hedging instrument selection |
| PR-06 | Product spec → admin platform config → illustration validation |
| PR-07 | Withdrawn at Gate 1 under GC-01 (D-03). Platform could not support it without custom development (R-04); build allocation returned to reserve. Not deferred — out of scope. |
| PR-08 | Withdrawn at Gate 1 under GC-01 (D-03). Illustration engine could not produce compliant hypothetical performance (I-02). Not deferred — out of scope. |
| PR-09 | Filing plan → IIPRC submission (DEP-01) → approval → state activation |
| PR-10 | Filing plan → SERFF submissions → department review → state activation |
| PR-11 | Scope exclusion, closed under GC-02. Deferral memorandum filed; filing plan, distribution footprint and Stage 4 training scope all derive from it. |
| PR-12 | Illustration spec → Brightpath build → validation vs filed methodology |
| PR-13 | Training spec → enablement build → delivery → completion records at Gate 4 |
| PR-14 | Hedging design → GC-05 readiness plan → ISDA execution (DEP-06) → live shadow book |
| PR-15 | Cordelane SOW → configuration (DEP-03) → issue and servicing testing |
| PR-16 | Halverson Re term sheet → treaty → capital treatment confirmation |
| PR-17 | Ops design → process build → end-to-end test with trained staff at Gate 4 |
| PR-18 | Channel plan → GC-04 written commitments → appointment and licensing pipeline |

5. Verification Coverage by Gate

| Verifying gate | Requirements | IDs |
| --- | --- | --- |
| G2 | 5 | PR-04, PR-05, PR-06, PR-12, PR-15 |
| G3 | 6 | PR-01, PR-02, PR-03, PR-09, PR-10, PR-16 |
| G4 | 4 | PR-13, PR-14, PR-17, PR-18 |
| — (no verifying gate) | 3 | PR-07, PR-08, PR-11 |

Verification load concentrates at Gate 3 — regulatory approval, reserve adequacy and final rates all land together — and at Gate 4, where operational and distribution readiness is demonstrated rather than planned. Gate 2's share is smaller than it looks: three of its requirements were made materially easier by the GC-01 scope reduction, since the two strategies the illustration engine could not support are no longer in the set it must validate.

6. Traceability Gaps

| ID | Gap |
| --- | --- |
| TG-01 | No requirement traces to a benefit. The matrix traces requirements to gates and to test evidence, but nothing links PR-05 (the capped indexed strategy) to BEN-05 (crediting mix), or PR-18 (channel) to BEN-01 (volume). A product can therefore satisfy every requirement and still miss its business case, and this matrix would show full coverage throughout. The Benefits Realization Plan carries the benefit side; the two documents are not joined. |
| TG-02 | Two requirements are verified by parties outside the program. PR-09 and PR-10 close only when regulators approve (DEP-01, DEP-02). The program can evidence submission quality and nothing further; the requirement's closure is not within its gift. |
| TG-03 | PR-13 verification is a completion record, not an effectiveness measure. Advisor training under NAIC #275 is verified at Gate 4 by delivery and completion records. Whether the training changed advisor behavior is a market-conduct question no gate in this program asks. |
| TG-04 | No requirement covers the post-launch window. Every row verifies at or before Gate 4. Gate 5 reviews outcomes, not requirements — so nothing in this matrix has a verification point after 06 Mar 2028. |

7. Document Control

| Version | Date | Change |
| --- | --- | --- |
| 1.0 | 05 Feb 2026 | Opened at Gate 0 with the concept requirement set, including the five proposed crediting strategies. |
| 1.1 | 11 Jun 2026 | Gate 1 authorizations recorded. PR-07 and PR-08 moved to withdrawn under GC-01 / D-03; PR-11 recorded as excluded under GC-02 / D-02. No row deleted. |
| 1.2 | 16 Oct 2026 | PR-14 trace marked at risk following the September program review (GC-05 / DEP-06). Traceability gaps TG-01..TG-04 formalized. |

Maintained by C. Tyrrell, NPD Program Manager and Chair of the Gate Review Board. Related: Gate Decision Framework · Gate Conditions Register · RAIDD Log · Benefits Realization Plan (see TG-01).

Lighthouse Financial Services Company — Beacon Index Advantage program. Fictional portfolio artifact produced by C. Tyrrell to
demonstrate stage-gate new product development governance. No real company, product, person or
filing is depicted.