## Slide 1
STEERING REVIEW · STEERING REVIEW · STAGE 2
Beacon Index
Advantage
Steering committee review — Beacon Index Advantage is in Stage 2 development (Week 17 of 40) on a recycle-compressed schedule, reading Amber on hedging readiness and distribution while the corrected economics hold above hurdle.
Stage 2 · Wk 17/40
Heading to Gate 2
● Amber
Overall Health
13.4% IRR
vs. 11.0% Hurdle
$27.904M
Authorized

## Slide 2
AGENDA
Today's Steering Review
1
Program Health Snapshot
2
Where We Stand — Status
3
Objectives & Conditions Status
4
Scope & Change Log
5
The Program Team
6
Stage-Gate Governance
7
Gate Roadmap & Schedule
8
Budget Forecast
9
How We Stay in Sync
10
Risk Register — Aged
11
Issues — Raised & Resolved
12
Decisions & Look-Ahead
2

## Slide 3
PROGRAM HEALTH
Where We Stand — Stage 2
Beacon Index Advantage sits in Stage 2 reading Amber — the Gate-1 recycle is behind us and the economics hold above hurdle, but hedging readiness and distribution commitment are the live risks.
Gate 1 recycled on 30 April and cleared GO WITH CONDITIONS on 11 June once the economics were corrected — the capital charge was understated by 87 basis points, taking the IRR from 14.6% to a corrected 13.4%, still above the 11% hurdle. Because the launch date held, Stage 2 absorbed the recycle by compressing from 46 to 40 weeks. Three of the five gate conditions are closed. The RAG is Amber because two risks are elevated — hedging readiness (R-05, now 20) and distribution deprioritization (R-07, now 16) — and $17M of Year-1 premium remains uncommitted. The get-to-Gate-2 path is the GC-05 hedging plan, the GC-03 peer review, and closing the distribution gap.
● Amber
Overall health
Wk 17 / 40
Stage 2 to Gate 2
3 of 5
Gate-1 conditions closed
3

## Slide 4
PROGRAM STATUS
Amber on Hedging & Distribution; the Recycle Is Behind Us
The corrected economics hold above hurdle; the risk sits in hedging readiness and distribution commitment, not in the numbers.
Economics are Green: the recycle-corrected IRR of 13.4% clears the 11% hurdle, with the cap at 9.25% against a 9.00% peer benchmark and the floor fixed at 8.50%. Schedule is Amber: the recycle cost six weeks that Stage 2 is absorbing on a 40-week run to Gate 2. Hedging is Amber: readiness (R-05) is elevated to 20 and drives the at-risk condition GC-05. Distribution is Amber: GC-04 closed only partially — $17M of Year-1 premium is still uncommitted (I-06). The committee's focus is the two Amber domains, not the return.
KEY FACTS
Economics
● Green — 13.4% IRR above 11% hurdle
Schedule
● Amber — recycle-compressed 40 wks
Hedging (GC-05)
● Amber — at-risk; R-05 elevated to 20
Distribution
● Amber — $17M Y1 gap (I-06)
4

## Slide 5
OBJECTIVES
How We're Tracking to Plan
1
✓ Gate 1 cleared GO WITH CONDITIONS after the recycle — economics corrected to a 13.4% IRR, above the 11% hurdle
2
✓ GC-01, GC-02, GC-04 closed — strategies cut to three, New York removed, IMO volumes re-validated
3
AT RISK — GC-05: the hedging readiness plan with ISDA milestones for Gate 2; R-05 elevated to 20
4
On track — GC-03: independent external actuarial peer review of GLWB rider pricing before Gate 2
5
AT RISK — $17M of Year-1 premium uncommitted after GC-04 (I-06); distribution deprioritization (R-07) elevated to 16
5

## Slide 6
SCOPE & CHANGE
What's Changed Since Kickoff
IN SCOPE
✓
Recycle correction (I-01)
Capital charge corrected 3.33% → 4.2%; IRR 14.6% → 13.4%; launch held → Stage 2 compressed 46 → 40 wks
✓
GC-01 · Strategies 5 → 3
Launch crediting strategies reduced from five to three (closed 21 Jul); dependency removed
✓
GC-02 · New York removed
NY removed from launch scope with a deferral memorandum (closed 03 Jul) — now load-bearing across filing
OUT OF SCOPE (CANDIDATE BACKLOG)
✕
Launch date held
6 Mar 2028 unchanged — the recycle was absorbed by compressing Stage 2, not by moving launch
✕
Fixed-indexed-annuity structure
Still a fixed indexed annuity, not a RILA (D-01) — state-filed via the Interstate Compact
✕
Authorized envelope held
$27.904M ceiling unchanged; $412K of the $2.304M contingency drawn to date
6

## Slide 7
TEAMS
The Program Team — 90 in Stage 2
90 people across the program in Stage 2. The lead pricing-actuary vacancy (I-03, R-10) was filled 08 Sep; hedging operations are being reinforced against the elevated R-05. Full roster in the Resource Plan.
8
Program Leadership & PMO
Lead: C. Tyrrell (NPD PM — chairs the Gate Review Board, no vote)
14
Actuarial & Pricing
Leads: S. Ravichandran (pricing), T. Brennan (reserving) — pricing vacancy filled (I-03)
16
Product, Regulatory & Compliance
Leads: P. Hollingsworth (filing), B. Lindqvist (GC & CCO); NY deferral, GLWB form (I-05)
20
Systems & Illustration (Cordelane)
Lead: E. Kowalczyk — illustration risk (R-08) reduced 16 → 8
12
Investments & Hedging Operations
Lead: M. Delacroix — hedging readiness (R-05) elevated; drives GC-05
20
Distribution & Advisor Enablement
Leads: R. Castellanos, H. Kirkpatrick — 4 of 6 wholesalers committed (I-06)
7

## Slide 8
GOVERNANCE
Who Decides What
The program is governed by a Gate Review Board that renders one of five outcomes at each gate — GO, GO WITH CONDITIONS, RECYCLE, HOLD, or CANCEL — on a two-tier test: must-meet knockout criteria first, then a weighted 1–5 score. Gate 1 exercised the RECYCLE outcome, then GO WITH CONDITIONS. The board holds five votes; the NPD Program Manager chairs it but does not vote.
Gate Review Board
Renders the gate outcome; Gate 1 recycled, then GO WITH CONDITIONS (5 conditions)
6 seats / 5 votes — chaired, no vote, by C. Tyrrell
Sponsor
Business ownership, funding authorization, program continuation
G. Marchetti, Chief Product Officer
Actuarial & Risk
Pricing, capital, and the corrected-economics sign-off
N. Adeyemi (Chief Actuary) · D. Pemberton (CRO, observer)
Legal & Compliance
Regulatory filing, GLWB form language (I-05), distribution conduct
B. Lindqvist (General Counsel & CCO)
8

## Slide 9
TIMELINE
Stage 2 — Week 17 of 40, Heading to Gate 2
Gate 0 GO and Gate 1 GO-WITH-CONDITIONS are behind us; Stage 2 runs on a recycle-compressed 40-week schedule to the Gate 2 decision in April 2027.
Stage 1 · Concept → Case
Gate 0 GO ✓ · Feb–Jun '26
Gate 1 · Recycle → Conditions
Recycled, then GO w/ conditions ✓ · Apr–Jun '26
Stage 2 · Build & File
In progress — Wk 17/40 ◆ · Jun '26–Apr '27
Gate 2 → Launch
Upcoming · Apr '27–Mar '28
Post-Launch · Gate 5
Upcoming · Sep '28
KEY MILESTONES
✓ 05 Feb '26
Gate 0 — concept approved (GO, 5-0)
✓ Apr → 11 Jun '26
Gate 1 recycled, then GO WITH CONDITIONS (economics corrected)
◆ 16 Oct '26
Stage 2 development — Week 17 of 40
Apr '27
Gate 2 decision
06 Mar '28
Product launch (date held)
07 Sep '28
Gate 5 — post-launch review
9

## Slide 10
TIMELINE · DETAIL
Project Phases — Detailed View
The program as a work view — bars show when each workstream runs and where they overlap.
'26 H1
'26 H2
'27 H1
'27 H2
'28 H1
Post
Prog.
Gates 0–1 ✓
Stage 1 — concept & business case
Gate 1 recycle → conditions
Stage 2 (now)
Build, file & illustration
Hedging & distribution readiness
Gate 2 → Launch
Test & launch prep (Stage 3–4)
Launch → post-launch review
10

## Slide 11
BUDGET
Budget Status
TOTAL PROGRAM BUDGET $27.904M
Stage 1 — Concept & Business Case
$2,180,000
Released and spent; the recycle drew $232K of contingency (I-01)
Stage 2 — Build & File (in progress)
$11,640,000
Authorized at Gate 1; ~Week 17 of 40 in progress
Stage 3 — Test & Launch Prep
$7,450,000
Gated — authorized at Gate 2 (Apr 2027)
Stage 4 — Launch & Stabilize
$4,330,000
Gated — authorized at Gate 4
Gate Contingency (9.0%)
$2,304,000
$412K drawn ($232K recycle + $180K GC-03 peer review); $1,892K held
Authorized envelope of $27.904M (base $25.6M + 9.0% contingency $2.304M), released one stage at a time. $412K of contingency is drawn — the recycle and the GC-03 external peer review — leaving $1,892K held. The envelope ceiling is unchanged.
11

## Slide 12
BUDGET FORECAST
Budget Forecast — Within the $27.904M Authorized Envelope
The corrected economics hold — a 13.4% IRR against the 11% hurdle — and spend is tracking within the $27.904M authorized envelope through Stage 2.
The Gate-1 recycle corrected an 87-basis-point understatement of the capital charge (3.33% to 4.2%), taking the IRR from 14.6% to 13.4% — still above the 11% hurdle, on a 5-year premium projection of $1.875B. Spend is within the authorized envelope: $412K of the $2.304M contingency is drawn (the recycle and the external peer review), leaving $1,892K held against the elevated hedging and distribution risks heading into Gate 2.
● ON TRACK
CUMULATIVE SPEND — PLAN vs. ACTUAL / FORECAST ($M)
Chart: 
| Feb'26 | Jun'26 | Oct'26 | Apr'27 | Nov'27 | Sep'28
Planned | 0 | 2.18 | 7.2 | 13.82 | 23 | 27.904
Actual + Forecast | 0 | 2.4 | 7.9 | 14.4 | 23.6 | 27.9
$27.904M
Authorized (4 tranches)
13.4% IRR
vs. 11.0% hurdle (corrected)
$412K
Contingency drawn of $2.304M
12

## Slide 13
WORKING TOGETHER
How We Stay in Sync
CADENCE
FORUM
PURPOSE
Per gate
Gate Review Board
Formal gate outcome — GO / conditions / recycle / hold / cancel; 5 votes, Chair no vote
Weekly
Program Status Review
Cross-workstream status, gate-condition tracking, RAIDD updates
Monthly
Sponsor / CPO Review
Program health, risk acceptance, and the path to Gate 2 with the sponsor
Bi-weekly
Gate-2 Conditions Review
GC-03 peer review and GC-05 hedging plan tracked to closure before Gate 2
13

## Slide 14
RISKS
Risks and Mitigation
The full register at a glance — each risk with its mitigation, likelihood, and impact; detailed cards follow.
IDENTIFIED RISKS
MITIGATION STRATEGY
LIKELIHOOD
IMPACT
01
Hedging readiness lags launch
✓
Hedging plan + ISDA milestones for Gate 2 (GC-05)
High
High
02
Distribution partners deprioritize
✓
IMOs re-validated; $17M worked through I-06
High
High
03
Pricing assumptions under peer review
✓
External actuarial peer review before Gate 2 (GC-03)
Medium
High
04
Illustration engine in the filing window
✓
Illustration sequenced early — risk reduced 16 → 8
Medium
Medium
14

## Slide 15
RISK REGISTER
Risk Register (1 of 2)
R-05
Hedging readiness lags launch
LIKELIHOOD HIGH
IMPACT HIGH
ISDA execution, derivatives operations, and daily rebalance readiness are lagging — the risk elevated from 15 to 20 this period and now drives the at-risk gate condition GC-05.
OWNER M. Delacroix
STATUS Open — elevated 15 → 20
Mitigation: A hedging readiness plan with explicit ISDA execution milestones is being prepared for Gate 2 (GC-05); operations staffing is being reinforced now.
R-07
Distribution partners deprioritize
LIKELIHOOD HIGH
IMPACT HIGH
IMO and wholesaler partners could deprioritize Beacon against competitor launches in the same quarter — elevated from 12 to 16, and linked to the $17M uncommitted Year-1 premium.
OWNER R. Castellanos
STATUS Open — elevated 12 → 16
Mitigation: Re-validated volumes with the three largest IMOs (GC-04); the uncommitted $17M is being worked through I-06 with named wholesaler commitments.
15

## Slide 16
RISK REGISTER
Risk Register (2 of 2)
R-06
Pricing assumptions under peer review
LIKELIHOOD MEDIUM
IMPACT HIGH
Lapse and GLWB-utilization assumptions could prove unsupportable under external actuarial peer review — the risk that drives condition GC-03.
OWNER S. Ravichandran
STATUS Open — active
Mitigation: An independent external actuarial peer review of the GLWB rider pricing is scheduled to complete before Gate 2 (GC-03, on track).
R-08
Illustration engine in the filing window
LIKELIHOOD MEDIUM
IMPACT MEDIUM
The illustration engine's ability to produce compliant hypothetical illustrations inside the filing window — the risk reduced from 16 to 8 as the engine work de-risked.
OWNER E. Kowalczyk
STATUS Open — reduced 16 → 8
Mitigation: Illustration validation was sequenced early against the filing window; the reduction reflects real progress, not a re-scoring.
16

## Slide 17
ISSUES
Issues — Raised & Resolved
Issues that arose during execution and how each was dispositioned — the record of what actually happened, not just what we watched for.
IDENTIFIED ISSUES
ACTION / RESOLUTION
OWNER
STATUS
01
Gate 1 recycled 30 Apr 2026 — distribution volume assumptions were never validated with the wholesaler channel, and the hurdle-rate calc used a superseded capital charge (understated 87 bp)
✓
The economics were corrected (IRR 14.6% → 13.4%, still above hurdle); Gate 1 cleared GO WITH CONDITIONS on 11 Jun; the launch date held
C. Tyrrell
Resolved
02
Brightpath's hypothetical-performance module could not support 2 of the 5 proposed crediting strategies
✓
Closed by scope cut — launch strategies were reduced from five to three (GC-01)
E. Kowalczyk
Resolved
03
Lead pricing-actuary vacancy ran 11 weeks open, sitting on the critical path (realization of R-10)
✓
The role was filled on 08 Sep 2026; the critical-path exposure was retired
G. Marchetti
Closed
04
The configuration environment is shared with an in-flight servicing release, creating test-window contention
✓
Being scheduled around in the Stage 3 plan so the two releases do not collide
V. Sandoval
Open
05
GLWB contract-form language was returned twice by outside counsel over the free-look / death-benefit interaction
✓
A third redraft is with counsel; resolution is tracked ahead of the filing window
A. Nkemelu
Open
06
The plan assumed 6 field wholesalers; Distribution can commit 4 at launch, leaving $17M of Year-1 premium uncommitted
✓
Linked to the GC-04 efficacy finding; named wholesaler commitments are being pursued to close the gap before Gate 2
R. Castellanos
Open
17

## Slide 18
DECISIONS & CHANGES
Decisions & Changes Since Kickoff
Three Gate-1 conditions are closed and the recycle is behind us; the hedging condition and the $17M distribution gap are the live decisions.
Gate 1
Recycled 30 Apr, then GO WITH CONDITIONS on 11 Jun once the capital charge was corrected — IRR 13.4%, above hurdle; launch date held
Gate Review Board Ratified 11 Jun
Conditions
Three of five Gate-1 conditions closed — GC-01 (strategies 5→3), GC-02 (NY removed), GC-04 (IMO volumes re-validated)
Gate Review Board Closed this stage
Needed
Endorse the GC-05 hedging readiness plan and a path to close the $17M Year-1 distribution gap ahead of the Gate 2 decision
Steering Committee This review
18

## Slide 19
NEXT STEPS
The Look-Ahead
1
Now → Gate 2
Complete GC-03 (external peer review) and deliver the GC-05 hedging plan with ISDA milestones
2
Now → Gate 2
Close the $17M distribution gap (I-06) with named wholesaler commitments; resolve the GLWB form (I-05)
3
Apr '27
Gate 2 decision — the go/no-go into launch preparation, launch date held at 6 Mar 2028
19

## Slide 20
QUESTIONS?
Let's build something that sets the gold standard.
C. Tyrrell · NPD Program Manager · Gate Review Board Chair (no vote)
Beacon Index Advantage
All program artifacts available at ct-pm.pages.dev/lighthouse/