## 1 The complete log
Ref | Request | Disposition | Cost | Schedule | Constraint protected | Constraint spent
CR-001 | Extend integration layer to cover 270/271 real-time eligibility | Approved | $780,000 | — | Day 1 integrity | Cost
CR-002 | Add second data-steward cohort for the clerical review band | Approved | $1,240,000 | — | Data integrity | Cost
CR-003 | Add 12 offshore data stewards to work down the review queue | Rejected | — | — | — | —
CR-004 | TSA extension, three months, core admin and IT services | Approved | $3,450,000 | 13 wk | Data integrity | Schedule margin and cost
CR-005 | Extend IMO and workstream leads through revised TSA exit | Approved | $1,260,000 | 13 wk | Data integrity | Cost
CR-006 | Refactor claims adjudication rules engine during migration | Rejected | — | — | TSA exit date | —
CR-007 | Provider network rationalization phase 2 | Deferred | — | — | Schedule and cost | Scope
CR-008 | Care management advanced analytics module | Deferred | — | — | Schedule and cost | Scope
CR-009 | Migrate claims history beyond 7 years | Approved with modification | — | — | TSA exit date | Scope (depth of history)
CR-010 | Accelerate member ID card reissue ahead of Day 1 | Approved | $410,000 | — | Day 1 integrity | Cost
CR-011 | Second Azure landing zone for the retained mainframe facade | Approved | $460,000 | — | Day 1 integrity | Cost
CR-012 | Retention bonus pool extension for Cumberland Valley key talent | Withdrawn | — | — | — | —
Approved change — 6 requests | $7,600,000 | 13 wk

## 2 Reconciliation to the cost ba
Line | Amount | Note
Post-close base estimate | $51,800,000 | Class 2, set at re-baseline
Contingency at 8% | $4,144,000 | Held inside the baseline against identified risk
Cost baseline | $55,944,000 | The figure change control governs
Management reserve | $4,200,000 | Outside the baseline; released by the sponsor
Authorized funding | $60,144,000 | Baseline plus reserve
Bridge
Approved change requests (6) | $7,600,000 | Sum of the approved column above
Absorbed by contingency | −$4,144,000 | Contingency fully consumed
Drawn from management reserve | $3,456,000 | Sponsor decision, not a program one
Actual outturn | $59,400,000 | Cost baseline plus the reserve draw
Variance against cost baseline | +$3,456,000 | Over the baseline
Variance against authorized funding | −$744,000 | Inside authorization
Management reserve remaining | $744,000 | Returned unspent

## About
Change Control Log
Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health, Cumberland Valley Health Plan, Cheatham Mutual Holdings and Rutherford Cloud Operations are fictional entities; no real transaction, rate, or member data is represented.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.