## 2 The cost side
Basis | Amount | Note
Pre-close deal model (Class 5) | $52,500,000 | Estimated under a legal bar on examining member data
Post-close authorization (Class 2) | $60,144,000 | The first estimate built from evidence
Actual integration spend | $59,400,000 | $744,000 returned against authorization
Variance against the deal model | +$11,100,000 | Explained in the Closeout Report and the Change Control Log

## 3 The benefit side runrate by
Synergy source | Year 3 target | Achieved | %
Platform & IT consolidation | $24,000,000 | $21,120,000 | 88%
Provider network rationalization | $19,000,000 | $11,970,000 | 63%
Vendor & contract consolidation | $18,000,000 | $18,000,000 | 100%
Corporate function consolidation | $16,000,000 | $15,040,000 | 94%
Facilities & other | $8,000,000 | $7,200,000 | 90%
Run-rate | $85,000,000 | $73,330,000 | 86%

## 4 Where the case stops being cl
Period | Deal model, cumulative | Actual, cumulative | Variance
Year 1 | $22,000,000 | $19,400,000 | −$2,600,000
Year 2 | $58,000,000 | $47,600,000 | −$10,400,000
Year 3 | $121,000,000 | $106,800,000 | −$14,200,000

## 5 Threeyear position
Line | Amount
Cumulative synergy captured through Year 3 | $106,800,000
Integration spend | −$59,400,000
Net three-year position | $47,400,000
Benefit-to-cost ratio | 1.80 : 1
Net the deal model projected | $68,500,000

## About
Cost-Benefit Analysis
Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health, Cumberland Valley Health Plan, Cheatham Mutual Holdings and Rutherford Cloud Operations are fictional entities; no real transaction, rate, or member data is represented.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.