## Table
Section | Term | Meaning in this suite
The Transaction | Gun-jumping | Acting as a single company before the transaction closes — sharing competitively sensitive information, coordinating pricing, or integrating operations. It is an antitrust violation, not a matter of etiquette, and it is the reason a Clean Team exists.
| Clean Team | An independent team, engaged by ACME Health Legal rather than by the program, permitted to review competitively sensitive information before closing and to return conclusions only, never the underlying records. ⚠ A clean team retained by the party it shields would not be a barrier.
| Carve-out | An acquisition of a subsidiary out of a continuing parent, rather than a whole company. Cumberland Valley Health Plan is carved out of its parent, which keeps operating and keeps providing shared services after close. The continuing seller is what makes a TSA coherent.
| Whole-company merger | The contrasting case: shareholders take cash and the selling entity ceases to exist. There is no continuing counterparty, so there is nobody to provide transitional services and no TSA to exit.
| HSR clearance | Federal antitrust clearance under Hart-Scott-Rodino. One of two gates this transaction could not close without.
| Form A | State insurance regulator approval of a change of control of an insurer. The second gate, and the one that attaches conditions — on this program a condition barring offshore handling of member data.
Day 1 and What Follows | Day 1 | The first day of common ownership — October 2, 2023 here. Legal, regulatory and operational continuity must hold from that morning.
| Integrated | The state in which two organizations run as one on one set of systems. ⚠ Day 1 is not integrated, and conflating the two is the classic first-timer error. On this program Day 1 and integration are separated by roughly fifteen months.
| Day 100 | A checkpoint, not a gate — January 9, 2024. It asks whether the program is stable enough to continue on plan, and on this program it recorded that the review population was still unquantified.
Transitional Services | Transition Services Agreement (TSA) | A contract under which the seller continues to provide named services to the sold business for a defined period. ⚠ A TSA obliges the seller to PROVIDE a service. It does not oblige the seller to make the buyer CAPABLE of it.
| TSA exit | Standing a service up independently and switching the seller off. Exiting the TSA is the integration — the migrations exist to make each exit possible.
| Reverse shadowing | The acceptance test for knowledge transfer: the buyer performs the task while the provider observes. Watching someone else do it is not evidence of capability.
Contracts and Vendors | Assignment | Transferring the benefit of a contract to another party. Often permitted, and often not sufficient — it can leave the original party still liable.
| Novation | Replacing one party to a contract with another by agreement of all three, so the original party is released. ⚠ Where an entity's form changes at close, novation rather than assignment is usually what is actually required.
| Change-of-control clause | A contract term triggered by a change in ownership, giving the counterparty rights — consent, repricing, or termination. 12 inherited agreements carry one here and 3 confer an outright termination right.
| Business Associate Agreement (BAA) | A HIPAA-required contract with any party handling protected health information on the covered entity's behalf. 16 are required at close. ⚠ The divesting parent is a business associate — it hosts member data under the TSA, and it is the one most often missed because nobody files the seller under “vendors.”
Insurance Entities | Statutory merger | Combining two insurance entities with the approval of the domiciliary regulator. One route to consolidating a book of business.
| Assumption reinsurance | The other route: the acquiring insurer assumes the policies, generally with policyholder notice and regulatory approval. ⚠ A book of business cannot be moved the way a company can — policies are contracts with members, so consolidation is a regulated act, not a corporate one.
Estimating | AACE estimate class | A five-point scale for how much an estimate can be trusted, from Class 5 (concept screening, prepared with almost no data) to Class 1. The class is a property of the information available, not of the estimator's effort.
| Progressive elaboration | The PMI principle that plans become more accurate as more is known. It is the reason a program is not held to its first number.
| Class 5, legally imposed | ⚠ The M&A sharpening. Here the Class 5 condition was not sloppiness — antitrust law barred examining member-level data before close, so the first estimate was structurally guaranteed to be unreliable. The overrun is a consequence of the law, not of the estimating.
Baselines and Change | Baseline 1 — the deal model | The pre-close estimate: base $42M plus $6.3M contingency, $52.5M authorized. AACE Class 5, prepared under the prohibition above.
| Baseline 2 — the re-baseline | The first estimate produced with the data: base $51.8M, $60.1M authorized. AACE Class 2.
| Re-baseline | ⚠ An event, not change control. Change control governs movement away from a baseline; it cannot govern the arrival of the first credible one. The re-baseline replaces the plan rather than amending it, and it is approved by the Steering Committee, not by the change board.
| Change control | The mechanism that bridges Baseline 2 to actual. Approved changes total $7.6M against a final outturn of $59.4M. ⚠ The log must reconcile exactly — it is the arithmetic that makes the ending auditable.
Schedule | Float | A by-product of the network: time that exists because of how activities are sequenced. Nobody bought it and nobody decides to spend it.
| Margin | ⚠ Not float. The gap between the planned TSA exit and the contractual maximum was bought at signing. Spending it is a Steering Committee decision, not a scheduling adjustment. 90 days of it were still unused at exit.
| Late but whole | The ending this program actually had: TSA exit on December 31, 2024 against a contractual maximum of March 31, 2025. Consuming negotiated margin is a win; breaching a contractual maximum is a governance failure.
Member Identity | EMPI | Enterprise master patient index — the single index of members across the combined 2,220,000.
| Clerical review band | The third outcome of matching, between automatic match and automatic non-match, worked by trained stewards. Assumed at 8% of records; it came in at 26%.
| False positive | A merge of two different people. ⚠ The two matching errors are not symmetrical. A false negative leaves a duplicate, which is visible and fixable; a false positive puts one member's history under another's identity, and nothing in normal operations surfaces it.
Synergy | Run-rate synergy | The annualized saving in force at a point in time. The commitment here is $85M by the end of Year 3.
| Cumulative capture | What was actually banked along the way — a different number from run-rate, and $14.2M behind the model here. ⚠ Reporting only the flattering one is the most available way to mislead a steering committee.
| Dis-synergy | Costs the transaction creates rather than removes. An allowance of $6M is carried, because a plan that tracks only benefits always reports favorably.

## About
Glossary
Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health and Cumberland Valley Health Plan are fictional entities; no real transaction, rate, or member data is represented.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.