## Slide 1
PROGRAM KICKOFF · PRE-CLOSE · INTEGRATION PLANNING
Cumberland Valley
Integration Program
Buying a health plan is the easy part. This program has eighteen months of borrowed services to become independent of the company we bought it from.
March 20, 2023
Kickoff Date
C. Tyrrell
Program Manager
58
People (pre-close)
$52.5M
Authorized Budget

## Slide 2
AGENDA
What We'll Cover Today
1
Welcome & Deal Context
2
Why This Is Hard — The Carve-Out
3
Objectives & Success Criteria
4
Scope: In and Out
5
Teams & Delivery Model
6
Governance & Decision Rights
7
Schedule & Phase Gates
8
Budget Overview
9
Forecast & Earned Value
10
How We'll Work Together
11
Risks We're Watching
12
Decisions Ratified
13
Next Steps & Q&A
2

## Slide 3
WELCOME
Glad You're Here
Fifty-eight people start today on a program that legally cannot touch the thing it is planning to integrate — and that constraint shapes everything on the next eighteen slides.
ACME Health is acquiring Cumberland Valley Health Plan, roughly 420,000 members, in a carve-out from its parent company. Signing is done; closing is expected in the third quarter once regulatory approvals clear. Until that day we may not examine member-level data or begin integrating — doing so would be gun-jumping — so planning runs through a Clean Team under protocol. At close, the parent keeps providing shared services on a meter, and exiting those services is the integration. Today aligns the team and the Steering Committee on scope, governance, change control and cadence before detailed planning begins.
58
People at kickoff
420,000
Members acquired
$52.5M
Authorized budget
3

## Slide 4
THE BUSINESS CASE
Why We're Doing This
This is a carve-out, not a merger — and that single fact explains why the transitional services agreement exists and why exiting it is the real program.
Cumberland Valley is being divested by a parent that keeps running its payroll, its general ledger, its data center and its core administration platform on the day we close. In a whole-company merger the shareholders take cash and there is no continuing seller; here there is, and we are renting our own operations back from them on a meter. The transitional services term runs twelve months against an eighteen-month contractual maximum. Every workstream on this program ultimately answers one question: what has to be true before we can stop paying the seller to be us?
KEY FACTS
Structure
Carve-out from a parent company
Members
~420,000 joining ~1.8M
Baseline
$52.5M authorized (Class 5 deal model)
Real deadline
Transitional services exit, not close
4

## Slide 5
SUCCESS METRICS
What Success Looks Like
1
Close the transaction with every regulatory condition satisfied — no approval slips onto the integration critical path
2
Reach Day 1 with member-facing continuity intact — members keep their coverage, their cards work, their claims pay
3
Exit every transitional service inside the contractual maximum, with ACME demonstrably able to operate what it inherits
4
Resolve two member databases into one enterprise identity with no false merges — the error nothing in operations surfaces
5
Deliver the $85M run-rate synergy case by Year 3 without spending data integrity or Day 1 continuity to get there
5

## Slide 6
SCOPE
Where the Lines Are
IN SCOPE
✓
Regulatory approval & close readiness
HSR clearance, Form A filing, closing conditions
✓
Day 1 operational readiness
Member continuity, ID cards, eligibility, claims payment
✓
Transitional services exit
Six services, each with its own exit criteria and evidence
✓
Member identity resolution
Two member files into one enterprise identifier
✓
Platform, cloud & integration
Core administration consolidation, Azure migration, fourteen interfaces
✓
Synergy realization
Vendor, network, platform, corporate and facilities consolidation
OUT OF SCOPE (CANDIDATE BACKLOG)
✕
Anything before close that touches member data
Barred by antitrust — planning runs through the Clean Team
✕
Legal entity consolidation
Evaluated as an option; not a dependency of this program
✕
Benefit or product redesign
A redesigned benefit cannot be validated by parallel run
✕
Run-state operations after warranty
Transfers to the receiving organizations at closeout
6

## Slide 7
TEAMS
Everyone Who's Building This
58 people at kickoff — the pre-close roster. ⚠ This team legally changes shape at close: the Clean Team dissolves the day the transaction completes, and the data-steward function that resolves member identity cannot be hired until there is member data to work. Full named roster in the Resource Plan.
6
Steering Committee & Sponsorship
Sponsor: D. Ashmore, EVP & CFO
4
Integration Management Office
Lead: C. Tyrrell, Program Manager
4
Clean Team — pre-close only
Lead: P. Marchetti · dissolves at close
18
Technology Workstreams
W. Ferriday · Dr. A. Ravindran · K. Stallworth · B. Trammell
10
Business Workstreams
J. Kirkendall · T. Ruffalo · Dr. M. Ellsworth · E. Wetherby
16
Corporate Functions & Control
F. Underhill · H. Castellow · A. Quintanilla · L. Braithwaite
7

## Slide 8
GOVERNANCE
Who Decides What
Authority scales with the risk and impact of the decision, and one boundary is absolute: before close, nothing that would constitute integrating the two businesses may be decided at all, regardless of who wants to decide it. Any cost- or scope-impacting change goes to the Change Control Board, not informal PM approval.
Tier 1
Planning and task decisions within approved scope and the PM's delegated authority
Program Manager (C. Tyrrell)
Tier 2
Cost, scope, or schedule change exceeding PM authority
Change Control Board → Steering Committee
Tier 3
Strategic direction, program continuation, budget and reserve authority
Executive Sponsor (D. Ashmore, EVP & CFO)
Absolute
Anything constituting pre-close integration — gun-jumping exposure
Clean Team protocol (P. Marchetti) + Legal (F. Underhill)
8

## Slide 9
TIMELINE
Signing to Close to a Clean TSA Exit
Two clocks run at once — regulatory approval sets the close date, and the transitional services term starts counting the day after it.
Pre-Close Planning
Clean Team, regulatory, Day 1 design · Feb–Sep '23
Close & Day 1
Cutover, member continuity · Sep–Oct '23
Stabilize & Re-Baseline
Day 100, first credible estimate · Oct '23–Jan '24
Integrate & Migrate
Platform, cloud, identity, interfaces · Jan–Sep '24
TSA Exit & Closeout
Service-by-service exit, handover · Sep '24–Apr '25
KEY MILESTONES
Feb 13 '23
Definitive agreement signed
Mar 20 '23
Integration kickoff — planning begins
Q2 '23
Antitrust clearance expected
Q3 '23
Insurance regulatory approval expected
Q3 '23
Expected close → Day 1
Q1 '24
Day 100 review and re-baseline
9

## Slide 10
TIMELINE · DETAIL
Project Phases — Detailed View
The program as a work view — bars show when each workstream runs and where they overlap.
Q1 '23
Q2 '23
Q3 '23
Q4 '23
Q1 '24
Q2 '24
Q3 '24
Q4 '24
FY
Pre-Close (Clean Team protocol)
Regulatory filings & clearance
Day 1 readiness planning
Clean Team analysis
Close & Stabilize
Close & Day 1 cutover
Stabilization & Day 100
Re-baseline (Class 2)
Integrate (parallel)
Member identity resolution
Core administration consolidation
Cloud migration waves
Interface build & cutover
Exit
Transitional service exits
Knowledge transfer & acceptance
10

## Slide 11
BUDGET
Where the Money Goes
TOTAL PROGRAM BUDGET $52.5M
Core Administration Consolidation
$9,400,000
Claims and enrollment platform absorption
Member Identity Resolution & Data Migration
$7,600,000
EMPI platform, migration, stewardship capacity
Cloud Migration & Infrastructure
$8,200,000
Azure landing zone, migration waves, co-managed operations
Integration Layer & Interfaces
$5,300,000
Canonical model and fourteen interfaces
Program Management, Governance & Advisory
$4,900,000
IMO, Clean Team, consulting engagement
Transitional Services Charges
$4,100,000
Paid to the divesting parent through the term
Business Workstreams & Change
$2,500,000
Network, care management, member services, communications
Contingency Reserve (15% of base)
$6,300,000
Class 5 estimate — drawn only through the Change Control Board
Management Reserve
$4,200,000
Held outside the cost baseline; released by the Sponsor
Base estimate $42.0M plus 15% contingency gives a $48.3M cost baseline; management reserve takes authorized funding to $52.5M. ⚠ This is a Class 5 estimate and the contingency is 15% for a reason — see slide 12.
11

## Slide 12
FORECAST & VARIANCE
How We Forecast — Earned Value, Not Burn-Down
This is a predictive, phase-gated program managed to a cost baseline — but the baseline you are looking at is the least reliable one this program will ever have.
Antitrust law bars an acquirer from examining the target's member-level records before closing. The identity-resolution estimate underneath this budget therefore assumes roughly 65% of records resolve on exact matching and a further 27% automatically, leaving about 8% for manual review — assumptions carried from the deal model, not measurements. Nobody on this program is permitted to verify them until after close. That is why contingency sits at 15% rather than the 8-10% a well-specified program would carry, and why a formal re-baseline is planned once the first lawful profiling run completes. Estimate class is a statement about available evidence, not about effort.
$52.5M
Authorized (Class 5 deal model)
15%
Contingency — held against a blind estimate
Post-close
Re-baseline planned, Class 2
12

## Slide 13
WORKING TOGETHER
How We'll Stay in Sync
CADENCE
FORUM
PURPOSE
Weekly
Integration Management Office
Workstream status in, one unified report out
Weekly
Vendor check-ins — individually
Never a joint forum; delivery problems are commercially sensitive
Monthly
Steering Committee
Formal program-health review with the Executive Sponsor
As needed
Change Control Board
Cost- or scope-impacting change requests
Standing
Clean Team clearance
Any request touching target data, before it is actioned
13

## Slide 14
RISKS
Risks and Mitigation
The full register at a glance — each risk with its mitigation, likelihood, and impact; detailed cards follow.
IDENTIFIED RISKS
MITIGATION STRATEGY
LIKELIHOOD
IMPACT
01
Member identity resolution volume
✓
Profiling first post-close; 15% contingency; re-baseline planned
High
High
02
Regulatory approval timing
✓
Early filing; Day 1 planned to a window, not a fixed date
Medium
High
03
Key talent departure at the target
✓
Retention tied to knowledge transfer, not presence
Medium
High
04
First-time cloud adoption
✓
Rehost now, optimize after exit; landing zone before waves
Medium
Medium
14

## Slide 15
RISKS WE'RE WATCHING
Risks We're Watching (1 of 2)
R-01
Member identity resolution volume
LIKELIHOOD HIGH
IMPACT HIGH
The share of member records needing manual review is an assumption we are legally barred from testing before close. If the real figure is materially higher, identity resolution becomes the critical path and the transitional services term is the thing at risk.
OWNER Dr. A. Ravindran
STATUS Open — highest attention
Mitigation: Profiling scheduled as the first substantive post-close data activity; steward capacity sized with headroom; 15% contingency held; re-baseline planned rather than assumed away.
R-02
Regulatory approval timing
LIKELIHOOD MEDIUM
IMPACT HIGH
Insurance regulatory approval is outside the program's control and sets the close date, which in turn starts the transitional services clock. A slip moves every downstream date.
OWNER R. Cadwallader
STATUS Open
Mitigation: Filing prepared early with pre-submission engagement; Day 1 plans built to a window rather than a fixed date so a slip re-times rather than re-plans.
15

## Slide 16
RISKS WE'RE WATCHING
Risks We're Watching (2 of 2)
R-03
Key talent departure at the target
LIKELIHOOD MEDIUM
IMPACT HIGH
The program depends for twelve to fifteen months on Cumberland Valley staff whose own futures are being decided, and they know it. The knowledge that matters is undocumented and sits with mid-level analysts, not executives.
OWNER D. Marchbanks
STATUS Open
Mitigation: Retention agreements scoped to knowledge transfer obligations rather than presence; transfer treated as a deliverable with named receivers and acceptance criteria.
R-04
First-time cloud adoption
LIKELIHOOD MEDIUM
IMPACT MEDIUM
ACME has never operated a cloud platform and cannot wait to become mature before migrating — the transitional services clock does not pause for a learning curve.
OWNER B. Trammell
STATUS Open
Mitigation: Rehost first and optimize after exit; landing zone before any wave; co-managed operating model with a contracted step-down so capability transfers rather than being assumed.
16

## Slide 17
DECISIONS RATIFIED
Decisions We're Starting With
Three decisions are already ratified going into planning — captured here so no one has to reconstruct them later.
D-01
Mixed integration thesis adopted — absorb, preserve, or best-of-both decided per capability rather than one blanket approach
Steering Committee At charter
D-02
Clean Team protocol adopted; no ACME staff member sees target member-level data before close
F. Underhill / P. Marchetti At charter
D-03
Cloud operating model set to co-managed with a contracted step-down, rather than build-our-own or fully outsourced
D. Ashmore, on B. Trammell's recommendation At kickoff
17

## Slide 18
NEXT STEPS
What Happens Next
1
Within 2 weeks
Work breakdown structure and schedule baseline finalized
2
This quarter
Transitional services schedule negotiated service by service, with exit criteria
3
Before close
Day 1 readiness plan complete and rehearsed under Clean Team control
18

## Slide 19
QUESTIONS?
Let's build something that sets the gold standard.
C. Tyrrell · Program Manager, Integration
ACME Health / Cumberland Valley Health Plan Integration
All program artifacts available at ct-pm.pages.dev/ma-integration/