Organization Chart

Organization · Artifact 31 · how to read this suite

The integration program organization as at March 11, 2024 — 84 people across two companies and five outside firms, in 17 delivery workstreams. Page 1 is the executive view — sponsor, program manager, governance bodies and the 17 workstream leads. Pages 2 to 4 draw each group of teams in full, because a single diagram at this scale can only show leaders and the teams underneath them are the part worth seeing. Contract vehicle per person is in the Resource Plan.

These charts show accountability, not employment, and on this program the two barely overlap. The Program Manager is a consultant: he leads the Integration Management Office and employs nobody in it. Workstream leads report to their own executives. Roughly half the boxes belong to people whose review, salary and continued employment are decided by someone who appears nowhere on these pages. His authority is written into an engagement contract rather than an organization chart — the normal condition for an integration program, and the reason the governance model matters more here than the reporting lines do.

Page 1 — Executive Leadership and Governance

Diagram 1

|  |  |  |  |  | OUTSIDE THE PROGRAM |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | ACME Board of Directors |  |  |  |  |
|  |  |  |  |  |  | Clean Team |
|  |  |  |  |  |  | 4 people · both General Counsel · pre-close |
|  |  | Integration Steering Committee |  |  |  |  |
|  |  | 6 executives · gate approvals · escalation |  |  |  |  |
|  |  |  |  |  |  | Cheatham Mutual Holdings |
|  |  |  |  |  |  | TSA provider · divesting parent |
|  |  | C. Tyrrell |  |  |  |  |
|  |  | Program Manager · consultant · employs nobody |  |  |  |  |
|  |  |  |  |  |  | Human Resources |
|  |  |  |  |  |  | retention · severance · outside the budget |
| Claims & Core | Data & EMPI | Application | Cloud & | Business | Corporate |  |
| Administration |  | Integration | Infrastructure | Operations | and Control |  |
| W. Ferriday · 11 people | Dr. A. Ravindran · 11 people | K. Stallworth · 11 people | B. Trammell · 7 people | 4 workstreams · 8 people | 9 workstreams · 21 people |  |
| D. Halloran | C. Bhattacharya | J. Amonett | G. Whitmire | Paired counterparts |  |  |
| counterpart | counterpart | counterpart | counterpart | Cumberland Valley |  |  |
| Solid lines: accountability into the program. |  |  |  |  |  |  |
| Dashed: paired counterpart, jointly accountable for the same deliverables. |  |  |  |  |  |  |
| Gold: bodies the program depends on and does not direct. |  |  |  |  |  |  |

Reporting line, named

ACME Health Board of Directors — Transaction approved Feb 13, 2023

D. Ashmore — EVP & Chief Financial Officer — Executive Sponsor

C. Tyrrell — Program Manager, Integration (engagement lead)

Governance bodies

Integration Steering Committee 6

D. Ashmore — EVP & Chief Financial Officer, ACME — Executi…

R. Villanueva — Chief Operating Officer, ACME

M. Kessinger — President & CEO, Cumberland Valley

T. Broadnax — SVP Corporate Development, ACME

L. Hollingsworth — General Counsel, ACME

S. Achebe — Chief Information Officer, ACME

Integration Management Office 4

N. Farnsworth — PMO Analyst

J. Petrosyan — Synergy & Financial Analyst

A. Winterbourne — Change & Communications Lead

G. Threadgill — TSA Manager — owns exit

Reports to the Sponsor. Employs nobody on the program.

Clean Team 4

P. Marchetti — Clean Team Lead

K. Oyelaran — Clean Team Analyst — pricing & network rates

B. Sandoval — Clean Team Analyst — membership & claims volu…

H. Tillinghast — Clean Team Counsel (outside)

⚠ Reports to both General Counsel. No line into the IMO.

Workstream leads — 17 workstreams, each an ACME lead paired with a Cumberland Valley counterpart

| Workstream | ACME lead | Cumberland Valley counterpart | People |
| --- | --- | --- | --- |
| Claims & Core Administration | W. Ferriday — VP Claims Operations, ACME — Workstream Lead | D. Halloran — Business Analyst — enrollment & eligibility | 11 |
| Data & EMPI | Dr. A. Ravindran — Director, Enterprise Data Management, ACME … | C. Bhattacharya — Manager, Member Data, Cumberland Valley | 11 |
| Application Integration | K. Stallworth — Director, Enterprise Integration, ACME — Wo… | J. Amonett — Manager, Interfaces, Cumberland Valley | 11 |
| Cloud & Infrastructure | B. Trammell — VP Infrastructure, ACME — Workstream Lead | G. Whitmire — Director, IT Operations, Cumberland Valley | 7 |
| Provider Network | J. Kirkendall — VP Network Management, ACME — Workstream Le… | A. Boudreaux — Director, Provider Contracting, Cumberland … | 2 |
| Care Management | Dr. M. Ellsworth — Chief Medical Officer, ACME — Workstream Le… | Dr. P. Nwachukwu — VP Care Management, Cumberland Valley | 2 |
| Member Services | T. Ruffalo — VP Member Experience, ACME — Workstream Lead | C. Hollifield — Director, Member Services, Cumberland Valley | 2 |
| Finance & Accounting | S. Beauregard — VP Financial Planning & Analysis, ACME — Wo… | N. Applewhite — Controller, Cumberland Valley | 2 |
| HR & Talent | D. Marchbanks — SVP Human Resources, ACME — Workstream Lead | K. Osterhout — Director, HR Business Partner, Cumberland V… | 2 |
| Legal & Regulatory | F. Underhill — Associate General Counsel, M&A, ACME — Work… | M. Sheffield — General Counsel, Cumberland Valley | 3 |
| Compliance & Privacy | L. Braithwaite — Chief Privacy Officer, ACME — Workstream Le… | J. Ferrandino — Compliance Director, Cumberland Valley | 2 |
| Security | A. Quintanilla — Chief Information Security Officer, ACME — … | P. Hasenfratz — Manager, Information Security, Cumberland V… | 2 |
| Actuarial & Underwriting | E. Wetherby — VP Actuarial Services, ACME — Workstream Le… | C. Adeyemi — Chief Actuary, Cumberland Valley | 2 |
| Communications | B. Lundquist — VP Corporate Communications, ACME — Workstr… | R. Tomlinson — Director, Communications, Cumberland Valley | 2 |
| Vendor & Contract Management | H. Castellow — VP Procurement, ACME — Workstream Lead | D. Achterberg — Director, Vendor Management, Cumberland Val… | 3 |
| Facilities | W. Pickering — Director, Corporate Real Estate, ACME — Wor… | S. Grimsley — Facilities Manager, Cumberland Valley | 2 |
| EDI Transaction Assurance |  |  | 3 |

Page 2 — Core Delivery

The four workstreams that carry most of the program budget and the whole of the critical path.

Diagram 2

| Claims & Core Administration | Data & EMPI | Application Integration | Cloud & Infrastructure |
| --- | --- | --- | --- |
| 11 people | 11 people | 11 people | 7 people |
| W. Ferriday | Dr. A. Ravindran | K. Stallworth | B. Trammell |
| VP Claims Operations, ACME — Workstream L… | Director, Enterprise Data Management, ACM… | Director, Enterprise Integration, ACME — … | VP Infrastructure, ACME — Workstream Lead |
| D. Halloran | C. Bhattacharya | J. Amonett | G. Whitmire |
| Business Analyst — enrollment & eligibili… | Manager, Member Data, Cumberland Valley | Manager, Interfaces, Cumberland Valley | Director, IT Operations, Cumberland Valley |
| R. Sedgwick | P. Ramaswamy | K. Balasubramanian | C. Larkspur |
| Business Analyst — benefit configuration | Senior Data Engineer, EMPI Build | Business Analyst — interface requirements | Release & Environment Manager |
| M. Prideaux | M. Thibodeaux | A. Feldstein | H. Sandifer |
| Configuration Analyst, Core Administration | Data Architect, ACME | Senior Engineer, Interface Build | Manager, Platform Engineering, ACME |
| J. Whitfield | S. Wrenfield | B. Nkemdirim | E. Kalinowski |
| Configuration Analyst, Claims — retiring … | Principal Consultant, Identity Resolution | Test Manager — equivalence testing (onsho… | Cloud Architect — landing zone |
| S. Coventry | I. Duvernay | R. Delacroix | D. Fontenot |
| QA Analyst — parallel run reconciliation | Senior Data Engineer, Matching & Survivor… | Integration Architect — canonical model | Senior Cloud Engineer, Migration Waves |
| T. Calloway | Y. Abegunde | O. Hargrave | R. Ilesanmi |
| QA Analyst — parallel run reconciliation | Data Quality Analyst | Senior Engineer, Integration Layer | FinOps Analyst — tagging, showback, reser… |
| E. Nakagawa | L. Pemberton | V. Krishnamoorthy |  |
| Director, Core Admin Platform, ACME | Data Steward — clerical review queue | Offshore Delivery Manager |  |
| R. Lattimore | F. Guerrero | P. Devarakonda |  |
| VP Claims, Cumberland Valley — Counterpart | Data Steward — clerical review queue | Test Lead, Integration |  |
| D. Okpara | N. Ojukwu | S. Mahadevan |  |
| Manager, Claims Configuration, Cumberland… | Data Steward — clerical review queue | QA Engineer, Interface Regression |  |
| V. Castellanos | T. Vandiver | A. Vaidyanathan |  |
| Principal Consultant, Core Admin Migration | Data Steward Supervisor — SLA owner | QA Engineer, Interface Regression |  |

Page 3 — Business Operations

Member, provider and clinical functions — small teams, and every one of them paired across both companies.

Diagram 3

| Provider Network | Care Management | Member Services | Actuarial & Underwriting |
| --- | --- | --- | --- |
| 2 people | 2 people | 2 people | 2 people |
| J. Kirkendall | Dr. M. Ellsworth | T. Ruffalo | E. Wetherby |
| VP Network Management, ACME — Workstream … | Chief Medical Officer, ACME — Workstream … | VP Member Experience, ACME — Workstream L… | VP Actuarial Services, ACME — Workstream … |
| A. Boudreaux | Dr. P. Nwachukwu | C. Hollifield | C. Adeyemi |
| Director, Provider Contracting, Cumberlan… | VP Care Management, Cumberland Valley | Director, Member Services, Cumberland Val… | Chief Actuary, Cumberland Valley |

Page 4 — Corporate and Control

Finance, legal, risk and the assurance vendors.

Diagram 4

| Finance & Accounting | HR & Talent | Legal & Regulatory | Compliance & Privacy |
| --- | --- | --- | --- |
| 2 people | 2 people | 3 people | 2 people |
| S. Beauregard | D. Marchbanks | F. Underhill | L. Braithwaite |
| VP Financial Planning & Analysis, ACME — … | SVP Human Resources, ACME — Workstream Le… | Associate General Counsel, M&A, ACME — Wo… | Chief Privacy Officer, ACME — Workstream … |
| N. Applewhite | K. Osterhout | M. Sheffield | J. Ferrandino |
| Controller, Cumberland Valley | Director, HR Business Partner, Cumberland… | General Counsel, Cumberland Valley | Compliance Director, Cumberland Valley |
|  |  | R. Cadwallader |  |
|  |  | Director, Regulatory Affairs, ACME — DOI … |  |
| Security | Communications | Vendor & Contract Management | Facilities |
| 2 people | 2 people | 3 people | 2 people |
| A. Quintanilla | B. Lundquist | H. Castellow | W. Pickering |
| Chief Information Security Officer, ACME … | VP Corporate Communications, ACME — Works… | VP Procurement, ACME — Workstream Lead | Director, Corporate Real Estate, ACME — W… |
| P. Hasenfratz | R. Tomlinson | D. Achterberg | S. Grimsley |
| Manager, Information Security, Cumberland… | Director, Communications, Cumberland Vall… | Director, Vendor Management, Cumberland V… | Facilities Manager, Cumberland Valley |
|  |  | M. Rousseau |  |
|  |  | Contracts Consultant — change-of-control … |  |
|  |  | EDI Transaction Assurance |  |
|  |  | 3 people |  |
|  | N. Reinhardt |  |  |
|  | Engagement Lead, X12 Assurance |  |  |
|  | T. Osei-Bonsu |  |  |
|  | Senior EDI Analyst — 834 enrollment, 820 … |  |  |
|  | L. Marchesi |  |  |
|  | Senior EDI Analyst — 837/835 claims & rem… |  |  |

What These Charts Do Not Show

| Not shown | Why it matters |
| --- | --- |
| Line management | Nobody here reports to the Program Manager. Workstream leads are accountable to the program and employed elsewhere. |
| Who decides someone's future | ⚠ Target-side staff are managed by executives who may not be here in a year, and they know it. Sixteen roles carry retention agreements; every one is at Cumberland Valley. |
| Capacity | A box is not a full-time person. Several appear for a monthly meeting. The Resource Plan carries effort; these pages carry accountability. |
| The shape after closing | The roster went from 58 pre-close to 80 post-close and changed composition, not just size — the Clean Team left and the data stewards arrived. |

The second row is the one an integration program manager learns to hold in mind. A counterpart at the acquired company is being asked to document how their systems work, transfer that knowledge to the acquirer, and hit dates — while the same program decides whether their function survives. Nothing in a reporting line manages that, and no amount of goodwill substitutes for naming it. It is why knowledge transfer is contracted as a deliverable with named receivers rather than assumed as a by-product of people being helpful.

Related artifacts: 1 — Integration Charter · 5 — Clean Team Protocol · 8 — Consulting SOW · 9 — Integration Management Plan · 14 — Resource Plan · 19 — Retention & Key Talent

Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health, Cumberland Valley Health Plan and Cheatham Mutual Holdings are fictional entities; no real transaction, rate, or member data is represented.