## 1 Two Baselines and Why (1)
Component | Baseline 1 deal model, Feb 2023 | Baseline 2 re-baseline, Jan 2024 | Movement
Base estimate | $42,000,000 | $51,800,000 | +$9,800,000
Contingency | $6,300,000 15% of base | $4,144,000 8% of base | −$2,156,000
Cost baseline | $48,300,000 | $55,944,000 | +$7,644,000
Management reserve | $4,200,000 | $4,200,000 | —
Total authorized | $52,500,000 | $60,144,000 | +$7,644,000

## 1 Two Baselines and Why (2)
Baseline | Estimate class | Expected accuracy | Basis
1 — deal model | Class 5, concept screening | −20% to +50% or wider | ⚠ Benchmarks and management representations. No member-level data examined.
2 — re-baseline | Class 2, control | −5% to +15% | Post-close discovery, WBS decomposed to 54 work packages, resource plan costed from a rate card

## 2 Contingency and Management Re
Instrument | Amount | Controlled by | Draw triggers
Contingency | $4,144,000 | Program Manager, to $250,000; Sponsor above | Known unknowns inside scope — estimating variance, defect remediation, rework
Management reserve | $4,200,000 | ⚠ Executive Sponsor, at any amount | Events outside the plan. Each draw reported individually to the Steering Committee.

## 3 Cost by Control Account
Ref | Control account | Budget | % | Owner
1.3 | Data Migration & Identity Resolution | $11,400,000 | 22.0 | Dr. A. Ravindran
1.4 | Core Administration Consolidation | $8,900,000 | 17.2 | W. Ferriday
1.5 | Cloud Migration & Infrastructure | $7,800,000 | 15.1 | B. Trammell
1.6 | Integration Architecture & Interfaces | $5,200,000 | 10.0 | R. Delacroix
1.1 | Program Management & IMO | $4,200,000 | 8.1 | C. Tyrrell
1.2 | Day 1 Readiness & Cutover | $3,600,000 | 7.0 | R. Villanueva
1.7 | TSA Exit & Knowledge Transfer | $2,700,000 | 5.2 | G. Threadgill
1.9 | Organization, Change & Communications | $2,400,000 | 4.6 | A. Winterbourne
1.8 | Provider Network & Care Management | $2,000,000 | 3.9 | J. Kirkendall
1.10 | Vendor & Contract Consolidation | $1,900,000 | 3.7 | H. Castellow
1.11 | Legal, Regulatory & Compliance | $1,700,000 | 3.3 | F. Underhill
| Base estimate | $51,800,000 | 100 | Reconciles to the WBS

## 4 Spend to Date and Forecast
Position | Amount | Of base | Note
Spent to March 4, 2024 | $17,300,000 | 33.4% | Front-loaded by Day 1 readiness and landing zone build
Committed, not yet spent | $6,900,000 | 13.3% | Contracted vendor work and appliance transfer
Remaining base | $27,600,000 | 53.3% | Weighted toward identity resolution and core admin cutover
Base estimate | $51,800,000 | 100%
Contingency drawn to date | $620,000 | 15.0% of contingency | Interface rework and an extended landing zone security review
Management reserve drawn | $0 | — | ⚠ Nothing outside the plan has occurred

## 5 Cost to Achieve Against Syner
Position | Amount | Character
Committed synergy, run-rate by Year 3 | $85,000,000 | Recurring, annual
Dis-synergy allowance, netted inside | $6,000,000 | Recurring, annual
Program cost to achieve, authorized | $60,144,000 | One-time

## 6 What This Budget Does Not Con
Cost | Carried by | Why it sits outside
TSA service fees | Receiving functions, as operating cost | ⭐ Deliberate. The function slow to absorb a service should feel the cost of being slow. Putting the fees in the program budget would insulate them from it.
Retention payments | Human Resources | The program identifies the roles; it does not price them. ⚠ Sixteen roles, all at Cumberland Valley.
Severance and restructuring | Corporate | A consequence of the transaction, not of the integration program
Transaction costs — advisory, legal, financing | Corporate Development | Incurred before the program existed

## 7 Authority and Change Control
Decision | Approver | Instrument
Reallocation within a control account | Program Manager | Recorded, no change request
Reallocation between control accounts, under $250,000 | Program Manager | Change request
Cost impact $250,000 to $1,000,000 | Executive Sponsor | Change request
Cost impact above $1,000,000 | Steering Committee | Change request
Any draw on management reserve | Executive Sponsor | ⚠ At any amount, reported individually
Change to the cost baseline itself | Steering Committee | Re-baseline, not a change request

## About
Program Budget
Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health, Cumberland Valley Health Plan and Cheatham Mutual Holdings are fictional entities; no real transaction, rate, or member data is represented.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.