## WBS
WBS | Level | Task | Assigned to | Budget | Start | Finish | Days
1 | 1 | ACME Health / Cumberland Valley Health Plan Integration Program | C. Tyrrell | 51800000 | 2023-10-02 | 2025-12-16 | 576
1.1 | 2 | Program Management & IMO | C. Tyrrell | 4200000 | 2023-10-02 | 2023-12-05 | 46
1.1.1 | 3 | Program planning & baseline control | N. Farnsworth | 900000 | 2023-10-02 | 2023-10-13 | 9
1.1.2 | 3 | Status, steering & synergy reporting | J. Petrosyan | 850000 | 2023-10-06 | 2023-10-19 | 9
1.1.3 | 3 | Change control administration | A. Winterbourne | 550000 | 2023-10-12 | 2023-10-20 | 6
1.1.4 | 3 | Risk, issue & dependency management | C. Tyrrell | 600000 | 2023-10-17 | 2023-10-25 | 6
1.1.5 | 3 | Program closeout & lessons learned | N. Farnsworth | 400000 | 2023-10-20 | 2023-10-27 | 5
1.1.6 | 3 | IMO tooling & document control | J. Petrosyan | 900000 | 2023-10-25 | 2023-11-07 | 9
1.2 | 2 | Day 1 Readiness & Cutover | R. Villanueva | 3600000 | 2023-10-16 | 2023-12-11 | 40
1.2.1 | 3 | Day 1 readiness assessment & runbook | E. Nakagawa | 800000 | 2023-10-16 | 2023-10-26 | 8
1.2.1.1 | 4 | Function-by-function readiness assessment | E. Nakagawa |  | 2023-10-16 | 2023-11-13 | 20
1.2.1.2 | 4 | Cutover runbook authoring | D. Okpara |  | 2023-11-13 | 2023-12-04 | 15
1.2.1.3 | 4 | Runbook dry run & rehearsal | C. Hollifield |  | 2023-12-04 | 2023-12-18 | 10
1.2.1.4 | 4 | Rollback procedure & rehearsal | T. Ruffalo |  | 2023-12-18 | 2023-12-28 | 8
1.2.2 | 3 | Payroll & benefits cutover | D. Okpara | 700000 | 2023-10-20 | 2023-10-31 | 7
1.2.3 | 3 | Member ID card reissue | C. Hollifield | 900000 | 2023-10-25 | 2023-11-08 | 10
1.2.3.1 | 4 | Card design & regulatory review | E. Nakagawa |  | 2023-10-25 | 2023-11-08 | 10
1.2.3.2 | 4 | Member file extract & address validation | D. Okpara |  | 2023-11-08 | 2023-11-24 | 12
1.2.3.3 | 4 | Print vendor proof & production run | C. Hollifield |  | 2023-11-24 | 2023-12-20 | 18
1.2.3.4 | 4 | Distribution & exception handling | T. Ruffalo |  | 2023-12-20 | 2024-01-17 | 20
1.2.4 | 3 | Day 1 command center & hypercare | T. Ruffalo | 600000 | 2023-11-01 | 2023-11-09 | 6
1.2.5 | 3 | Go/no-go gate & evidence pack | R. Villanueva | 600000 | 2023-11-06 | 2023-11-14 | 6
1.3 | 2 | Data Migration & Identity Resolution | Dr. A. Ravindran | 11400000 | 2023-10-30 | 2024-04-23 | 126
1.3.1 | 3 | Source profiling & data quality assessment | Y. Abegunde | 1200000 | 2023-10-30 | 2023-11-16 | 13
1.3.1.1 | 4 | Member file extract & load | Y. Abegunde |  | 2023-10-30 | 2023-11-09 | 8
1.3.1.2 | 4 | Completeness & format profiling | M. Thibodeaux |  | 2023-11-09 | 2023-11-27 | 12
1.3.1.3 | 4 | Internal duplicate analysis | S. Wrenfield |  | 2023-11-27 | 2023-12-11 | 10
1.3.1.4 | 4 | Cross-entity overlap measurement | Y. Abegunde |  | 2023-12-11 | 2024-01-01 | 15
1.3.1.5 | 4 | Profiling report & re-forecast | Dr. A. Ravindran |  | 2024-01-01 | 2024-01-09 | 6
1.3.2 | 3 | EMPI platform build & configuration | I. Duvernay | 2100000 | 2023-11-07 | 2023-12-08 | 23
1.3.3 | 3 | Match rules & survivorship specification | S. Wrenfield | 1400000 | 2023-11-22 | 2023-12-13 | 15
1.3.3.1 | 4 | Standardization & blocking key design | S. Wrenfield |  | 2023-11-22 | 2023-12-08 | 12
1.3.3.2 | 4 | Deterministic rule configuration | I. Duvernay |  | 2023-12-08 | 2023-12-22 | 10
1.3.3.3 | 4 | Probabilistic weight training | S. Wrenfield |  | 2023-12-22 | 2024-01-12 | 15
1.3.3.4 | 4 | Threshold calibration & review band sizing | I. Duvernay |  | 2024-01-12 | 2024-01-30 | 12
1.3.3.5 | 4 | Survivorship rules per attribute | S. Wrenfield |  | 2024-01-30 | 2024-02-13 | 10
1.3.4 | 3 | Clerical review operations | L. Pemberton | 3300000 | 2023-12-01 | 2024-01-22 | 36
1.3.4.1 | 4 | Steward recruitment & onboarding | T. Vandiver |  | 2023-12-01 | 2024-01-05 | 25
1.3.4.2 | 4 | Steward SOP authoring & training | T. Vandiver |  | 2024-01-05 | 2024-01-26 | 15
1.3.4.3 | 4 | Review queue operations - wave 1 | L. Pemberton |  | 2024-01-26 | 2024-03-29 | 45
1.3.4.4 | 4 | Review queue operations - wave 2 | F. Guerrero |  | 2024-03-29 | 2024-05-31 | 45
1.3.4.5 | 4 | Review queue operations - wave 3 | N. Ojukwu |  | 2024-05-31 | 2024-07-12 | 30
1.3.4.6 | 4 | Queue SLA monitoring & escalation | T. Vandiver |  | 2024-07-12 | 2024-09-06 | 40
1.3.5 | 3 | Migration execution & reconciliation | M. Thibodeaux | 2000000 | 2023-12-27 | 2024-01-26 | 22
1.3.6 | 3 | Data quality audit & false-positive review | L. Braithwaite | 900000 | 2024-01-11 | 2024-01-24 | 9
1.3.7 | 3 | Coverage history consolidation | L. Pemberton | 500000 | 2024-01-17 | 2024-01-24 | 5
1.4 | 2 | Core Administration Consolidation | W. Ferriday | 8900000 | 2023-11-28 | 2024-04-12 | 98
1.4.1 | 3 | Platform configuration & benefit build | R. Sedgwick | 2400000 | 2023-11-28 | 2024-01-03 | 26
1.4.1.1 | 4 | Benefit plan build & configuration | R. Sedgwick |  | 2023-11-28 | 2024-01-16 | 35
1.4.1.2 | 4 | Provider contract & fee schedule load | M. Prideaux |  | 2024-01-16 | 2024-02-20 | 25
1.4.1.3 | 4 | Group & eligibility structure build | J. Whitfield |  | 2024-02-20 | 2024-03-19 | 20
1.4.1.4 | 4 | Configuration peer review & sign-off | R. Sedgwick |  | 2024-03-19 | 2024-04-02 | 10
1.4.2 | 3 | Claims edit inventory & porting | M. Prideaux | 1300000 | 2023-12-15 | 2024-01-04 | 14
1.4.3 | 3 | Parallel run & equivalence reconciliation | B. Nkemdirim | 2200000 | 2023-12-26 | 2024-01-29 | 24
1.4.3.1 | 4 | Expected-difference register | S. Coventry |  | 2023-12-26 | 2024-01-11 | 12
1.4.3.2 | 4 | Parallel run cycle 1 | T. Calloway |  | 2024-01-11 | 2024-02-08 | 20
1.4.3.3 | 4 | Variance triage & root cause | B. Nkemdirim |  | 2024-02-08 | 2024-03-05 | 18
1.4.3.4 | 4 | Parallel run cycle 2 | S. Coventry |  | 2024-03-05 | 2024-04-02 | 20
1.4.3.5 | 4 | Reconciliation sign-off | T. Calloway |  | 2024-04-02 | 2024-04-12 | 8
1.4.4 | 3 | EDI trading partner re-registration | L. Marchesi | 1100000 | 2024-01-11 | 2024-01-29 | 12
1.4.5 | 3 | Cutover execution | S. Coventry | 1200000 | 2024-01-19 | 2024-02-07 | 13
1.4.5.1 | 4 | Cutover go/no-go gate | W. Ferriday |  | 2024-01-19 | 2024-01-24 | 3
1.4.5.2 | 4 | Final data sync & freeze | C. Larkspur |  | 2024-01-24 | 2024-01-30 | 4
1.4.5.3 | 4 | Cutover execution weekend | C. Larkspur |  | 2024-01-30 | 2024-02-02 | 3
1.4.5.4 | 4 | Post-cutover hypercare | M. Prideaux |  | 2024-02-02 | 2024-02-23 | 15
1.4.6 | 3 | Legacy platform decommissioning | E. Nakagawa | 700000 | 2024-01-29 | 2024-02-07 | 7
1.5 | 2 | Cloud Migration & Infrastructure | B. Trammell | 7800000 | 2023-12-20 | 2024-04-18 | 86
1.5.1 | 3 | Azure landing zone design & build | E. Kalinowski | 1800000 | 2023-12-20 | 2024-01-16 | 19
1.5.1.1 | 4 | Management group & subscription topology | E. Kalinowski |  | 2023-12-20 | 2024-01-03 | 10
1.5.1.2 | 4 | Network design & address reconciliation | H. Sandifer |  | 2024-01-03 | 2024-01-24 | 15
1.5.1.3 | 4 | Identity & privileged access model | E. Kalinowski |  | 2024-01-24 | 2024-02-09 | 12
1.5.1.4 | 4 | Policy guardrails & compliance baseline | H. Sandifer |  | 2024-02-09 | 2024-02-23 | 10
1.5.1.5 | 4 | Logging, monitoring & FinOps foundation | R. Ilesanmi |  | 2024-02-23 | 2024-03-12 | 12
1.5.1.6 | 4 | Landing zone acceptance gate | B. Trammell |  | 2024-03-12 | 2024-03-19 | 5
1.5.2 | 3 | Archive bulk transfer | D. Fontenot | 900000 | 2024-01-02 | 2024-01-15 | 9
1.5.3 | 3 | Migration waves 1-2 | H. Sandifer | 1300000 | 2024-01-08 | 2024-01-26 | 14
1.5.4 | 3 | Migration waves 3-4 | D. Fontenot | 1600000 | 2024-01-17 | 2024-02-09 | 17
1.5.4.1 | 4 | Wave 3 - care management & UM | D. Fontenot |  | 2024-01-17 | 2024-02-21 | 25
1.5.4.2 | 4 | Wave 3 exit evidence & restore test | E. Kalinowski |  | 2024-02-21 | 2024-03-04 | 8
1.5.4.3 | 4 | Wave 4 - integration layer & warehouse | H. Sandifer |  | 2024-03-04 | 2024-04-15 | 30
1.5.4.4 | 4 | Wave 4 exit evidence & restore test | D. Fontenot |  | 2024-04-15 | 2024-04-25 | 8
1.5.5 | 3 | Migration wave 5 | G. Whitmire | 800000 | 2024-01-29 | 2024-02-08 | 8
1.5.6 | 3 | Enterprise data warehouse build | E. Kalinowski | 1000000 | 2024-02-02 | 2024-02-19 | 11
1.5.7 | 3 | FinOps foundation & cost management | D. Fontenot | 400000 | 2024-02-09 | 2024-02-16 | 5
1.6 | 2 | Integration Architecture & Interfaces | R. Delacroix | 5200000 | 2024-01-09 | 2024-03-28 | 57
1.6.1 | 3 | Canonical model & architecture design | R. Delacroix | 900000 | 2024-01-09 | 2024-01-22 | 9
1.6.2 | 3 | Integration layer build | O. Hargrave | 1500000 | 2024-01-15 | 2024-02-06 | 16
1.6.2.1 | 4 | Canonical model implementation | R. Delacroix |  | 2024-01-15 | 2024-02-12 | 20
1.6.2.2 | 4 | Adapter build - both platforms | O. Hargrave |  | 2024-02-12 | 2024-03-18 | 25
1.6.2.3 | 4 | Reconciliation & control total framework | A. Feldstein |  | 2024-03-18 | 2024-04-08 | 15
1.6.2.4 | 4 | Replay & idempotency implementation | R. Delacroix |  | 2024-04-08 | 2024-04-24 | 12
1.6.3 | 3 | Interface build - enrollment & eligibility | O. Hargrave | 800000 | 2024-01-25 | 2024-02-06 | 8
1.6.4 | 3 | Interface build - claims & remittance | K. Balasubramanian | 700000 | 2024-01-31 | 2024-02-09 | 7
1.6.5 | 3 | Interface build - accumulators & write-back | O. Hargrave | 800000 | 2024-02-05 | 2024-02-15 | 8
1.6.6 | 3 | Interface regression & X12 assurance | A. Vaidyanathan | 500000 | 2024-02-09 | 2024-02-16 | 5
1.7 | 2 | TSA Exit & Knowledge Transfer | G. Threadgill | 2700000 | 2024-01-23 | 2024-03-05 | 30
1.7.1 | 3 | TSA service management & reporting | G. Threadgill | 600000 | 2024-01-23 | 2024-01-31 | 6
1.7.2 | 3 | Knowledge transfer & reverse shadowing | H. Sandifer | 900000 | 2024-01-26 | 2024-02-09 | 10
1.7.2.1 | 4 | Transfer plan & named receiver assignment | E. Nakagawa |  | 2024-01-26 | 2024-02-07 | 8
1.7.2.2 | 4 | Shadowing - provider led | H. Sandifer |  | 2024-02-07 | 2024-03-20 | 30
1.7.2.3 | 4 | Reverse shadowing - ACME led | N. Farnsworth |  | 2024-03-20 | 2024-05-01 | 30
1.7.2.4 | 4 | Transfer acceptance & sign-off | G. Threadgill |  | 2024-05-01 | 2024-05-15 | 10
1.7.3 | 3 | Service-by-service exit certification | N. Farnsworth | 700000 | 2024-02-02 | 2024-02-13 | 7
1.7.4 | 3 | Residual dependency closure | E. Nakagawa | 500000 | 2024-02-07 | 2024-02-14 | 5
1.8 | 2 | Provider Network & Care Management | J. Kirkendall | 2000000 | 2024-02-06 | 2024-03-07 | 22
1.8.1 | 3 | Provider master consolidation | A. Boudreaux | 700000 | 2024-02-06 | 2024-02-15 | 7
1.8.2 | 3 | Network rationalization analysis | Dr. P. Nwachukwu | 600000 | 2024-02-09 | 2024-02-19 | 6
1.8.3 | 3 | Care management platform transition | J. Kirkendall | 700000 | 2024-02-14 | 2024-02-23 | 7
1.9 | 2 | Organization, Change & Communications | A. Winterbourne | 2400000 | 2024-02-20 | 2024-03-27 | 26
1.9.1 | 3 | Organization design & role mapping | A. Winterbourne | 600000 | 2024-02-20 | 2024-02-28 | 6
1.9.2 | 3 | Retention & key talent program | K. Osterhout | 500000 | 2024-02-23 | 2024-03-01 | 5
1.9.3 | 3 | Employee communications & change | R. Tomlinson | 700000 | 2024-02-28 | 2024-03-08 | 7
1.9.4 | 3 | Member & provider communications | D. Marchbanks | 600000 | 2024-03-04 | 2024-03-12 | 6
1.10 | 2 | Vendor & Contract Consolidation | H. Castellow | 1900000 | 2024-03-05 | 2024-04-03 | 21
1.10.1 | 3 | Change-of-control sweep & consents | M. Rousseau | 600000 | 2024-03-05 | 2024-03-13 | 6
1.10.2 | 3 | Business Associate Agreement re-execution | D. Achterberg | 400000 | 2024-03-08 | 2024-03-15 | 5
1.10.3 | 3 | Vendor consolidation execution | H. Castellow | 900000 | 2024-03-13 | 2024-03-26 | 9
1.11 | 2 | Legal, Regulatory & Compliance | F. Underhill | 1700000 | 2024-03-19 | 2024-04-12 | 18
1.11.1 | 3 | Legal entity consolidation | M. Sheffield | 600000 | 2024-03-19 | 2024-03-27 | 6
1.11.2 | 3 | Regulatory filings & DOI conditions | R. Cadwallader | 500000 | 2024-03-22 | 2024-03-29 | 5
1.11.3 | 3 | Privacy & compliance assurance | J. Ferrandino | 600000 | 2024-03-27 | 2024-04-04 | 6