## Table
Ref | Deliverable | Integration Management Office | Claims & Core Administration | Data & EMPI | Application Integration | Cloud & Infrastructure | Business Operations | Corporate & Control | Vendor & Contract Management
D-01 | Integration Charter and program plan | A | I | I | · | · | · | C | ·
D-02 | Application disposition decisions | C | A | R | R | C | · | · | ·
D-03 | Vendor and contract disposition | I | · | · | · | C | · | C | A
D-04 | Vendor SOWs and BAAs | C | · | · | · | · | · | A | R
D-05 | Member identity resolution | I | R | A | C | · | · | · | ·
D-06 | Clerical review queue worked to closure | I | · | A | · | · | C | · | ·
D-07 | Integration layer and interfaces | · | R | R | A | C | · | · | ·
D-08 | Cloud landing zone and migration waves | I | · | · | R | A | · | · | ·
D-09 | TSA exit, service by service | A | R | · | · | R | · | C | C
D-10 | Legal entity consolidation | I | C | · | · | · | · | A | ·
D-11 | Member communications and ID cards | · | C | C | · | · | A | · | ·
D-12 | Synergy realization and reporting | C | · | · | · | · | R | A | R
D-13 | Program budget and change control | R | I | · | · | I | · | A | ·
D-14 | Day 1 readiness and go/no-go | A | R | R | · | R | · | C | ·
D-15 | Closeout and benefits handover | A | · | · | · | · | C | R | ·

## Paired counterparts one delive
Workstream | ACME lead | Cumberland Valley counterpart
Claims & Core Administration | W. Ferriday | R. Lattimore
Data & EMPI | Dr. A. Ravindran | C. Bhattacharya
Application Integration | K. Stallworth | —
Cloud & Infrastructure | B. Trammell | —

## Bodies outside the matrix
Body | Relationship
Clean Team | Harpeth Clean Team Services, engaged by ACME Legal
Integration Steering Committee | D. Ashmore (CFO, Sponsor) and five executives
Cheatham Mutual Holdings | the divesting parent, under the TSA
Human Resources | ACME HR, outside the program budget
Regulators | state insurance department and the FTC/DOJ

## About
RACI Matrix
Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health and Cumberland Valley Health Plan are fictional entities; no real transaction, rate, or member data is represented.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.