## 1 Risk Register summary (1)
Disposition | Count | What it means
Open or actively tracked | 18 | Scored, owned, mitigation under way
Closed | 4 | The exposure no longer exists — the event passed, or the condition was met
⚠ Realized and moved to issues | 3 | Happened. Probability is now 1, so they leave the register entirely.
Identified since Day 1 | 25 | 18 + 4 + 3

## 1 Risk Register summary (2)
Ref | Risk | Closed | Why it closed
R-C1 | Regulatory approval delayed or conditioned unfavorably | Sep 2023 | Form A approved. ⚠ One condition applies and converted to R-07, accepted.
R-C2 | Day 1 payroll or benefits failure | Jan 2024 | Passed. HRIS and payroll migrated at month three without a missed cycle.
R-C3 | Platform capacity insufficient for combined volume | Nov 2023 | Load analysis confirmed headroom post-close
R-C4 | Landing zone not ready before the first migration wave | Jan 2024 | Accepted against ten evidenced conditions; Wave 1 proceeded

## 1 Risk Register summary (3)
Was | Risk | Realized | Now
R-11 | Provider directory discrepancies between the two networks | Nov 2023 | I-01, open
R-14 | Trading partner re-registration slower than planned | Jan 2024 | I-02, open
R-16 | Discovery reveals integration scope beyond the deal model | Dec 2023 | I-03, closed at the re-baseline

## 1 Risk Register summary (4)
ID | Risk | Exposure | Owner
R-01 | Member identity resolution materially harder than modeled | Critical | Dr. A. Ravindran
R-02 | Attrition of retention-covered target staff before TSA exit | Critical | D. Marchbanks
R-05 | Core administration cutover slips past the TSA plan date | Critical | W. Ferriday
R-03 | Cloud skills gap slows migration or incident response | High | B. Trammell
R-08 | Data warehouse go-live without demonstrated recovery | High | H. Sandifer

## 2 Assumptions
ID | Assumption | Owner | Validation point
A-01 | Target member data quality broadly as represented in diligence | Dr. A. Ravindran | ⚠ Post-close profiling, in progress. Open The last untested assumption from closing, and the largest.
A-02 | ACME's platform absorbs the combined volume without re-architecture | W. Ferriday | Load analysis, Nov 2023. Closed Headroom confirmed.
A-03 | Target vendor contracts assignable or novatable with consent | H. Castellow | Pre-close sweep. Closed Twelve change-of-control provisions; three termination rights, all resolved.
A-04 | No regulatory condition restricting where member data may be processed | R. Cadwallader | Form A terms, Sep 2023. ⚠ Converted A condition does apply — became R-07, accepted.
A-05 | Steward throughput of 100 records per day is achievable at quality | T. Vandiver | First full month of queue operations. Open
A-06 | Trading partners re-register within 90 days of notice | L. Marchesi | ⚠ Converted Slower than assumed — became I-02.
A-07 | Historical archive fits the migration window using physical transfer | D. Fontenot | Appliance rotation to Mar 2024. On track Ahead of plan.
A-08 | Cheatham Mutual staff remain available for knowledge transfer through exit | G. Threadgill | Monthly TSA service review. Open ⚠ Not contractually guaranteed beyond named roles.

## 3 Issue Log
ID | Issue | Owner | Status | Target | Closed | Resolution
I-01 | Provider directory discrepancies between the two networks | A. Boudreaux | Open | May 2024 | — | Remediation ahead of network rationalization; both directories reconciled against the single provider master
I-02 | Trading partner re-registration slower than planned | L. Marchesi | Open | Aug 2024 | — | ⚠ Externally paced. Clearinghouse exit re-sequenced two months later; no impact on core admin cutover.
I-03 | Discovery revealed integration scope beyond the deal-model estimate | C. Tyrrell | Closed | Jan 2024 | Jan 22, 2024 | Resolved through the January re-baseline, not through change control
I-04 | Landing zone security review extended by two weeks | A. Quintanilla | Closed | Jan 2024 | Jan 19, 2024 | Additional privileged-access controls added; funded from contingency
I-05 | Interface rework after canonical model change to coverage periods | R. Delacroix | Closed | Feb 2024 | Feb 9, 2024 | Three adapters reworked. ⚠ Root cause was a definition disagreement surfaced late.
I-06 | Two workstreams reporting different member counts for the same population | N. Farnsworth | Closed | Dec 2023 | Dec 15, 2023 | One was counting subscribers, the other covered lives. Definition published; both now report the same basis.

## 4 Dependency Log
ID | Dependency | Owner | Status | Impact if missed
D-01 | Cheatham Mutual provides TSA services to contracted levels | G. Threadgill | On track | ⚠ Operations of the acquired business stop. No substitute exists.
D-02 | Trading partners complete re-registration | L. Marchesi | At risk | Providers lose electronic claim submission if the clearinghouse is exited first. See I-02.
D-03 | Rutherford Cloud Operations meets step-down boundaries | B. Trammell | On track | ACME does not reach self-sufficiency; the MSP relationship becomes permanent by default
D-04 | State regulator confirms no further conditions on data handling | R. Cadwallader | Met | Additional constraints would re-open the offshore boundary and the landing zone policy set
D-05 | Physical transfer appliances returned and ingested to schedule | D. Fontenot | On track | Archive transfer falls back to the circuit, which cannot carry it inside the window
D-06 | Provider contract renewal dates fall as modeled | J. Kirkendall | At risk | Network synergy re-profiles to later cycles — timing loss, not value loss
D-07 | Accrediting body measurement year closes on the published calendar | E. Wetherby | On track | Quality rates invalidated for the year if the reporting vendor changes mid-cycle

## 5 Decision Log
ID | Decision | Decided by | Date | Rationale
DE-01 | Mixed integration thesis rather than full absorption | Steering Committee | Jun 2023 | Absorbing everything would destroy the care management capability the transaction was partly undertaken to acquire
DE-02 | Preserve the target's care management platform; retire ACME's | Steering Committee | Jun 2023 | Both options consolidate to one platform, so the saving is the same either way. What differs is which capability survives.
DE-03 | Replace the enterprise data warehouse rather than absorb either | S. Achebe | Jun 2023 | The alternative was not "keep what we have" but "substantially rebuild one of them anyway"
DE-04 | Co-managed cloud operating model with a contracted step-down | B. Trammell | Sep 2023 | Fully managed never builds the capability; self-managed learns cloud during a migration under a contractual wall
DE-05 | Member services CRM coexists to Day 100, then absorbs | T. Ruffalo | Jun 2023 | ⚠ Knowingly accepts three months of duplicated cost to protect Day 1 operational integrity — rank 2 over rank 4
DE-06 | Data stewards engaged on staff augmentation, not fixed price | C. Tyrrell | Feb 2023 | Fixed-pricing a review queue pays a vendor to be fast, and in identity matching the fast error merges two people
DE-07 | Plan to twelve months, not to the eighteen-month TSA maximum | Steering Committee | Feb 2023 | Margin negotiated at signing exists to absorb what discovery reveals; a plan that consumes it first has converted protection into schedule
DE-08 | Re-baseline rather than change-control the estimate movement | Steering Committee | Jan 2024 | Change control governs movement away from a baseline; it cannot govern the arrival of the first credible one
DE-09 | Eleven delivery staff added without moving the cost baseline | D. Ashmore | Feb 2024 | The work was already funded in the work packages; the roster had failed to name who performs it
DE-10 | Wave 1 scoped to non-production workloads | B. Trammell | Dec 2023 | The first wave proves the path, not the value. Discovering a broken runbook on claims adjudication costs the program.

## 6 Governance
Register | Reviewed | Convention
Risks | Workstream weekly; full register monthly | Maintained in artifact 28. Critical exposure is reviewed at every Steering meeting regardless of movement.
Assumptions | At each validation point | ⚠ Closes or converts to a risk. Never simply expires.
Issues | Weekly | Reported with age as well as count — a stable count with rising age is a backlog
Dependencies | Fortnightly | Escalated to the external party's named contact, not to the Steering Committee first
Decisions | Appended on decision | ⚠ Never edited retrospectively. A superseding decision is a new entry that references the old one.

## About
RAIDD Log
Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health, Cumberland Valley Health Plan, Cheatham Mutual Holdings and Rutherford Cloud Operations are fictional entities; no real transaction, rate, or member data is represented.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.