## 1 Four Labor Categories
Organization | People | Category | Role on the program
ACME Health | 31 | Employee | Workstream leads, IMO analysts, target-state design, all decision authority
Cumberland Valley Health Plan | 21 | Employee | Workstream counterparts — how the acquired business actually operates
Arrington Advisory Group | 17 | Consulting | Program management and the three specialisms ACME's bench is thinnest on
Arrington Advisory Group (offshore) | 4 | Consulting | Interface regression testing against de-identified data
Harpeth Clean Team Services | 4 | Specialist vendor | Pre-close information barrier. ⚠ Dissolves at closing.
Two Rivers Talent Partners | 4 | Staff augmentation | Clerical review of identity matches
Gallatin EDI Assurance | 3 | Specialist vendor | X12 transaction assurance
Total roster | 84 |  | Across the full program window

## 2 Contract Vehicle Per Person
Vehicle | People | Who owns the outcome | Who may direct the work
FTE | 52 | ACME / Cumberland Valley | Their line manager
Deliverable SOW | 21 | Arrington — against accepted deliverables | Arrington. ACME defines "done", not "how".
Fixed-price SOW | 7 | The vendor — against a defined result | The vendor
Staff aug (T&M) | 4 | ACME — hours are rented, not outcomes | ⚠ ACME — see the guardrail below

## 3 The Roster Changes Shape at C
Population | Pre-close | Post-close | Reason
Clean Team | 4 | 0 | The antitrust basis for the barrier ends at closing. Nobody crosses into the program.
Data stewards | 0 | 4 | ⚠ Member-level data is not lawfully available before closing. The work cannot begin earlier.
Migration, cloud and build engineers | 0 | 14 | Execution against the target is prohibited pre-close
EDI assurance | 0 | 3 | Testing requires production transaction flow
TSA management | 0 | 1 | There is no TSA until there is a transaction
Total on the program | 58 | 80 | Different populations, not the same one grown

## 4 Rate Card
Category | Rate | Vehicle
Engagement lead / Program Manager | $265 | Deliverable SOW
Principal consultant | $245 | Deliverable SOW
Architect — integration, cloud | $230 | Deliverable SOW
Senior engineer / senior analyst | $195 | Deliverable SOW
Analyst — PMO, data quality, FinOps | $155 | Deliverable SOW
Offshore delivery manager | $95 | Deliverable SOW
Data steward supervisor | $92 | Staff aug
Offshore test lead | $80 | Deliverable SOW
Data steward | $68 | Staff aug
Offshore QA engineer | $65 | Deliverable SOW

## 5 Constraints That Are Not Nego
Constraint | Effect on resourcing
No member-level data outside the United States | ⚠ Tennessee DOI conditions and ACME privacy policy. Clerical review, data stewardship and anything touching the member file must be staffed onshore. The obvious lever for a queue overrun does not exist.
Offshore work is de-identified only | The four offshore staff test interface regression against synthetic and de-identified datasets. Their scope is bounded by what can be done without a real member record.
Clean Team is walled off | Four people who see restricted information and return only conclusions. They may not be redeployed onto the program afterward.
Employee continuation period | Corporate function consolidation cannot begin until the merger agreement's continuation period expires, regardless of readiness.
Steward throughput is fixed | ⚠ A steward working faster is a steward spending less time on the hard cases, which is where false positives originate. Capacity scales by adding people, and onboarding runs several weeks.

## 6 Retention and Key Person Conc
Concentration | Exposure and response
Core administration configuration | A small number of long-tenured staff hold undocumented platform knowledge. Knowledge transfer is a deliverable with named receivers, not an assumed by-product of the TSA.
Member data structures | Concentrated in one Cumberland Valley manager. ⚠ Single point of knowledge for the program's largest risk.
Provider contract history | Held by the target's contracting director; material to network rationalization
Data steward supervision | One supervisor owns the queue service level. Deputy identified and cross-trained.

## 7 Reconciliation Against the WB
People | Group | Why they carry no work package
5 | Steering Committee | Governance, not delivery. They approve, decide and escalate; a control account owner reports to them. ⚠ Putting an executive on a work package would misrepresent who does the work.
4 | Clean Team | Pre-close only. Dissolved before the WBS window opens.
22 | Workstream members | ⚠ Their work sits inside a package owned by a colleague. See below.
31 | Not on the WBS | 53 + 31 = 84

## 8 Attrition and Churn
Reality | How the plan absorbs it
Consultants rotate | Deliverable SOW means Arrington owns continuity, not ACME. ⚠ Named-personnel continuity is contracted for the roles where transfer depends on the same individual.
Target-side staff leave | Retention on 14 roles; knowledge transfer specified as a deliverable so a departure after transfer is a staffing problem rather than a program one
Acquirer staff are reassigned | Workstream leads are named and their release requires the Sponsor's agreement, not their line manager's alone
Stewards turn over | Staff augmentation absorbs this by design — the supplier replaces, ACME retrains. Onboarding time is in the queue forecast, not assumed away.
The MSP steps down | Cloud operations transfer to ACME across four contracted phases; capability is measured at each boundary rather than assumed

## 9 The Roster All 84 Named
Name | Role | Organization | Vehicle | Window | R
Steering Committee · 6
D. Ashmore | EVP & Chief Financial Officer, ACME — Executive Sponsor | ACME | FTE | Throughout | —
R. Villanueva | Chief Operating Officer, ACME | ACME | FTE | Throughout | —
M. Kessinger | President & CEO, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
T. Broadnax | SVP Corporate Development, ACME | ACME | FTE | Throughout | —
L. Hollingsworth | General Counsel, ACME | ACME | FTE | Throughout | —
S. Achebe | Chief Information Officer, ACME | ACME | FTE | Throughout | —
Integration Management Office · 5
C. Tyrrell | Program Manager, Integration (engagement lead) | Arrington | Deliv. SOW | Throughout | —
N. Farnsworth | PMO Analyst | Arrington | Deliv. SOW | Throughout | —
J. Petrosyan | Synergy & Financial Analyst | ACME | FTE | Throughout | —
A. Winterbourne | Change & Communications Lead | Arrington | Deliv. SOW | Throughout | —
G. Threadgill | TSA Manager — owns exit | ACME | FTE | Post-close | —
Clean Team · 4
P. Marchetti | Clean Team Lead | Harpeth | Fixed price | Pre-close only | —
K. Oyelaran | Clean Team Analyst — pricing & network rates | Harpeth | Fixed price | Pre-close only | —
B. Sandoval | Clean Team Analyst — membership & claims volume | Harpeth | Fixed price | Pre-close only | —
H. Tillinghast | Clean Team Counsel (outside) | Harpeth | Fixed price | Pre-close only | —
Claims & Core Administration · 11
R. Sedgwick | Business Analyst — benefit configuration | ACME | FTE | Throughout | —
D. Halloran | Business Analyst — enrollment & eligibility | Cumberland Valley | FTE | Throughout | R
M. Prideaux | Configuration Analyst, Core Administration | ACME | FTE | Post-close | —
J. Whitfield | Configuration Analyst, Claims — retiring platform | Cumberland Valley | FTE | Post-close | R
S. Coventry | QA Analyst — parallel run reconciliation | ACME | FTE | Post-close | —
T. Calloway | QA Analyst — parallel run reconciliation | Cumberland Valley | FTE | Post-close | —
W. Ferriday | VP Claims Operations, ACME — Workstream Lead | ACME | FTE | Throughout | —
E. Nakagawa | Director, Core Admin Platform, ACME | ACME | FTE | Throughout | —
R. Lattimore | VP Claims, Cumberland Valley — Counterpart | Cumberland Valley | FTE | Throughout | R
D. Okpara | Manager, Claims Configuration, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
V. Castellanos | Principal Consultant, Core Admin Migration | Arrington | Deliv. SOW | Post-close | —
Data & EMPI · 11
P. Ramaswamy | Senior Data Engineer, EMPI Build | Arrington | Deliv. SOW | Post-close | —
Dr. A. Ravindran | Director, Enterprise Data Management, ACME — Workstream Lead | ACME | FTE | Throughout | —
M. Thibodeaux | Data Architect, ACME | ACME | FTE | Throughout | —
C. Bhattacharya | Manager, Member Data, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
S. Wrenfield | Principal Consultant, Identity Resolution | Arrington | Deliv. SOW | Post-close | —
I. Duvernay | Senior Data Engineer, Matching & Survivorship | Arrington | Deliv. SOW | Post-close | —
Y. Abegunde | Data Quality Analyst | Arrington | Deliv. SOW | Post-close | —
L. Pemberton | Data Steward — clerical review queue | Two Rivers | Staff aug | Post-close | —
F. Guerrero | Data Steward — clerical review queue | Two Rivers | Staff aug | Post-close | —
N. Ojukwu | Data Steward — clerical review queue | Two Rivers | Staff aug | Post-close | —
T. Vandiver | Data Steward Supervisor — SLA owner | Two Rivers | Staff aug | Post-close | —
Application Integration · 11
K. Balasubramanian | Business Analyst — interface requirements | Arrington | Deliv. SOW | Throughout | —
A. Feldstein | Senior Engineer, Interface Build | Arrington | Deliv. SOW | Post-close | —
B. Nkemdirim | Test Manager — equivalence testing (onshore) | Arrington | Deliv. SOW | Post-close | —
K. Stallworth | Director, Enterprise Integration, ACME — Workstream Lead | ACME | FTE | Throughout | —
J. Amonett | Manager, Interfaces, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
R. Delacroix | Integration Architect — canonical model | Arrington | Deliv. SOW | Throughout | —
O. Hargrave | Senior Engineer, Integration Layer | Arrington | Deliv. SOW | Post-close | —
V. Krishnamoorthy | Offshore Delivery Manager | Arrington (offshore) | Deliv. SOW | Post-close | —
P. Devarakonda | Test Lead, Integration | Arrington (offshore) | Deliv. SOW | Post-close | —
S. Mahadevan | QA Engineer, Interface Regression | Arrington (offshore) | Deliv. SOW | Post-close | —
A. Vaidyanathan | QA Engineer, Interface Regression | Arrington (offshore) | Deliv. SOW | Post-close | —
Cloud & Infrastructure · 7
C. Larkspur | Release & Environment Manager | ACME | FTE | Throughout | —
B. Trammell | VP Infrastructure, ACME — Workstream Lead | ACME | FTE | Throughout | —
H. Sandifer | Manager, Platform Engineering, ACME | ACME | FTE | Throughout | —
G. Whitmire | Director, IT Operations, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
E. Kalinowski | Cloud Architect — landing zone | Arrington | Deliv. SOW | Throughout | —
D. Fontenot | Senior Cloud Engineer, Migration Waves | Arrington | Deliv. SOW | Post-close | —
R. Ilesanmi | FinOps Analyst — tagging, showback, reservations | Arrington | Deliv. SOW | Post-close | —
Provider Network · 2
J. Kirkendall | VP Network Management, ACME — Workstream Lead | ACME | FTE | Throughout | —
A. Boudreaux | Director, Provider Contracting, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
Care Management · 2
Dr. M. Ellsworth | Chief Medical Officer, ACME — Workstream Lead | ACME | FTE | Throughout | —
Dr. P. Nwachukwu | VP Care Management, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
Member Services · 2
T. Ruffalo | VP Member Experience, ACME — Workstream Lead | ACME | FTE | Throughout | —
C. Hollifield | Director, Member Services, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
Finance & Accounting · 2
S. Beauregard | VP Financial Planning & Analysis, ACME — Workstream Lead | ACME | FTE | Throughout | —
N. Applewhite | Controller, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
HR & Talent · 2
D. Marchbanks | SVP Human Resources, ACME — Workstream Lead | ACME | FTE | Throughout | —
K. Osterhout | Director, HR Business Partner, Cumberland Valley | Cumberland Valley | FTE | Throughout | —
Legal & Regulatory · 3
F. Underhill | Associate General Counsel, M&A, ACME — Workstream Lead | ACME | FTE | Throughout | —
R. Cadwallader | Director, Regulatory Affairs, ACME — DOI Form A owner | ACME | FTE | Throughout | —
M. Sheffield | General Counsel, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
Compliance & Privacy · 2
L. Braithwaite | Chief Privacy Officer, ACME — Workstream Lead | ACME | FTE | Throughout | —
J. Ferrandino | Compliance Director, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
Security · 2
A. Quintanilla | Chief Information Security Officer, ACME — Workstream Lead | ACME | FTE | Throughout | —
P. Hasenfratz | Manager, Information Security, Cumberland Valley | Cumberland Valley | FTE | Throughout | —
Actuarial & Underwriting · 2
E. Wetherby | VP Actuarial Services, ACME — Workstream Lead | ACME | FTE | Throughout | —
C. Adeyemi | Chief Actuary, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
Communications · 2
B. Lundquist | VP Corporate Communications, ACME — Workstream Lead | ACME | FTE | Throughout | —
R. Tomlinson | Director, Communications, Cumberland Valley | Cumberland Valley | FTE | Throughout | —
Vendor & Contract Management · 3
H. Castellow | VP Procurement, ACME — Workstream Lead | ACME | FTE | Throughout | —
D. Achterberg | Director, Vendor Management, Cumberland Valley | Cumberland Valley | FTE | Throughout | R
M. Rousseau | Contracts Consultant — change-of-control sweep | Arrington | Deliv. SOW | Throughout | —
Facilities · 2
W. Pickering | Director, Corporate Real Estate, ACME — Workstream Lead | ACME | FTE | Throughout | —
S. Grimsley | Facilities Manager, Cumberland Valley | Cumberland Valley | FTE | Throughout | —
EDI Transaction Assurance · 3
N. Reinhardt | Engagement Lead, X12 Assurance | Gallatin | Fixed price | Post-close | —
T. Osei-Bonsu | Senior EDI Analyst — 834 enrollment, 820 premium | Gallatin | Fixed price | Post-close | —
L. Marchesi | Senior EDI Analyst — 837/835 claims & remittance | Gallatin | Fixed price | Post-close | —

## About
Resource Plan
Illustrative program data — created to demonstrate M&A integration program management practice. ACME Health, Cumberland Valley Health Plan, Cheatham Mutual Holdings and Rutherford Cloud Operations are fictional entities; no real transaction, rate, or member data is represented.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.