## Slide 1
STEERING REVIEW · ESCALATION · MONTH 8 POST-CLOSE
Steering Committee
Escalation
One decision is sought: extend transitional services by three months and fund it from management reserve. This pack states the recommendation, the two alternatives, and what the program will not do regardless of the outcome.
May 14, 2024
Meeting Date
● RED
Program Status
26%
Review Band vs 8% Modeled
$55.944M
Cost Baseline

## Slide 2
AGENDA
Today's Steering Review
1
Program Health
2
Program Status — RAG
3
Objectives Status
4
Scope & Change Log
5
Teams & Delivery Model
6
Governance & Decision Rights
7
Schedule & Phase Gates
8
Budget Forecast
9
Decision Sought — The Options
10
How We Work Together
11
Risks — Aged Register
12
Issues
13
Decisions & Look-Ahead
2

## Slide 3
PROGRAM HEALTH
Where We Stand at Month 8
Day 1 held, the platform is stable, and members are being served — and this program is red, because one workstream cannot finish inside the time it has.
The first full profiling run against the consolidated member estate completed on April 15, 2024. It measured a clerical review band of 26% against a deal-model assumption of 8%. The queue that follows cannot be worked inside the remaining transitional services term at any capacity the program can lawfully or safely deploy. Nothing has gone wrong operationally. The program is red because a measurement showed a workstream cannot complete in the time available, and no amount of current operational health changes that.
● RED
Overall status
26%
Measured review band
109,200
Records in the queue
3

## Slide 4
PROGRAM STATUS
Red on Schedule; Quality and Day 1 Integrity Hold
Status reflects the ability to complete, not the absence of incidents — and the two are routinely confused in the direction that flatters the program.
Nothing has gone wrong operationally. Members are being served, claims are paying, the platform is stable, and Day 1 integrity has held since cutover. The program is red because a measurement taken in April showed that identity resolution cannot finish inside the remaining transitional services term, and no amount of current operational health changes that. A program that reported green here would be reporting on its incident log rather than on its ability to deliver.
KEY FACTS
Schedule
● Red — identity resolution exceeds the remaining TSA term
Budget
● Amber — contingency substantially committed; a reserve draw is sought today
Scope
● Amber — two deferrals offered alongside the request
Quality
● Green — steward false-positive audits within tolerance
Day 1 integrity
● Green — held throughout; no member-facing failure attributable to integration
4

## Slide 5
OBJECTIVES
How We're Tracking to Plan
1
Close the transaction with every regulatory condition satisfied — ✓ achieved, closed on schedule
2
Reach Day 1 with member-facing continuity intact — ✓ achieved and holding at month 8
3
Exit every transitional service inside the contractual maximum — at risk; the decision sought today protects it
4
Resolve two member databases into one identity with no false merges — on track on quality, not on volume
5
Deliver the $85,000,000 run-rate synergy case by Year 3 — on track on run-rate; cumulative capture slipping
5

## Slide 6
SCOPE & CHANGE
What's Changed Since Kickoff
IN SCOPE
✓
Transitional services extension
Three months, core administration and IT — the decision sought
✓
Program leadership continuation
IMO and workstream leads through the revised exit
✓
Identity resolution to completion
Second onshore steward cohort already approved and recruiting
OUT OF SCOPE (CANDIDATE BACKLOG)
✕
Provider network rationalization, phase 2
Deferred to Year 2 — J. Kirkendall accepts; gated by contract anniversaries outside the revised term
✕
Care management advanced analytics
Deferred to Year 2 — Dr. M. Ellsworth accepts; no dependency on the TSA exit
✕
Offshore steward capacity
Raised, examined and REJECTED — barred under the state contract; the rejection is recorded, not left open
✕
Any relaxation of match thresholds
Frozen when the rules were issued; not a lever available to the program or this Committee
6

## Slide 7
TEAMS
The Team — Grown to 84, Stewards Are the Constraint
84 people at month 8 — the roster changed shape at close, as planned: the Clean Team dissolved the day the transaction completed and the data-steward function stood up in its place. ⚠ A second steward cohort was already approved and recruiting when the profiling completed — the program is not asking for reserve because it was surprised.
6
Steering Committee & Sponsorship
Sponsor: D. Ashmore, EVP & CFO
5
Integration Management Office
Lead: C. Tyrrell, Program Manager
14
Data & EMPI — incl. data stewards
Lead: Dr. A. Ravindran · Supervisor: T. Vandiver
26
Technology Workstreams
W. Ferriday · K. Stallworth · B. Trammell
14
Business Workstreams
J. Kirkendall · T. Ruffalo · Dr. M. Ellsworth · E. Wetherby
19
Corporate Functions & Control
F. Underhill · H. Castellow · A. Quintanilla · L. Braithwaite
7

## Slide 8
GOVERNANCE
Who Decides What
The charter ranks this program's constraints, and that ranking is what decides today: the transitional services contractual maximum and Day 1 integrity are hard, synergy is firm, cost flexes, and scope flexes first. The recommendation spends the two lowest-ranked constraints to protect the two highest.
Tier 1
Planning and task decisions within the PM's delegated authority
Program Manager (C. Tyrrell)
Tier 2
Cost or scope change exceeding PM authority
Change Control Board → Steering Committee
Tier 3
Management reserve draw; transitional services extension
Executive Sponsor (D. Ashmore) — sought today
Absolute
Match thresholds and offshore processing of member data
Not available to anyone in this room
8

## Slide 9
DECISION SOUGHT
Three Courses — and the One That Looks Free
Three courses are available. The recommendation is Option A. Options B and C are both survivable in the short term, and the program's objection to each is that the cost is paid later, by someone else, in a form that is difficult to attribute back to this decision.
OPTION
PROTECTS
SPENDS
A
Extend three months — exit moves to end of December 2024
Data integrity; member-facing continuity
Negotiated TSA margin; management reserve
RECOMMENDED
B
Exit on the baseline date with the queue open
Cost and the original schedule
Data integrity
NOT RECOMMENDED
C
Exit on the baseline date, raise steward throughput
Cost and schedule, on paper
Quality, invisibly
THE TRAP
Option C is the one that will look most attractive in this room.
It costs nothing, breaches no date, and produces a clean queue report inside the original term. Its cost is paid later, by members, in a form that is nearly impossible to attribute back to this meeting. A false negative leaves a duplicate record — irritating and self-correcting. A false positive merges two people: one member's protected health information under another's identity, claims adjudicating against the wrong history, a clinician reading the wrong chart — and unlike a duplicate, no routine process ever reveals it. The program can accept a schedule cost or a financial cost. It cannot recommend accepting this one.
Margin is not float.
Float is a by-product of the schedule network and belongs to the schedule. The six months between the exit plan and the contractual maximum were negotiated deliberately at signing as a governance buffer, and they belong to this Committee. Spending them is the outcome they were purchased for — a buffer never spent under a real constraint was either unnecessary, or the program failed to recognize when to use it.
9

## Slide 10
TIMELINE
Close Behind Us, the TSA Clock Ahead
Day 1 held and the platform is stable — but the transitional services term is now the binding constraint, and one workstream cannot finish inside it.
Pre-Close Planning
Clean Team, regulatory · Feb–Sep '23
Close & Day 1
Cutover, continuity · Sep–Oct '23
Stabilize & Re-Baseline
Day 100, Class 2 estimate · Oct '23–Jan '24
Integrate & Migrate
Identity, platform, cloud · Jan–Dec '24
TSA Exit & Closeout
Service-by-service exit · Dec '24–Apr '25
KEY MILESTONES
Sep 29 '23
Transaction closed
Jan 9 '24
Day 100 review
Jan 22 '24
Re-baseline to a Class 2 estimate
Apr 15 '24
First full profiling run — the finding
May 3 '24
Status report moves to red
May 14 '24
This meeting — decision sought
10

## Slide 11
TIMELINE · DETAIL
Project Phases — Detailed View
The program as a work view — bars show when each workstream runs and where they overlap.
Q4 '23
Q1 '24
Q2 '24
Q3 '24
Q4 '24
Q1 '25
FY
Complete
Close & Day 1 cutover
Stabilization & Day 100
Re-baseline (Class 2)
In flight
Cloud migration waves
Core administration consolidation
Interface build & cutover
The constraint
Identity resolution — review queue
TSA exit (revised, if approved)
11

## Slide 12
BUDGET
Budget Status
TOTAL PROGRAM BUDGET $55.944M
Core Administration Consolidation
$11,900,000
Claims and enrollment platform absorption
Member Identity Resolution & Data Migration
$9,800,000
EMPI platform, migration, steward capacity
Cloud Migration & Infrastructure
$10,100,000
Landing zone, migration waves, co-managed operations
Integration Layer & Interfaces
$6,400,000
Canonical model and fourteen interfaces
Program Management, Governance & Advisory
$6,200,000
IMO, consulting engagement
Transitional Services Charges
$4,700,000
Paid to the divesting parent through the term
Business Workstreams & Change
$2,700,000
Network, care management, member services, communications
Contingency Reserve (8% of base)
$4,144,000
Class 2 estimate — substantially committed
Base estimate $51,800,000 plus 8% contingency gives the $55,944,000 cost baseline set at the January re-baseline. Management reserve of $4,200,000 sits outside it and is released by the Sponsor — which is what today's request asks for.
12

## Slide 13
BUDGET FORECAST
Budget Forecast — Trending to $59.4M, Inside Authorized Funding
The forecast at completion is $59,400,000 against a $55,944,000 cost baseline — and inside the $60,144,000 authorized.
Contingency is substantially committed. The extension sought today exceeds what remains and requires a draw on management reserve, which is a Sponsor decision rather than a program one. Contingency covers identified risks inside the baseline and the program may commit it; reserve sits outside the baseline for what a baseline cannot anticipate. Reaching for reserve is a signal in itself — it says the program has exhausted what it was authorized to spend against known risk.
● AT RISK
CUMULATIVE SPEND — PLAN vs. ACTUAL / FORECAST ($M)
Chart: 
| M0 | M3 | M5 | M8 | M11 | M14 | M18
Planned | 4.2 | 16.5 | 26 | 35.5 | 44 | 51.5 | 55.944
Actual + Forecast | 4.4 | 17.8 | 28.6 | 39.2 | 47.9 | 55.2 | 59.4
$55,944,000
Cost baseline (Class 2)
$59,400,000
Forecast at completion
$60,144,000
Authorized — the forecast sits inside it
13

## Slide 14
WORKING TOGETHER
How We Stay in Sync
CADENCE
FORUM
PURPOSE
Weekly
Integration Management Office
Workstream status in, one unified report out
Weekly
Vendor check-ins — individually
Never a joint forum; delivery problems are commercially sensitive
Monthly
Steering Committee
Formal program-health review — this meeting
As needed
Change Control Board
Cost- or scope-impacting change requests
Weekly
Steward false-positive audit
Sampled outside the workstream that sets the thresholds
14

## Slide 15
RISKS
Risks and Mitigation
The full register at a glance — each risk with its mitigation, likelihood, and impact; detailed cards follow.
IDENTIFIED RISKS
MITIGATION STRATEGY
LIKELIHOOD
IMPACT
01
Member identity resolution volume
✓
Second steward cohort already recruiting; extension sought today
High
High
02
Core administration cutover slips past the TSA plan date
✓
Resolved by the same extension — no duplicate response
High
High
03
Attrition of retention-covered target staff
✓
Retention tied to transfer obligations, not presence
Medium
High
04
Cloud skills gap slows migration or incident response
✓
Rehost-first held; step-down contracted, not assumed
Low
Medium
05
State conditions restrict where member data may be processed
✓
Not a risk — a condition of operating; recorded so it is not re-proposed
High
High
15

## Slide 16
RISK REGISTER
Risk Register (1 of 2)
R-01
Member identity resolution volume
LIKELIHOOD HIGH
IMPACT HIGH
MATERIALIZED. Scored Critical since February 2024, ten weeks before the profiling run confirmed it. The measured review band is 26% against a modeled 8%; the resulting queue cannot be worked inside the remaining term.
OWNER Dr. A. Ravindran
STATUS Materialized — escalated today
Mitigation: Second onshore steward cohort approved and recruiting before the finding; the extension sought today is the remaining response. The register is not being rediscovered — it is being acted on.
R-05
Core administration cutover slips past the TSA plan date
LIKELIHOOD HIGH
IMPACT HIGH
Consequential to R-01 rather than independent — the cutover is sound but the identity work it depends on is not finishing inside the term.
OWNER W. Ferriday
STATUS Raised — was Medium, now High
Mitigation: Resolved by the same extension; no separate mitigation is proposed, because a second response to one cause is duplicated cost.
16

## Slide 17
RISK REGISTER
Risk Register (2 of 2)
R-02
Attrition of retention-covered target staff
LIKELIHOOD MEDIUM
IMPACT HIGH
Steady. No departures among retention-covered roles this period; the knowledge-transfer obligations are being met on schedule.
OWNER D. Marchbanks
STATUS Stable — unchanged
Mitigation: Retention tied to transfer obligations rather than presence; acceptance recorded per procedure and per named receiver.
R-03
Cloud skills gap slows migration or incident response
LIKELIHOOD LOW
IMPACT MEDIUM
LOWERED. Migration waves have run without a capability-driven incident and the managed-service step-down is proceeding to contract.
OWNER B. Trammell
STATUS Lowered — was High, now Medium
Mitigation: Rehost-first held; landing zone preceded every wave; step-down contracted rather than assumed.
17

## Slide 18
ISSUES
Issues — Raised & Resolved
Issues that arose during execution and how each was dispositioned — the record of what actually happened, not just what we watched for.
IDENTIFIED ISSUES
ACTION / RESOLUTION
OWNER
STATUS
01
Clerical review queue exceeds the transitional services term
✓
Extension of three months sought today, funded from management reserve
C. Tyrrell
escalated
02
Contingency substantially committed at month 8
✓
Reserve draw requested; no further contingency commitments without Board approval
D. Ashmore
open
03
Cumulative synergy capture running behind the deal model
✓
Both run-rate and cumulative capture reported every period; neither netted against the other
S. Beauregard
open
04
Offshore steward capacity proposed as a remedy
✓
Examined and rejected — barred under the state contract; rejection recorded
F. Underhill
closed
05
Two deferrals require named owners before they leave the plan
✓
Both accepted by the owning leads rather than imposed
C. Tyrrell
closed
18

## Slide 19
DECISIONS & CHANGES
Decisions & Changes Since Kickoff
Two decisions are ratified and one is sought today — the one sought is the reason this meeting was called.
D-04
Re-baseline to a Class 2 estimate accepted — $55,944,000 cost baseline replacing the Class 5 deal model
Steering Committee January 2024
D-05
Offshore steward capacity rejected; onshore cohort approved instead at higher cost
Steering Committee April 2024
NEEDED
Three-month transitional services extension to end of December 2024, funded from management reserve
Executive Sponsor — SOUGHT TODAY May 14, 2024
19

## Slide 20
NEXT STEPS
The Look-Ahead
1
On approval
Transitional services extension executed with the divesting parent
2
Within 2 weeks
Revised exit criteria issued service by service against the new date
3
Monthly
Both synergy measures reported — run-rate and cumulative capture, never one alone
20

## Slide 21
QUESTIONS?
Spend the margin we bought. Protect the thing we cannot buy back.
C. Tyrrell · Program Manager, Integration
ACME Health / Cumberland Valley Health Plan Integration
All program artifacts available at ct-pm.pages.dev/ma-integration/