## 1 An Estimate Without a Method
A basis of estimate records | So that
The method | A reviewer can tell whether the approach suits the thing being estimated. Bottom-up on an undefined scope is precision theater; analogous on a fully specified study list is laziness.
The cost driver | Everyone knows what would move the number. If the driver is participants dosed, a two-month schedule slip that changes no participant count barely moves the cost — and a protocol amendment adding one visit moves it a great deal.
The source | The estimate can be re-derived by somebody else. “Vendor quotation” and “experience” are different kinds of claim.
The accuracy class | The reader knows how much of the number to believe. A figure quoted to the dollar from a Class 4 estimate is asserting a precision nobody has.

## 2 Three Methods Chosen by What
Method | Pools | Value | When it is the right choice
Parametric | 6 | $172,300,000 | A unit rate multiplied by a countable driver. Right where the driver is fixed by protocol and the rate is contracted — which describes most clinical cost in this program.
Bottom-up | 2 | $17,700,000 | Built from a defined list of things. Right where the scope is genuinely enumerable: a study list, a batch count. Wrong wherever the list is the thing you are uncertain about.
Analogous | 3 | $27,000,000 | Scaled from comparable programs. The honest choice where nothing is fixed yet — and it should be declared rather than dressed up as something firmer.

## 3 The Basis Pool by Pool
Pool | Amount | Method | Cost driver | Source | Class | What the estimate rests on
Nonclinical pharmacology & GLP toxicology | $8,500,000 | Bottom-up | Study count and species | CRO quotations against a defined study list | 2 | Fully scoped before Gate 1. Study-by-study pricing from three bidders; the estimate is close to a contract.
CMC — early development | $6,200,000 | Analogous | Molecule class | Two prior peptide programs, adjusted for step count | 4 | ⚠ The weakest early estimate in the program. Process development cost scales with problems encountered, and problems encountered are not knowable in advance.
IND-enabling package & submission | $3,800,000 | Parametric | Document count | Internal hours per module × blended rate | 3 | Assembly work with a well-understood shape and low historical variance. The module list is fixed by regulation, so the only real uncertainty is review cycles.
Phase 1 clinical | $8,500,000 | Parametric | Participants × per-participant cost | Unit pricing from the Phase 1 unit | 2 | Single site, fixed protocol, 64 participants. One of the two most reliable estimates here.
Phase 2 clinical | $38,000,000 | Parametric | Participants × per-participant cost | CRO unit pricing, blended across regions | 3 | 480 participants at a known per-participant rate. The rate is contracted; the participant count is protocol-fixed.
Phase 3 clinical | $109,100,000 | Parametric | Participants × per-participant cost × duration | Meridian master services agreement unit rates | 3 | ⚠ 50% of the program in one pool. Reliable per participant and sensitive to anything that changes the participant count or the visit schedule — a single added assessment moves this pool by more than most pools cost.
NDA preparation & review support | $12,400,000 | Analogous | Submission complexity | Two prior NME submissions, escalated | 4 | The Integrated Summaries are new analyses rather than compilations, and their effort is hard to predict before the data exists.
CMC scale-up & process validation | $9,200,000 | Bottom-up | Batches and validation runs | Aldergate batch pricing plus internal oversight hours | 3 | Batch pricing is firm. The number of batches is not, if a validation run fails.
Regulatory affairs | $7,600,000 | Parametric | Internal hours | Roster hours × blended rate | 2 | Internal labor with a known rate and a known headcount. Effectively a control estimate.
Program management | $5,300,000 | Parametric | Internal hours | Roster hours × blended rate | 2 | As above — a small pool with a known headcount and a known rate, so the confidence is high and the amount is too small to matter if it is not.
External fees, advisors & other non-labor | $8,400,000 | Analogous | Program size | Historical percentage of comparable programs | 4 | A residual category by construction, and residual categories are always the least well estimated.
Base program | $217,000,000

## 4 Accuracy Class and Why Effort
| Name | Expected accuracy | Provision | This program | Share | When it applies
Class 5 | Order of magnitude | -50% / +100% | 35% | — | — | Analogous only. Appropriate at Gate 0 for anything past the next stage.
Class 4 | Study estimate | -30% / +50% | 20% | $27,000,000 | 12% | Parametric from comparable programs, few parameters fixed.
Class 3 | Budget estimate | -20% / +30% | 12% | $160,100,000 | 74% | Parametric with the driving parameters fixed. Most of this program at Gate 4.
Class 2 | Control estimate | -15% / +20% | 8% | $29,900,000 | 14% | Bottom-up on a defined scope, vendor pricing in hand.
Class 1 | Definitive | -5% / +10% | 5% | — | — | Executed contracts and a fixed protocol. Rare before the final stage.

## 5 Contingency Is an Output Not
Value
Provision implied by the estimate mix | $27,004,000
As a percentage of base | 12.4%
Authorized in the charter | $26,040,000 — 12.0%
Difference | 964,000 (0.4% of base)

## 6 How the Estimate Matures
Gate | Best class achievable | Why
Gate 0 | Class 5 | Order of magnitude for everything past Stage 1. The program was authorized on a number that could have been wrong by a factor of two in either direction.
Gate 1 | Class 4 | Nonclinical actualized; clinical still analogous.
Gate 3 | Class 3 | Phase 2 contracted; Phase 3 parametric on agreed unit rates.
Gate 4 | Class 3 | Phase 3 protocol fixed and the CRO rate card executed. This is as good as it gets before the trial runs.
Gate 5 | Class 2 | Everything but review support is actual or contracted.

## 7 What This Program Estimated B
Estimate | What was assumed | Why it was wrong
Site activation duration | 18 weeks from selection to green light | ⚠ Not a cost estimate at all — a duration estimate that drives cost. It was built from an average across prior programs without adjusting for the fact that this trial activates 260 sites simultaneously rather than sequentially, which contends for the same contracting and ethics-review capacity.
Early CMC development | Analogous from two prior peptide programs | The comparators had six- and seven-step syntheses that transferred without incident. Analogous estimating carries the assumption that the comparator was typical, and a method transfer that fails is not typical — it is the tail.
External fees and advisors | A historical percentage of program size | A residual category estimated as a percentage is a placeholder with a decimal point. It was adequate, and it was adequate by luck rather than by method.

## About
Basis of Estimate
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Basis of Estimate · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.