## 1 The Case and the Number That
Value
Success-case NPV, conditional on approval | $1,362,000,000
Internal rate of return | 43.6%
Peak annual revenue | $1,640,000,000
Probability of technical and regulatory success at Gate 0 | 7.0% — 47% × 30% × 50%
⚠ Risk-adjusted expected value at Gate 0 | $96,000,000
Authorized program cost | $243,040,000

## 2 Why the Number Moves Without
Gate | Risk-adjusted NPV | Movement
Gate 0 — candidate selection | $96,025,247
Gate 3 — Phase 2 readiness | $204,309,036 | ×2.1 vs Gate 0
Gate 4 — Phase 3 initiation (today) | $681,030,120 | ×7.1 vs Gate 0
Gate 5 — submission | $1,253,095,420 | ×13.0 vs Gate 0

## 3 The Assumption Stack
Assumption | Value | What it rests on
Eligible US population | 41,000,000 | Adults meeting the BMI criteria. Epidemiological, stable, and the least contested number in the chain.
Treated fraction | 4.0% | ⚠ The proportion who will be on ANY drug in this class at peak. A market-growth assumption, not a share assumption, and the one with the widest credible range.
Our share of treated patients | 8% | Fourth entrant into a class where two incumbents hold preferred formulary position. Assumes a differentiating claim we do not yet have.
Net price per patient-year | $12,500 | ⚠ WAC less an assumed 26% gross-to-net erosion. The assumption the CFO abstained over, un-refreshed since the original case.
Persistence at 12 months | 80% | Chronic therapy. Every revenue model in this class is a persistence model wearing a revenue model's clothes.

## 4 Sensitivity
Driver | Low | Base | High | NPV swing
Share of treated patients | 5% | 8% | 11% | ██████████████ $512M
Net price per patient-year | $10,500 | $12,500 | $13,500 | ███████████ $386M
Treated fraction | 3.0% | 4.0% | 5.0% | █████████ $341M
Persistence at 12 months | 70% | 80% | 85% | ██████ $214M
Launch timing | +12 months | on plan | — | ███ $118M
Program cost | +20% | on plan | −10% | █ $43M

## 5 What Changed Since Gate 3
Element | Direction | What happened
Probability of success | de-risked | Phase 2 survived, so the Phase 2→3 transition probability no longer applies. Risk-adjusted value rises without the asset improving.
Scope | CR-02 added | A cardiovascular sub-study, $6,400,000, pre-empting a likely post-marketing requirement.
Cost | contingency drawn | The March analytical method transfer failure. Absorbed within contingency; ceiling unchanged.
Tolerability evidence | weaker than target | ⚠ Phase 2 GI discontinuation 5.1% against a ≤4% target and a ≤7% minimum. Clears the minimum, misses the target, and it is the differentiator.

## 6 Where the Case Is Soft
Not claimed | Why not
That the program is worth its cost on expected value | It is not, and was not at Gate 0. Expected value then was 96M against an authorized 243M. ⚠ The case is for the OPTION, not the asset.
That the share assumption is defensible today | It rests on a differentiating claim that sits fourth in a six-position testing hierarchy and has not been tested. Gate condition GC-03 exists because of it.
That the gross-to-net assumption is current | ⚠ It is not. It has not been refreshed since the original case, which is the recorded basis of the Chief Financial Officer's abstention at this gate.
That cost control determines the outcome | Program cost is the LEAST sensitive driver in the model — a 20% overrun moves NPV less than a 3-point share miss. ⚠ A program managed primarily to budget is optimizing the smallest lever it has.

## 7 The Recommendation
Position
Recommendation | Proceed — release $125,800,000 for Stage 4
On what basis | Phase 2 delivered a dose and an efficacy signal sufficient to support two pivotals. The remaining risk is Phase 3 execution and approval, which is the risk this stage exists to retire.
What the Committee is NOT being asked | ⚠ To approve the commercial forecast, the label, or the launch. This gate authorizes a tranche and a Phase 3 program. Nothing further.
Conditions proposed | CMC readiness to a defined standard before Gate 5; the CV sub-study protocol issued to the DMC; a market access evidence plan approved and executed.

## About
Gate 4 Business Case Package
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Gate 4 Business Case Package · tabled 30 June 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.