## 1 The Register
Ref | Change | Raised by | Decided | Outcome | Reasoning | Full form
CR-01 | Add an Asian-population cohort to Phase 2 | Program | 09 Oct 2024 | Approved | Increases N by 50. Supports the later EU and Asia-Pacific strategy without a separate bridging study. | record
CR-02 | Add a cardiovascular outcomes sub-study to Phase 3 | Program | 20 Apr 2026 | Approved | Adds $6,400,000 and six months to the Phase 3 window. Pre-empts a post-marketing requirement (D-06). | record
CR-D1 | Add a head-to-head comparative tolerability trial | J. Barrington | 2025-11-14 | Declined | ⚠⚠ The most consequential decline in the program. Would have cost roughly $34,000,000 and eighteen months against a fixed patent expiry. Defensible on the information available — and it is the evidence a payer asks for first, which this program will not have. | record
CR-D2 | Extend Phase 3 to a third pivotal in an adolescent population | Dr. A. Okoye | 2026-02-03 | Declined | PREA is satisfied by the agreed initial Pediatric Study Plan (iPSP) with a post-approval deferral. Running it now would add cost and calendar to satisfy an obligation already deferred. | record
CR-D3 | Switch the primary endpoint to percent achieving ≥10% reduction | Dr. F. Achterberg | 2026-01-20 | Declined | ⚠ Statistically attractive and agreed with the agency at End-of-Phase-2 as a KEY SECONDARY. Changing a co-primary after EOP2 alignment would have reopened a settled question and invited a new one. | record
CR-D4 | Add a second contract manufacturer for drug product | Dr. K. Oyelaran | 2026-04-28 | Declined | Technology transfer, a second validation and a second pre-approval inspection — roughly two years, against a filing date that does not move. Recorded as an accepted single-source risk instead. | record

## 2 CR02 A Change That Was Appro
Step | What happened
Raised | By the Chief Medical Officer, with the alternative stated: do nothing, and accept a likely post-marketing requirement imposed at approval instead.
Impact | $6,400,000, six months added to the Phase 3 window, a new endpoint, a separate analysis and a standalone clinical study report. ⚠ Checked against the traceability matrix: it creates an entirely NEW chain rather than altering an existing one.
Routed | Tier 4 — scope and anything touching the submission. Development Committee, not the Program Director.
Decided | Approved. Funded from contingency; the ceiling did not move.
Baselined | Held as a discrete work package (1.6.5) rather than absorbed into the Phase 3 clinical account.
Verified | Sub-study protocol issued to the (Independent) Data Monitoring Committee (DMC) 12 August 2026, closing gate condition GC-02.

## 3 CRD1 The Decline That Matter
What it would have provided | ⚠ The comparative evidence a payer asks for first, and the clinical claim the label strategy is built on — generated directly rather than inferred from an indirect comparison.
What it would have cost | Roughly $34,000,000 and eighteen months, against a patent that expires on a fixed date.
Why it was declined | The eighteen months came off the commercial life at the far end, the cost was outside contingency, and the tolerability endpoint was already positioned in the Phase 3 hierarchy — so the evidence would be generated anyway, if the endpoint cleared.
What actually happened | ⚠⚠ The endpoint sits fourth in a six-position hierarchy. It is generated, and it is claimable only if three endpoints above it succeed first.

## 4 The Lifecycle and Where (1)
Step | Who | What must happen
Raise | Anyone | A change request states the change, the driver, and the option of NOT doing it. ⚠ A request with no stated alternative is a proposal, not a request.
Impact | PMO with the affected owners | Cost, schedule, scope, quality, risk. Checked against the traceability matrix for what else it touches.
Route | PMO | To the authority tier the impact demands, never to the tier that is easiest to reach.
Decide | The named authority | Approve, decline, or defer with a stated review date. ⚠ Deferral is a decision and is recorded as one.
Baseline | PMO | An approved change updates the scope, schedule and cost baselines together, or none of them.
Verify | Control account owner | The change is confirmed implemented before the request is closed. ⚠ Approved is not done.

## 4 The Lifecycle and Where (2)
Impact | Authority | How it is recorded
Within a work package, no cost or date impact | Control account owner | Recorded in the control account; no register entry
Across work packages, within the control account envelope | Control account owner | Change note, notified to the PMO
Cost impact within contingency, no date or scope change | Program Director | Contingency draw recorded WITH the rejected alternative
Scope, milestone dates, or anything touching the submission | Development Committee | Change request; CR-01 and CR-02 are the two raised
The authorized ceiling | Board | Ceiling is not a Committee matter at any size
Anything affecting participant safety | Immediate — no approval required | Safety bypasses commercial escalation entirely

## 5 What Never Reached the Regist
Never reached the register | Why, and what it cost
Protocol clarifications issued as letters, not amendments | ⚠ Legitimate where genuinely clarifying, and the boundary is thin. A 'clarification' that changes what a site does is an amendment wearing a cheaper name.
Additional monitoring visits at underperforming sites | Within the Contract Research Organization (CRO)'s contracted scope, so no change order. It consumed monitoring capacity budgeted for elsewhere and appears in no register.
Extra analytical method qualification runs after the transfer failure | Absorbed into the Chemistry, Manufacturing and Controls (CMC) control account envelope under tier 2 authority. Correct by the rules, and it means the true cost of I-02 is spread across two records.
Growing scope of the market access evidence package | ⚠ Driven by GC-03 rather than by a change request. A gate condition can expand work without ever passing through change control.

## About
Change Control Log
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Change Control Register · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.