## 1 The Register
Ref | Change | Raised by | Decided | Outcome | Reasoning | Full form
CR-01 | Add an Asian-population cohort to Phase 2 | Program | 09 Oct 2024 | Approved | Increases N by 50. Supports the later EU and Asia-Pacific strategy without a separate bridging study. | record
CR-02 | Add a cardiovascular outcomes sub-study to Phase 3 | Program | 20 Apr 2026 | Approved | Adds $6,400,000 and six months to the Phase 3 window. Pre-empts a post-marketing requirement (D-06). | record
CR-D1 | Add a head-to-head comparative tolerability trial | J. Barrington | 2025-11-14 | Declined | ⚠⚠ The most consequential decline in the program. Would have cost roughly $34,000,000 and eighteen months against a fixed patent expiry. Defensible on the information available — and it is the evidence a payer asks for first, which this program will not have. | record
CR-D2 | Extend Phase 3 to a third pivotal in an adolescent population | Dr. A. Okoye | 2026-02-03 | Declined | PREA is satisfied by the agreed iPSP with a post-approval deferral. Running it now would add cost and calendar to satisfy an obligation already deferred. | record
CR-D3 | Switch the primary endpoint to percent achieving ≥10% reduction | Dr. F. Achterberg | 2026-01-20 | Declined | ⚠ Statistically attractive and agreed with the agency at End-of-Phase-2 as a KEY SECONDARY. Changing a co-primary after EOP2 alignment would have reopened a settled question and invited a new one. | record
CR-D4 | Add a second contract manufacturer for drug product | Dr. K. Oyelaran | 2026-04-28 | Declined | Technology transfer, a second validation and a second pre-approval inspection — roughly two years, against a filing date that does not move. Recorded as an accepted single-source risk instead. | record

## 2 CR02 A Change That Was Appro
Step | What happened
Raised | By the Chief Medical Officer, with the alternative stated: do nothing, and accept a likely post-marketing requirement imposed at approval instead.
Impact | $6,400,000, six months added to the Phase 3 window, a new endpoint, a separate analysis and a standalone clinical study report. ⚠ Checked against the traceability matrix: it creates an entirely NEW chain rather than altering an existing one.
Routed | Tier 4 — scope and anything touching the submission. Development Committee, not the Program Director.
Decided | Approved. Funded from contingency; the ceiling did not move.
Baselined | Held as a discrete work package (1.6.5) rather than absorbed into the Phase 3 clinical account.
Verified | Sub-study protocol issued to the DMC 12 August 2026, closing gate condition GC-02.

## 3 CRD1 The Decline That Matter
What it would have provided | ⚠ The comparative evidence a payer asks for first, and the clinical claim the label strategy is built on — generated directly rather than inferred from an indirect comparison.
What it would have cost | Roughly $34,000,000 and eighteen months, against a patent that expires on a fixed date.
Why it was declined | The eighteen months came off the commercial life at the far end, the cost was outside contingency, and the tolerability endpoint was already positioned in the Phase 3 hierarchy — so the evidence would be generated anyway, if the endpoint cleared.
What actually happened | ⚠⚠ The endpoint sits fourth in a six-position hierarchy. It is generated, and it is claimable only if three endpoints above it succeed first.

## 4 The Lifecycle and Where (1)
Step | Who | What must happen
Raise | Anyone | A change request states the change, the driver, and the option of NOT doing it. ⚠ A request with no stated alternative is a proposal, not a request.
Impact | PMO with the affected owners | Cost, schedule, scope, quality, risk. Checked against the traceability matrix for what else it touches.
Route | PMO | To the authority tier the impact demands, never to the tier that is easiest to reach.
Decide | The named authority | Approve, decline, or defer with a stated review date. ⚠ Deferral is a decision and is recorded as one.
Baseline | PMO | An approved change updates the scope, schedule and cost baselines together, or none of them.
Verify | Control account owner | The change is confirmed implemented before the request is closed. ⚠ Approved is not done.

## 4 The Lifecycle and Where (2)
Impact | Authority | How it is recorded
Within a work package, no cost or date impact | Control account owner | Recorded in the control account; no register entry
Across work packages, within the control account envelope | Control account owner | Change note, notified to the PMO
Cost impact within contingency, no date or scope change | Program Director | Contingency draw recorded WITH the rejected alternative
Scope, milestone dates, or anything touching the submission | Development Committee | Change request; CR-01 and CR-02 are the two raised
The authorized ceiling | Board | Ceiling is not a Committee matter at any size
Anything affecting participant safety | Immediate — no approval required | Safety bypasses commercial escalation entirely

## 5 What Never Reached the Regist
Never reached the register | Why, and what it cost
Protocol clarifications issued as letters, not amendments | ⚠ Legitimate where genuinely clarifying, and the boundary is thin. A 'clarification' that changes what a site does is an amendment wearing a cheaper name.
Additional monitoring visits at underperforming sites | Within the CRO's contracted scope, so no change order. It consumed monitoring capacity budgeted for elsewhere and appears in no register.
Extra analytical method qualification runs after the transfer failure | Absorbed into the CMC control account envelope under tier 2 authority. Correct by the rules, and it means the true cost of I-02 is spread across two records.
Growing scope of the market access evidence package | ⚠ Driven by GC-03 rather than by a change request. A gate condition can expand work without ever passing through change control.

## About
Change Control Register
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Change Control Register · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.