## Draw Authority
Amount | Approver | Recording | Evidence required
Up to $500,000 | Program Director | Notified to the Committee at the next checkpoint. | Operational recovery within an authorized stage.
$500,001 – $2,500,000 | Committee Chair with CFO concurrence | Minuted at the next Committee meeting. | Requires a written statement of the rejected alternative.
Above $2,500,000 | Full Development Committee | Formal decision, recorded in the register. | Requires alternatives assessment and an impact statement on the remaining reserve.
Any draw that would exhaust the reserve | Board | Escalated. The reserve sits inside the ceiling. | Exhausting contingency is a ceiling matter, not a contingency matter.

## 2 Register
Ref | Draw | Against | Type | Approved | Amount
CD-01 | Cardiovascular outcomes sub-study | CR-02 | Approved change | 20 Apr 2026 | $7,200,000
CD-02 | CMC analytical method transfer recovery | I-02 | Materialised issue | 24 Mar 2026 | $1,850,000
Total drawn |  |  |  |  | $9,050,000
Reserve remaining |  |  |  |  | $16,990,000

## 3 How the Reserve Was Sized
Consideration | Effect on the percentage
Stage of the program at authorization | Late-phase programs carry less uncertainty per dollar than early ones. Published practice puts 10–15% on late-phase work and 15–20% on early phase.
Concentration of spend | 58% of base sits in one stage. A reserve has to be adequate against the stage that dominates, not against the average stage.
Proportion of cost that is external | 83%. Contracted work varies less than internal effort, which argues for a lower reserve — but change orders are the mechanism by which it varies, and they are not free.
Regulatory dependency | An agency expectation can add scope at any time. CR-02 is exactly that case, and it alone consumed 28% of the reserve.

## 4 Draw Records (1)
Field | Record
Amount | $7,200,000 (28% of reserve)
Drawn against | CR-02 — approved change
Approved | 20 April 2026
Decided by | Development Committee

## 4 Draw Records (2)
Field | Record
Amount | $1,850,000 (7% of reserve)
Drawn against | I-02 — materialised issue
Approved | 24 March 2026
Decided by | Development Committee

## 5 Reading the Two Draws Togethe
| CD-01 — CR-02 | CD-02 — I-02
Origin | A choice the program made | Something that went wrong
Foreseen? | Yes — arose from a known agency expectation | No — was not on any risk register
What it buys | Scope: a study designed on the program's terms | Recovery: getting back to where the plan assumed the program already was
Lesson | None. The mechanism worked as intended. | Technical transfer between organizations is systematically under-registered

## 7 Forecast
Remaining exposure | Reserve implication
PPQ campaign failure | Three consecutive batches. A failure costs the sequence plus investigation — the largest single plausible draw remaining.
Pre-approval inspection finding | R-07, rated Low. Remediation cost depends entirely on what is found.
Agency information requests during review | Usually absorbed in regulatory effort; a request for new analysis is not.
Enrolment recovery beyond the current plan | Additional sites are the recovery lever, and sites cost money.
Phase 3 read-out | No reserve implication. A failed pivotal does not draw contingency — it ends the program.

## Requests Declined
Date | Request | Amount | Reason declined
2027-04-11 | Additional biomarker sub-study | $3,200,000 | Scientifically interesting, not required for the filing and not in the TPP. Contingency is not a mechanism for funding scope the gate did not authorize.
2028-02-27 | Accelerated EU dossier preparation | $2,400,000 | EU filing is explicitly out of scope (Charter §4). A declined scope item does not return as a contingency request.
2029-05-09 | Additional launch market research | $900,000 | Commercial launch investment sits under a separate authorization. Declined on jurisdiction, not on merit.

## 6 Remaining Reserve
Measure | Amount
Reserve at authorization | $26,040,000
Drawn to date | $9,050,000
Remaining | $16,990,000
Remaining as % of unspent base | 14.6%

## About
Contingency Register
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Contingency Register · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.