## 1 Five Options Compared
Option | Cost to Vitalis | Risk-adjusted value | Value per $1 at risk | Retained upside | Risk carried | Assessment
Kill at Gate 0 | $0 | $0 | — | None | None | ⚠ The baseline every other option is measured against, and the one most often left out. Zero cost, zero return, and the capability built over 3.7 years of discovery is written off with it.
Develop internally (adopted) | $243,040,000 | $96,000,000 | 0.39 | 100% | All of it | ⚠⚠ Expected value BELOW the authorized cost. Justified as buying the OPTION to continue, not the asset — and only defensible because the money is released one stage at a time.
Out-license after Phase 2 | $74,400,000 | $71,000,000 | 0.95 | ~15% royalty | Partner carries Phase 3 | Spend through Gate 3 only, then license. ⚠ Removes the largest risk and most of the return. The economics are close to internal development on a risk-adjusted basis and the distributions are completely different.
Co-develop with a partner | $121,500,000 | $84,000,000 | 0.69 | ~50% | Shared | Halves cost and upside. ⚠ Adds a governance layer with joint decision rights — the hidden cost is that gate decisions become negotiations.
Sell the asset at Gate 3 | $74,400,000 | $62,000,000 | 0.83 | None | Transferred entirely | A clean exit with a known number. ⚠ Forecloses everything, and a company that sells every asset at Phase 2 has no pipeline and eventually no reason to run discovery.

## 2 The Two Options Nobody Wants
Why it belongs in the analysis anyway
Kill at Gate 0 | ⚠ The baseline every other option is measured against. Without it, the comparison has no zero and every option looks positive. It is also the option a governance system exists to keep available — KILL is not failure, and a portfolio where nothing is ever killed at Gate 0 is not selecting, it is queueing.
Sell the asset at Gate 3 | A clean exit at $62,000,000 risk-adjusted, with every downstream risk transferred. ⚠ It forecloses everything — and a company that sells every asset after Phase 2 has no marketed products, eventually no reason to run discovery, and a valuation built entirely on other people's execution.

## 3 Benefits
Benefit | Type | When it lands | Note
Financial return on approval | Financial | 2031 onward | The success-case NPV. ⚠ Conditional, and the condition does most of the work.
A registered NME and an approved US label | Strategic | At approval | An asset the company owns outright, with 5 years NCE exclusivity and patent life to 2039.
First in-house 505(b)(1) capability | Institutional | Built through Stages 1–5 | ⚠ Not in the Gate 0 case. The company can now run a registrational program without a partner — and it is the benefit most likely to outlast the product.
A functioning stage-gate governance system | Institutional | Built through the program | ⚠ Also not in the Gate 0 case. Reusable across the pipeline.
Patients treated | Societal | From launch | Real and deliberately not monetized here. Assigning a dollar value to it would make the case look better and the analysis worse.

## 4 Disbenefits
Disbenefit | Foreseeable at Gate 0? | Assessment
Opportunity cost of the R&D budget | Foreseeable at Gate 0 | $243,040,000 not spent on other pipeline candidates over 7.6 years. ⚠ Recorded because a cost-benefit analysis that omits the alternative use of the money is not one.
Single-source manufacturing dependency | Foreseeable at Gate 0 | Accepted deliberately; a second site does not fit the ceiling.
Organizational attention | Foreseeable, not recorded at Gate 0 | ⚠ 109 people and the Committee's agenda for seven years. The company can run one program of this size at a time, and that constraint appears in no register.
Fourth-to-market commercial position | ⚠ Foreseeable at Gate 0 and NOT recorded | ⚠⚠ The disbenefit that mattered. It was knowable at candidate selection, it was not written down, and it is the one the outcome turned on.

## 5 How This Reads at Each Gate
Read at | What the comparison says | Still actionable?
Gate 0 | All five options open. Internal development is the highest-value and least capital-efficient choice. | ⚠ Yes. This is the only moment the full comparison means anything.
Gate 3 | Out-licensing and selling are still live; the sunk $74,400,000 is irrelevant to the forward decision. | Yes, and this is the decision point most programs skip. The question was not asked.
Gate 4 | ⚠ Partnering is theoretically possible and practically not — a partner joining at Phase 3 initiation buys the expensive half. | Barely. The economics have moved against every alternative.
Gate 5 | One option remains: submit. | No. The comparison is now a historical document.

## 6 What Would Have Changed the A
If this had been different | The answer becomes | Why
Probability of success below ~5% | Out-license after Phase 2 | ⚠ At 7.0% the expected value is already below the authorized cost. Two points lower and the capital at risk stops being defensible on any reading.
Second or third to market rather than fourth | Internal development, decisively | ⚠⚠ The share assumption is the model's largest driver. An earlier entrant needs no differentiating claim to hold formulary position, and the whole access problem disappears.
A partner offering more than ~60% of economics | Co-develop | At 50% the governance cost is not worth it — gate decisions become negotiations. Above 60% the risk transfer starts to pay for the friction.
A second asset competing for the same budget | ⚠ Any option that frees capital | The opportunity cost is recorded as a disbenefit and priced at zero, because there was no competing candidate. With one, out-licensing wins on capital efficiency alone.
A head-to-head trial affordable inside the ceiling | Internal, and comfortably | It would have retired the differentiation risk that the whole comparison hinges on. ⚠ It was priced at $34,000,000 and declined — see CR-D1.

## About
Cost-Benefit Analysis
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Cost-Benefit Analysis · options priced at Gate 0, reviewed 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.