## 1 Leading and Lagging
| Lagging | Leading
Answers | Did it happen? | Is it going to?
Examples here | Milestones met, spend to date, participants randomized to date | Site activation cycle time, monitoring visit completion, batch right-first-time
Trustworthy? | Completely — it is a fact | Only probabilistically. A leading indicator can be wrong, and sometimes is.
Actionable? | No. It is already true. | Yes, and that is the entire point — there is still time.
Failure mode | Steering by the wake | Reacting to noise, or watching a measure that leads nothing

## 3 Indicators
Ref | Indicator | Domain | Current | 3-month trend | Target | Lead time | Owner
LI-1 | Site activation cycle time | Enrolment | 22.4 weeks | ↑ worsening | ≤18 | 5 mo | Dr. R. Molyneux
LI-2 | Sites reaching green light | Enrolment | 4 per month | ↓ worsening | ≥8 | 5 mo | Dr. R. Molyneux
LI-3 | Randomizations vs required run-rate | Enrolment | 88 % of required | ↓ worsening | ≥100 | — | Dr. R. Molyneux
LI-4 | Screen-failure rate | Enrolment | 40 % | → worsening | ≤42 | — | Dr. R. Molyneux
LI-5 | Queries open over 30 days | Data | 236 count | ↓ improving | ≤300 | 14 mo | Dr. F. Achterberg
LI-6 | Protocol deviations per 100 participants | Data | 7.2 rate | ↑ worsening | ≤6 | 18 mo | Dr. R. Molyneux
LI-7 | Monitoring visits completed vs plan | Oversight | 91 % | ↓ worsening | ≥95 | 6 mo | G. Petrossian
LI-8 | Expedited safety reports on time | Safety | 100 % | → worsening | ≥100 | — | Dr. N. Halloran
LI-9 | Batch right-first-time | CMC | 91 % | ↑ improving | ≥90 | 9 mo | Dr. K. Oyelaran

## 4 What Each One Predicts
Ref | What it predicts | Source system | Lead time
LI-1 | Randomizations, about five months later. Every week added here is a week the site is not enrolling. | CTMS | 5 months
LI-2 | The enrolment run-rate ceiling. A site that is not activated cannot randomize anybody. | CTMS | 5 months
LI-3 | Last-participant-in, and therefore database lock and the filing date, one for one. | IRT | — concurrent
LI-4 | Nothing, currently. Included because it is the first thing anybody blames, and holding flat is how you rule it out. | EDC | — concurrent
LI-5 | Database lock readiness. Ageing queries are the work that will not compress at the end. | EDC | 14 months
LI-6 | Inspection findings and per-protocol population size. Rising deviations mean site training is decaying faster than monitoring catches it. | CTMS | 18 months
LI-7 | Everything monitoring would have found. A missed visit does not create a problem; it delays the discovery of one. | CRO report | 6 months
LI-8 | Nothing — it is a compliance floor, not a trend. Any value below 100 is an issue, not a dip. | Safety database | — concurrent
LI-9 | PPQ readiness and the registration batch schedule, which gates the filing independently of anything clinical. | MES | 9 months

## 5 The Measures That Were Reject
Excluded | Why
Percent complete | Estimated by the people doing the work, unfalsifiable, and it only ever moves one way. The WBS uses 0/100 earning for the same reason.
Total queries raised | Volume is an activity measure. A rising query count can mean poor data OR good monitoring, and the two require opposite responses. Ageing carries the information.
Cumulative spend | Rises monotonically whatever happens. It cannot go down, so it cannot warn.
Sites activated (cumulative) | Same defect. The rate is a leading indicator; the total is a scoreboard.
Headcount vacancies | A resourcing input, not a program outcome. It belongs to the function heads, and putting it here invites the program to manage something it does not own.
Covered lives | A vanity metric even at launch. Preferred-tier placement is the measure that predicts revenue; covered lives predicts nothing.

## 6 Where the Numbers Come From
Source | Indicators | Refresh | Why it matters
IRT | LI-3 | Real time | The randomization system of record. Neutral, and the same source used to trigger the CRO's milestone payments — so both parties read one number.
CTMS | LI-1, LI-2, LI-6 | Daily | Site status and deviations. Maintained by Meridian under the contract, audited by the sponsor.
EDC | LI-4, LI-5 | Daily | Clinical data capture. Query ageing is computed rather than reported, so it cannot be presented favorably.
Safety database | LI-8 | Real time | Separate from the EDC by design — which is why SAE reconciliation between the two is a control rather than a formality.
CRO performance report | LI-7 | Monthly | ⚠ The only vendor-reported figure on the panel. Verified quarterly against visit reports in the TMF, because a self-reported completion rate is an assertion until it is.
MES | LI-9 | Per batch | Manufacturing execution at Aldergate.

## 7 How to Read It Badly
Failure | What it looks like | The defense
Reacting to a single month | An indicator moves, somebody asks for a plan, the plan is written, the indicator moves back because it was noise. Cost: the plan, and the credibility of the next one. | Trend over three months, and thresholds on the level rather than the movement.
Managing the indicator instead of the thing | Query ageing improves because queries are closed without resolution. Activation cycle time improves because sites are declared active earlier. | Definitions fixed at Gate 4 — a site is not activated until green light, a query is not closed until the data changes or the query is withdrawn with a reason.
Treating amber as a state rather than a clock | An indicator sits amber for a year and everyone stops seeing it. This is the same failure the status report guards against with the three-period rule. | Every amber carries a date by which it should have recovered, and the dashboard is read alongside the status report rather than instead of it.

## About
Program Dashboard
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Program Dashboard · twelve months to 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.