## 1 Position at 15 October 2026
Measure | Value
Randomization target | 2,480 across two pivotal trials
Randomized to date | 1,684 (68%)
Planned to date | 1,760
Variance to curve | 76 behind (96% of plan)
Screened | 2,910
Screen failures | 1,142
Currently in screening | 84
Screen-failure rate | 40% of completed screening
Sites planned / activated / enrolling | 260 / 231 / 214
Randomizations per enrolling site per month | 2.2

## 2 The Curve
Month | Plan | Actual | Delta | Cumulative | Note
Jul 2026 | 180 | 142 | -38 | 142 / 180 | Activation ramp — 96 sites live at month end
Aug 2026 | 420 | 361 | -59 | 503 / 600 | Ramp continues; 168 sites live
Sep 2026 | 640 | 598 | -42 | 1,101 / 1,240 | 214 sites enrolling
Oct 2026 (to 15th) | 520 | 583 | +63 | 1,684 / 1,760 | First month ahead of plan

## 3 Where the Randomizations Come
Tier | Criterion | Sites | % sites | Randomized | % rand. | Note
High performers | ≥12 randomized | 42 | 18% | 812 | 48% | 18% of activated sites delivering 48% of randomizations.
On plan | 6–11 randomized | 78 | 34% | 601 | 36% | Performing to the assumption the enrolment curve was built on.
Below plan | 1–5 randomized | 94 | 41% | 271 | 16% | 41% of sites delivering 16% of randomizations. The remediation population.
Activated, none randomized | 0 | 17 | 7% | 0 | — | Activated but not yet productive — 7% of activated sites, inside the published ~11% non-activation norm, but 17 sites of paid start-up returning nothing.
Total activated | — | 231 | 100% | 1,684 | 100%

## 4 Why Participants Fail Screeni
Reason | Count | Share | Assessment
Prior GLP-1 receptor agonist exposure within 90 days | 384 | 34% | The largest single cause, and a direct consequence of requiring a washout in a market where GLP-1 use is widespread. Shortening it risks carry-over on the primary endpoint.
HbA1c ≥6.5% or diagnosed diabetes | 297 | 26% | Non-negotiable. A weight-management indication cannot be confounded by glycemic effect.
BMI below threshold at screening visit | 168 | 15% | Largely a referral-quality problem — sites pre-screening on self-reported rather than measured BMI. Avoidable waste.
Body weight unstable in the prior 90 days | 121 | 11% | Design integrity: an unstable baseline makes the endpoint uninterpretable.
Other exclusion criteria | 94 | 8% | Pancreatitis history, MTC/MEN2 family history, recent bariatric surgery, cardiovascular event within 180 days.
Withdrew consent during screening | 78 | 7% | Participant choice. Monitored for clustering by site, which would indicate a consent process problem rather than ordinary attrition.
Total screen failures | 1,142 | 100%

## 5 Diagnosis
Possible cause | Evidence | Verdict
Not enough people being screened | 2,910 screened for 1,684 randomizations, with 84 in flight. Screening volume is adequate to the target. | not the constraint
Too many screen failures | 40% of completed screening, mid-range against a published 20–80% span. Three-quarters of failures are structural. | not the constraint
Not enough sites open and productive | 29 of 260 planned sites not activated; a further 17 activated but randomizing nobody; 94 below plan. | this is the constraint

## 6 Recovery Plan
Action | Owner | By | Rationale
Activate the 29 unstarted sites | Dr. R. Molyneux | Q4 2026 | Highest-yield lever available. Start-up cost is already partly sunk.
Remediate or replace the 17 zero-randomizing sites | Dr. R. Molyneux | Q1 2027 | Site visits to establish whether the constraint is referral flow, staffing, or pre-screening quality. Replacement only where it is not fixable.
Draw from the reserve site list | Meridian Clinical Research | Q1 2027 | 34 pre-qualified sites held in reserve at protocol finalization for exactly this.
Improve pre-screening quality | Meridian Clinical Research | Q4 2026 | 168 screen failures were BMI-below-threshold, measurable before a screening visit is booked. Pure waste and the cheapest thing on this list to fix.
Central pre-screening registry | Dr. R. Molyneux | Q1 2027 | Identifies washout candidates early so the 90-day GLP-1 clock starts before referral rather than at the screening visit.

## Forecast
Scenario | Implied rate | Last patient in | Assessment | Assumption
Current run-rate continues | 480 / month | Mar 2027 | on plan | Assumes no further site activation and no attrition in current performers.
Recovery plan delivers in full | 545 / month | Feb 2027 | ahead | 29 unstarted sites activated plus reserve draw.
Recovery plan delivers half | 510 / month | Mar 2027 | on plan | The planning case. Most recovery plans deliver partially.
No recovery, current sites only | 395 / month | Jun 2027 | at risk | Assumes below-plan sites do not improve. Last-patient-in slips a quarter, which moves database lock and the filing date.

## About
Enrolment & Site Dashboard
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Enrolment & Site Dashboard · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.