## 2 What a Condition Is and What
| Raised by | Owned by | Consequence of not closing
Gate condition | The Committee, at a gate | A named individual | A gate matter at the following gate. Blocks nothing immediately, but the Committee must address it before deciding again.
Action item | Any forum | Whoever accepted it | Chased operationally. No governance consequence.
Risk | Anyone, any time | A named owner in the RAID log | Monitored. May never materialize.
Must-meet criterion | Fixed when the gate was defined | The program | Blocks the gate outright. Cannot be converted into a condition.

## 2 Register
Ref | Condition | Owner | Issued | Due | Closed | Status
GC-01 | Complete analytical method re-qualification at Aldergate for all three methods | Dr. K. Oyelaran | 30 Jun 2026 | 18 Dec 2026 | — | open
GC-02 | Confirm the cardiovascular sub-study protocol with the DMC before first CV-cohort dosing | Dr. S. Aldridge | 30 Jun 2026 | 30 Nov 2026 | 25 Sep 2026 | closed
GC-03 | Stand up the payer evidence plan and hold the first advisory boards | J. Barrington | 30 Jun 2026 | 31 Mar 2027 | — | at-risk

## 3 Condition Records (1)
Field | Record
Issued | 30 June 2026 at Gate 4
Arises from | S1 — CMC readiness (scored 3)
Owner | Dr. K. Oyelaran
Due | 18 December 2026
Addresses | I-02; the CMC readiness score recorded at Gate 4
Status | open

## 3 Condition Records (2)
Date | Progress
15 Jul 2026 | CMC team embedded on site at Aldergate.
28 Aug 2026 | Method 2 re-qualification report signed.
30 Sep 2026 | Method 3 re-run against protocol acceptance criteria; results within specification, report in preparation.

## 3 Condition Records (3)
Field | Record
Issued | 30 June 2026 at Gate 4
Arises from | CR-02 scope addition
Owner | Dr. S. Aldridge
Due | 30 November 2026
Addresses | CR-02 scope addition
Status | closed

## 3 Condition Records (4)
Date | Progress
12 Aug 2026 | Sub-study protocol issued to the DMC.
25 Sep 2026 | DMC chair confirmation received. Condition closed.

## 3 Condition Records (5)
Field | Record
Issued | 30 June 2026 at Gate 4
Arises from | S2 — market access evidence (scored 3)
Owner | J. Barrington
Due | 31 March 2027
Addresses | R-06; the market access score recorded at Gate 4
Status | at-risk

## 3 Condition Records (6)
Date | Progress
30 Jul 2026 | Evidence plan approved by the Committee.
18 Sep 2026 | Two advisory boards held; minutes filed.
09 Oct 2026 | Two of five remaining boards still unscheduled against the due date. Escalated to the Committee; owner asked to present a recovery plan at the November checkpoint.

## 5 What Makes a Verification Met
Property | Adequate | Inadequate
Observable | “Minutes from at least three advisory boards demonstrating the boards were held” | “Payer engagement underway” — unobservable, and true of almost any state
Binary | “Signed qualification reports for all three methods” | “Substantial progress on method transfer” — who decides what is substantial?
Owned by evidence, not opinion | “Written confirmation from the DMC chair, dated before first dosing” | “The team is satisfied the protocol is acceptable”

## 7 When a Condition Cannot Be Cl
Situation | Route
The work is complete but the evidence differs from the recorded method | Committee decision, minuted. The Chair cannot accept substitute evidence.
The date will be missed but the work will complete | Owner presents a recovery plan at the next checkpoint. The due date is not silently moved.
The condition has become impossible or irrelevant | Committee may retire it, recording why. A retired condition stays in the register.
The condition will not close before the next gate | It becomes an input to that gate's assessment. An open condition does not automatically block a gate, but it is on the table.

## About
Gate Conditions Register
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Gate Conditions Register · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.