## 1 Tracker Not Gate
| This assessment | The gate decision
When | Continuously, from Gate 4 (Jun 2026) onward | Once, on 30 Sep 2028
Who | Program Director, against criteria fixed at Gate 4 | The Development Committee
Produces | A position, and an early warning where one is available | A decision, minuted, with conditions
Authority | None. It cannot pass or fail anything. | Releases the Stage 5 tranche and authorizes the submission
Value | ⚠ Entirely in removing surprise. A gate that surprises the Committee has been governed badly for the two years preceding it. | The decision itself

## 2 The Criteria
Ref | Domain | Criterion | Kind | Target at Gate 5 | Position at 15 Oct 2026 | Assessable?
G5-01 | Clinical | Both pivotal trials complete with database lock | Must | Locked, with the clinical study reports signed | Enrolment in progress | Not yet
G5-02 | Clinical | Primary endpoint meets the minimum acceptable threshold | Must | ≥10% mean weight reduction at week 68 | Blinded | Not yet
G5-03 | Clinical | Safety profile supports the sought label | Must | No unexpected serious risk; DMC has not recommended stopping | No DMC concern raised | Partly
G5-04 | CMC | Registration batches manufactured and released | Must | 3 of 3 | 2 of 3 | Assessable
G5-05 | CMC | Analytical methods transferred and re-qualified | Must | 3 of 3 | 2 of 3 | Assessable
G5-06 | CMC | Process validation (PPQ) complete | Must | 3 consecutive conforming batches | Scheduled Q1–Q2 2027 | Not yet
G5-07 | CMC | Stability data sufficient to support the proposed shelf life | Must | 24 months | 18 months elapsed | Partly
G5-08 | Regulatory | Submission content agreed with the agency | Must | Pre-NDA meeting held, minutes received | Scheduled Aug 2028 | Not yet
G5-09 | Regulatory | No major amendment outstanding | Must | Zero | Zero | Assessable
G5-10 | Quality | Inspection readiness at all named manufacturing sites | Should | Two internal audits closed | First audit scheduled 2027 | Not yet
G5-11 | Commercial | Market access evidence package complete | Should | Payer dossier and advisory board program complete | 2 of 5 boards unscheduled | Assessable
G5-12 | Program | Budget within authorized ceiling | Must | Within ceiling | Within ceiling | Assessable

## 3 The Column That Matters Asses
Assessability | Count | What it means
Assessable | 5 | A real position exists today. These are the only criteria where an early warning is possible, and all three current shortfalls are here.
Partly | 2 | Assessable in the negative, or accruing on a clock. Stability at 18 of 24 months is a real position; the absence of a DMC stop is real evidence.
Not yet | 5 | ⚠ Structurally unassessable. Not neglected — there is nothing to see.

## 4 What Each Assessment Rests On
Ref | What the assessment actually rests on
G5-01 | Cannot be assessed until the last participant completes. The only meaningful proxy is the enrolment curve, which is a schedule measure rather than a readiness one.
G5-02 | ⚠ Structurally unassessable before unblinding. Assessing it early would require breaking the blind, which would destroy the thing being assessed.
G5-03 | Assessable continuously in the negative — the absence of a DMC stop is real evidence, and it is the only safety evidence the sponsor is entitled to see.
G5-04 | Third batch is scheduled within thirty days. Assessable today, currently short, and the item every other CMC criterion waits on.
G5-05 | ⚠ Already failed once. The re-run of method 3 is the single most watched item in the CMC track.
G5-06 | Cannot start until registration batches exist, so its readiness is entirely a function of G5-04.
G5-07 | Accrues at one month per month and cannot be accelerated by any action. The only risk is an out-of-trend result, which would be visible when it happened.
G5-08 | The meeting is two years out. What is assessable now is whether the questions that will be asked at it are being accumulated.
G5-09 | Assessable continuously and currently met. Zero major amendments is a credit that belongs upstream, to the people who agreed the content early.
G5-10 | A should-meet: a shortfall here produces a condition rather than a stop.
G5-11 | ⚠ Gate condition GC-03 from Gate 4. Assessable today, and currently behind.
G5-12 | Assessable continuously. The forecast internal-labor overrun is absorbed within contingency, so the ceiling itself is not in question at this date.

## 5 What Happens If a Criterion I
Situation at the gate | Outcome available | Why
A must-meet is unsatisfied | RECYCLE — not a condition | ⚠ Must-meets are not outvotable and cannot be conditioned. An unsatisfied must-meet means the program returns to the stage and comes back; it does not proceed with a promise.
A should-meet is short | GO WITH CONDITIONS | A condition with a named owner, a due date, and a verification method fixed at issue. This is what happened at Gate 4 with market access evidence.
A criterion is still unassessable | Neither — the gate cannot be held | ⚠ If the database is not locked, there is no submission to authorize. The gate moves; it does not proceed on a forecast.
Everything is met | GO | Which, on the evidence of the four gates behind us, is the least likely outcome.

## 6 How This Is Maintained
Rule | Why
Updated monthly, tabled quarterly | Alongside the status report. A readiness tracker reviewed only near the gate is a retrospective document.
A criterion moves to assessable only when evidence exists | Not when somebody has an opinion about how it will turn out. The distinction between position and forecast is the whole value of the artifact.
Shortfalls are reported as shortfalls, not as plans | ⚠ “2 of 3, third scheduled” is a shortfall with a plan attached. “On track” is a plan presented as a position.
The criteria are never edited | If Gate 4's criteria turn out to be wrong, that is a matter for the Committee at the gate, recorded as such. It is not fixed by amending the tracker.

## About
Gate 5 Readiness Assessment
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Gate 5 Readiness Assessment · criteria fixed 30 June 2026, assessed 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.