## Regulatory 15 terms
Term | Definition
505(b)(1) | A full New Drug Application in which all safety and effectiveness data were generated by or for the sponsor.
BLA — Biologics License Application | The equivalent pathway for a biologic. Not used here — VTX-401 is a small molecule peptide filed as an NDA.
CDER — Center for Drug Evaluation and Research | The FDA center responsible for reviewing small-molecule drug applications, including this one.
eCTD — electronic Common Technical Document | The five-module structure every submission is assembled into.⚠ Module 2 holds the SUMMARIES and is written last, read first.
Expedited programs — Fast Track, Breakthrough, Accelerated Approval, Priority Review | Four distinct mechanisms for shortening development or review, each with its own eligibility test.⚠⚠ Not a menu to opt into. Each requires evidence the program may not have, and Accelerated Approval buys speed by taking on confirmatory obligations.
Filing date | 60 days after submission, when the agency accepts the application for review.⚠⚠ The PDUFA clock runs from the FILING date, not the submission date — 10 months for a standard NME review, so 12 from submission.
IND — Investigational New Drug application | The application that permits human dosing to begin.⚠ Not an approval. It is a 30-day non-objection; the agency permits rather than endorses.
iPSP — initial Pediatric Study Plan | The agreed plan discharging PREA obligations, usually with a post-approval deferral.
NME — New Molecular Entity | An active moiety never previously approved. Carries 5 years NCE exclusivity.
Orphan designation | A status for drugs treating rare conditions, carrying 7 years of market exclusivity.⚠ Not available here — chronic weight management is not a rare disease.
PAI — Pre-Approval Inspection | Inspection of the named manufacturing sites, conducted before approval is granted.
PDUFA date — Prescription Drug User Fee Act | The date by which the agency aims to complete its review. Also called the action date.⚠ A goal, not a statutory deadline — and it is met the overwhelming majority of the time, which is why programs plan against it.
PMR / PMC — Post-Marketing Requirement / Commitment | Studies after approval. A requirement is imposed; a commitment is agreed.⚠⚠ Not interchangeable. A missed PMR is a compliance matter; a missed PMC is a conversation.
Refuse-to-file | The agency declining to begin review because the dossier cannot be reviewed.⚠⚠ Does not restart the review clock — it REMOVES it. There is no clock until the application is accepted.
Type B meeting | The scheduled FDA meeting category covering pre-IND, end-of-phase and pre-NDA meetings.

## Clinical 17 terms
Term | Definition
ADaM — Analysis Data Model | Analysis-ready datasets derived from SDTM, with documented derivations.⚠ Exists so a reviewer can re-run the sponsor's analysis without the sponsor.
Blind data review | Review of the data before unblinding, where analysis populations are assigned.⚠⚠ The SEQUENCE is the control: populations assigned before unblinding, or the result becomes unfalsifiable.
CRO — Contract Research Organization | The vendor executing trial operations. Meridian, here.⚠ Accountability for conduct cannot be delegated with the work.
CSR — Clinical Study Report | The complete ICH E3 account of one trial.⚠ Reports the pre-specified analyses in the pre-specified order, whatever they show.
Database lock | The point at which the clinical database is frozen and no further data may be changed.⚠ Everything downstream — unblinding, analysis, the CSR, the submission — is gated by it, and it cannot be partially done.
DMC / IDMC — (Independent) Data Monitoring Committee | The independent body with unblinded safety oversight and stopping authority.⚠⚠ Deliberately unmanageable by the sponsor. It tells the sponsor almost nothing, because explaining a CONTINUE would partially unblind.
ICH E3 / E6 — International Council for Harmonisation | E3 is the CSR structure; E6 is Good Clinical Practice.
Informed consent | The documented process by which a participant agrees to take part, having understood the risks.⚠⚠ A PROCESS, not a form. The signature evidences a conversation, and an inspector interviews the coordinator about how it was obtained.
IRT / IWRS — Interactive Response Technology | The system that randomizes participants and releases investigational product to sites.
ISS / ISE — Integrated Summary of Safety / Efficacy | Submission-level analyses pooling participants across studies.⚠⚠ NEW ANALYSES, not compilations of the CSRs. Teams that treat them as assembly budget days for months of work.
Protocol deviation | Any departure from the protocol as approved, whether or not it affected a participant.⚠ Under-reporting them is a common and highly detectable finding — the monitoring reports in the TMF are reconciled against the CSR.
SAE — Serious Adverse Event | An event meeting regulatory seriousness criteria, with defined reporting clocks.⚠ 'Serious' is a regulatory classification, not a judgment about severity.
SAP — Statistical Analysis Plan | Fixes what will be analyzed and in what order. Signed before database lock.⚠⚠ The testing hierarchy set here decides what may ultimately be CLAIMED.
Screen failure | A participant who completes screening but is not randomized.⚠ Rate is expressed against completed screening, not against everyone approached.
SDTM — Study Data Tabulation Model | Raw study data restructured into the tabulation model regulators require for submission.
Testing hierarchy | The pre-specified order in which endpoints are tested.⚠⚠ Testing STOPS at the first failure. Everything below becomes descriptive, however favorable it looks.
TMF — Trial Master File | The record evidencing the trial was conducted properly.⚠ Measured against an expected-document list written BEFORE the documents exist.

## CMC Quality 8 terms
Term | Definition
CAPA — Corrective and Preventive Action | The formal, documented response to a quality deviation, covering both the fix and the prevention of recurrence.
CMC — Chemistry, Manufacturing and Controls | Everything about making the product to a consistent standard.⚠ Gates the filing independently of anything clinical.
Form 483 | The list of inspectional observations issued at the close of an FDA inspection.⚠ Observations, not findings. The response matters as much as the content.
GxP — Good [Clinical/Laboratory/Manufacturing] Practice | The frameworks of regulated practice governing how work is conducted and evidenced.⚠ A floor, not a quality target — compliance is the entry condition, not the achievement.
Method transfer | Moving a validated analytical method from one laboratory or site to another.⚠⚠ Routinely underestimated. A validated method carries undocumented practice, and moving it exposes what was never written down.
PPQ — Process Performance Qualification | The runs demonstrating the commercial process performs consistently.
Registration batch | A batch manufactured at commercial scale whose data supports the filing.
Stability | Data demonstrating the product remains within specification over time.⚠⚠ Accrues at one month per month. It is the one program input that cannot be accelerated by any amount of money or attention.

## Commercial 7 terms
Term | Definition
Copay assistance | Manufacturer-funded reduction of a patient's out-of-pocket cost.⚠⚠ Rises automatically when coverage is poor — so a weak access position makes each remaining unit more expensive to sell.
Formulary | A payer's list of covered drugs and the tiers determining what a patient pays.
Gross-to-net | The gap between list price and what the manufacturer actually receives.⚠⚠ Roughly a quarter of list here. The largest deduction is rebates, which buy formulary POSITION rather than volume.
PBM — Pharmacy Benefit Manager | The intermediary negotiating coverage on behalf of plans.⚠ Three national PBMs control most covered lives, and they run a procurement.
Prior authorization | A payer requirement that a prescriber justify the prescription before it is covered.⚠ The main route to access for a product not on formulary — real revenue, and nothing like formulary placement.
TPP — Target Product Profile | The labeling claims the product must achieve to be commercially viable.⚠ Written at Gate 0 and revised only by governance. It is the requirements baseline.
WAC — Wholesale Acquisition Cost | The published list price before any rebate or discount is applied.⚠ Almost nobody pays it; net is roughly three quarters of it.

## Program management 8 terms
Term | Definition
Contingency | Funding held against identified risks and drawn under a named authority.⚠ Not a slush fund and not the same as management reserve — every draw names the risk or change it funded.
Control account | The level at which cost and schedule are managed and a named owner is accountable.
CPI / SPI — Cost / Schedule Performance Index | Earned value ratios: below 1.0 is unfavorable.⚠ Computed here on the internal labor envelope only, not the whole program.
Gate | A decision point at which the next stage of work is authorized and funded, or is not.⚠⚠ Not a milestone and not a quality review. A decision that can only go one way is not a decision.
RACI — Responsible, Accountable, Consulted, Informed | The grid mapping each decision to the people who do it, own it, advise on it and hear about it.⚠ Exactly one Accountable per row. Two names in that column means nobody is.
RECYCLE | A gate outcome returning the work to the stage it came from to remedy a specific deficiency, then back to the same gate.⚠ Distinct from HOLD, which pauses without requiring anything to be fixed.
TCPI — To-Complete Performance Index | The cost efficiency required across remaining work to finish on budget.⚠ The watermelon defense: a program reporting green with TCPI well above 1.0 is forecasting a recovery nobody has planned.
Tranche | The portion of the authorized total released at a single gate, rather than up front.⚠⚠ The tranche is what makes a gate a decision rather than advice.

## About
Glossary
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Glossary · reference artifact. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.