## Slide 1
Phase 3 Mobilization
VitaFlow (VTX-401) — program kickoff for Stage 4
Vitalis Therapeutics Inc. · 30 June 2026 · Stage 4 of 5
Notes: Twenty minutes plus questions. Partners are in the room — introduce Meridian and Aldergate leads before slide 2.

## Slide 2
How to use this deck
Written for the whole program team and our partners — including people who will join after this meeting and read it cold.
This deck is the initiation record for Stage 4. It is being presented once, and it will then sit in the program library for the next twenty-seven months, which is why it is written in full sentences rather than in prompts for a speaker.
If you are joining the program later and have been pointed here to find out what we are doing: read slides 3 to 10. They explain what the drug is, what problem it treats, where it came from, and why the company decided to spend $243,040,000 finding out whether it works. Nothing in those slides is about your function specifically, and all of it is about why your function is being asked for anything at all.
If you are here to execute Stage 4, slides 11 to 20 are the plan: the timeline, the trials, who owns what, which organizations are doing the work, how we will run the cadence, and what we are asking of you.
One thing this deck deliberately does not contain is a status. It is dated 30 June 2026 and it says what was true and knowable then. Status lives in the monthly report and the dashboard, both of which will contradict parts of this deck within a year. That is expected and it is not a defect.
Presented live
Once, at mobilization, to the program team and partner leadership.
Watched afterwards
On the recording, by people who could not attend or who joined later.
Read cold, months later
From the program library, by someone with no context who needs it fast. This is the mode the deck is written for.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
1
Notes: Say plainly that this deck goes in the program library and will be read by people who are not here. That is why it is dense.

## Slide 3
Where this program sits
The molecule is 21.4 years old by the time its patent expires. This program owns 7.6 of those years.
DISCOVERY
THIS PROGRAM
LAUNCH AND LIFECYCLE
Patent filed
Nov 2019
Gate 0 — we begin
Mar 2022
Approval target
Oct 2029
Patent expiry
Nov 2039
2018 to 2039 — 21.4 years. This program owns 7.6 of them.
The single most useful thing to understand about a drug development program is that it begins in the middle of something longer. The molecule was discovered by people who are not on this program, using money that is not in this budget, and it will be sold for years after this program has been closed and its team dispersed.
The patent was filed in November 2019 and runs to 2039. That clock started 3.7 years before Gate 0 and it is the reason every schedule conversation in this program has an edge to it: each month spent in development is a month removed from the commercial life at the other end. We did not start the clock and we cannot stop it.
What this program is accountable for is the middle band — from a selected candidate to an approved product. We inherit a molecule and a clock, and we hand over a product and a set of post-marketing obligations.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
2
Notes: This is the slide people remember. Land the point that we inherit a clock we did not start.

## Slide 4
What VitaFlow is
The product, before anything about the plan to develop it
VitaFlow is a GLP-1 receptor agonist: a peptide that mimics a hormone the gut releases after eating. It slows gastric emptying, increases the sense of fullness, and reduces food intake. It is given as a once-weekly subcutaneous injection from a prefilled pen, which the patient administers themselves at home.
The mechanism is well understood and it is not ours. Several products in this class are already approved and widely used. VitaFlow is a new molecular entity — a molecule nobody has approved before — but it is not a new idea, and that distinction runs through every strategic decision in the program.
The dose is escalated gradually over the first several weeks rather than started at the maintenance level. That is not a convenience; it is the principal method of managing the gastrointestinal side effects that characterize this entire class, and the escalation schedule is one of the few product attributes we are still able to change.
MOLECULE
VTX-401, acylated peptide
MECHANISM
GLP-1 receptor agonist
PRESENTATION
Once-weekly subcutaneous prefilled pen
INDICATION SOUGHT
Chronic weight management, BMI ≥30 or ≥27 with a comorbidity
PATHWAY
505(b)(1) NDA — new molecular entity
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
3
Notes: Do not over-explain the mechanism to the clinical team. Aim this at the PMO, finance and the new joiners.

## Slide 5
The problem we are treating
Why an indication, not a molecule, decides a program
Roughly 41 million adults in the United States meet the clinical definition we are seeking to treat: obesity, or overweight with at least one weight-related comorbidity such as type 2 diabetes, hypertension or obstructive sleep apnea. It is a chronic condition, it is progressive, and lifestyle intervention alone produces durable results in a small minority of people.
That framing matters for how the program is designed, and it explains two things that surprise people arriving from other industries. The first is trial duration: our pivotal trials run 68 weeks, because a weight-management claim has to demonstrate that reduction is sustained rather than transient. A twelve-week study would show a result and prove nothing.
The second is that the commercial question is not whether the drug works. Products in this class demonstrably work. The question is whether ours works well enough, and is tolerated well enough, to displace an incumbent that a payer has already contracted for — and that is a question about the size of the effect and the proportion of patients who stop taking it, not about whether the mechanism is real.
Which is why the target product profile treats gastrointestinal discontinuation as a load-bearing attribute rather than a safety footnote. It is the number most likely to differentiate us, and the number most likely to undo us.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
4
Notes: The 68-week duration always draws a question. Answer it here rather than later.

## Slide 6
Before us: discovery
3.7 years of work happened before Gate 0. None of it is in this budget, and all of it constrains what we can now do.
RESEARCH-FUNDED DISCOVERY
Target rationale
Jun 2018
Lead series identified
Mar 2019
Composition-of-matter patent filed
Nov 2019
Lead optimization
Apr 2020
Candidate nomination
Feb 2021
Selection dossier assembled
Aug 2021
Jun 2018 to Mar 2022 — 3.7 years, none of it funded by this program.
Discovery is a research activity and it is deliberately outside this program's scope. The work breakdown structure says so explicitly: non-GLP exploratory pharmacology sits in research and is not funded here. We did not choose the target, run the screen, or optimize the lead.
What we inherit from that period is not a blank sheet. The half-life, the receptor selectivity, the synthesis route and the patent expiry were all fixed before anyone on this program was assigned to it. Several decisions that will feel like ours over the next two years were in fact made in 2020 and 2021, and understanding that is the difference between managing a constraint and arguing with one.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
5
Notes: Useful for anyone who thinks we chose the molecule. We did not.

## Slide 7
Why VTX-401 and not the other two
The candidate that won was neither the most potent nor the best tolerated
VTX-398
Not selected
3-day half-life
The most potent of the three. A three-day half-life means twice-weekly injection, against a class where once-weekly is the established standard. Potency does not compensate for a dosing schedule patients will not keep.
VTX-401
SELECTED
7-day half-life
Middle of the three on potency and on the rodent tolerability signal. Clean receptor selectivity, and — decisively — a six-step synthesis with no chiral separation, which meant it could be made at commercial scale on known equipment.
VTX-412
Not selected
6-day half-life
The best tolerability signal in rodents, and the one the pharmacologists wanted. An eleven-step route with a chiral center that would not have scaled without a new facility. The molecule was not the constraint; the process was.
The lesson worth carrying out of this slide is that manufacturability decided the candidate. VTX-412 had the better tolerability signal and the pharmacologists preferred it; an eleven-step synthesis with a chiral separation would have required a new facility and roughly two additional years before a registration batch existed. VTX-398 was more potent and would have needed twice-weekly dosing into a once-weekly market.
A program manager arriving at Gate 0 inherits that trade whether or not they agree with it — and it is the earliest example of a pattern this program will see repeatedly: the filing date is a manufacturing date as much as it is a data date.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
6
Notes: The manufacturability point is the one to dwell on — it foreshadows every CMC conversation for the next two years.

## Slide 8
What was promised at Gate 0
The target product profile is the contract with the business
Attribute | Target at Gate 0
Indication | Chronic weight management in adults with BMI ≥30, or ≥27 with at least one weight-related comorbidity
Mean weight reduction, 68 weeks | ≥15% from baseline
Responder rate (≥5% reduction) | ≥80% of participants
Dosing interval | Once weekly, maintenance reached within 16 weeks of escalation
GI-attributed discontinuation | ≤4% through 68 weeks
Cardiovascular safety | No increased risk demonstrated; MACE hazard ratio upper bound <1.4
Presentation | Single-use prefilled pen, no reconstitution, 28 days at room temperature
Shelf life | 24 months at 2–8°C plus 28 days in use at room temperature
The target product profile is the closest thing a development program has to a requirements document, and it behaves like one: it is agreed early, it is changed only with governance, and every subsequent decision is measured against it.
It is version 3.0 at this gate. Version 1.0 was set at candidate selection with a weight-reduction target of at least 12 percent. Version 2.0 raised that to 15 percent on the strength of the Phase 1 pharmacokinetics — raising a target mid-program is unusual, and it was done because the data supported a stronger claim than the profile was asking for.
Version 3.0 added a cardiovascular endpoint following the End-of-Phase-2 meeting with the agency, and relaxed exactly one target: the dose-escalation interval moved from sixteen weeks to twenty. That is the only concession made in four years, and it was traded deliberately for tolerability.
Everything in the left-hand column is something we have committed to demonstrate. Nothing in it is aspirational.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
7
Notes: If asked why the escalation interval was relaxed: traded deliberately for tolerability, and it is the only concession in four years.

## Slide 9
The market we are entering
Fourth into a class where the first two hold the formulary
Two established once-weekly GLP-1 agonists
Approved, entrenched, and holding preferred formulary position with the major pharmacy benefit managers. Neither is displaced by a fourth entrant on efficacy alone.
One competitor in registrational trials
Expected to file roughly eighteen months ahead of VitaFlow, which is what makes the differentiation question urgent rather than theoretical.
A crowded, well-characterized class
⚠ Simultaneously a commercial weakness and a regulatory asset. The mechanism is understood, the endpoints are agreed, and the review division has seen this dossier shape before — which is why the pathway is predictable and the market is not.
Being fourth into a well-characterized class is a commercial weakness and a regulatory asset, and both halves of that sentence are the same fact. The review division has seen this dossier shape before, the endpoints are agreed, and the pathway is unusually predictable — which is precisely why the market is not.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
8
Notes: Do not let this become a discussion about whether we should have started. That decision is four years old.

## Slide 10
The business case, and why it is odd
The expected value at Gate 0 was less than the cost of finding out
$243,040,000
Authorized cost of finding out
$1,362,000,000
Net present value if it is approved
$96,025,247
Expected value at Gate 0, risk-adjusted
The third number is the one worth pausing on, because at Gate 0 the risk-adjusted expected value of this program was $96,025,247 against an authorized cost of $243,040,000. The expected value was less than the cost of finding out.
Read as a conventional investment appraisal, that says do not proceed. Read correctly, it says something different: the company is not buying a product at Gate 0, it is buying the option to keep going. The probability of technical and regulatory success at candidate selection was about seven percent, and seven percent of a large number is a small number.
This is the whole logic of stage-gate funding. Money is released one stage at a time against evidence, so that the $125,800,000 being committed today is authorized by a Committee that has seen Phase 2 results — evidence that did not exist when the program started. By this gate the risk-adjusted value has risen to $681,030,120, not because the drug got better, but because two of the three ways it could have failed are now behind us.
Funding follows the information rather than preceding it. If you remember one thing about how this program is financed, remember that.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
9
Notes: The expected-value-below-cost point is counterintuitive and worth the extra minute. It explains why funding arrives in tranches.

## Slide 11
The program, gate to gate
Gate 0 to launch: 7.6 years, $243,040,000, six gates.
STAGE 1
STAGE 2
STAGE 3
STAGE 4
STAGE 5
G0
Mar 2022
G1
Dec 2022
G2
Jun 2023
G3
May 2024
G4
Jun 2026
G5
Sep 2028
G6
Oct 2029
Mar 2022 to Nov 2029. Four gates behind us, three ahead.
Each gate is a decision point with the authority to stop the program, and each releases a tranche of money against evidence rather than against a plan. The stages between them are not equal: Stage 4, which starts today, is 58 percent of the budget and about a third of the calendar.
The shape is deliberate. Early stages are cheap and fast because their job is to kill the program economically if it is going to fail. By the time a program reaches Phase 3 it has survived the two most likely failure modes, and the spend rises accordingly — which is also why the governance tightens rather than relaxes.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
10
Notes: Point out that Stage 4 is 58% of the budget. It sets up the next slide.

## Slide 12
What the four gates behind us decided
Each one released money against evidence, and could have stopped the program
Gate 0
Mar 2022
Candidate Selection. VTX-401 chosen over two alternatives; program chartered and Stage 1 funded.
Gate 1
Dec 2022
IND-Enabling Readiness. GLP toxicology complete and the nonclinical package judged sufficient to support dosing humans.
Gate 2
Jun 2023
IND Submission. A gate that releases no money — it authorizes the filing, and the agency's silence for thirty days is what permits Phase 1 to begin.
Gate 3
May 2024
Phase 2 Readiness. Phase 1 dose selection accepted; the dose-ranging study authorized.
Gate 4
Jun 2026
TODAY. Phase 3 Initiation — go with conditions, 5-0-1. The largest single commitment in the program.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
11
Notes: Keep this fast. It is reference material for the read-later audience.

## Slide 13
Where we are today
Gate 4 carried with conditions on 30 June 2026. One abstention, recorded.
$125,800,000
Released today for Stage 4
2,480
Participants to randomize
260
Investigational sites
68 wks
Treatment per participant
Gate 4 carried five to nil with one abstention. The Chief Financial Officer abstained rather than voting against, on the grounds that the gross-to-net assumption underpinning the commercial case had not been refreshed since it was built. That abstention is on the record, it is not a procedural footnote, and one of the three conditions attached to this gate exists because of it.
Three conditions were issued. CMC readiness must reach a defined standard before Gate 5; the cardiovascular sub-study protocol must be issued to the Data Monitoring Committee; and a market access evidence plan must be approved and executed. Each has a named owner, a due date, and a verification method that was fixed when the condition was issued and cannot be renegotiated by the person who has to satisfy it.
We also enter Stage 4 carrying one open issue from Stage 3: the analytical method transfer to our contract manufacturer failed its acceptance criteria on first pass in March. Two of three methods have since been re-qualified. It is being managed, it has drawn contingency, and it is the reason CMC readiness is a gate condition rather than an assumption.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
12
Notes: Be straight about the abstention and the open method-transfer issue. Hiding either at kickoff costs credibility later.

## Slide 14
Stage 4 — what this team executes
27 months, $125,800,000, and the work that determines whether there is a submission.
Phase 3 startup & site
Nov 26
Phase 3 enrolment
Sep 27
Phase 3 treatment & fo
Jul 28
Registration batches
Aug 26
Process validation & P
Dec 27
SAP development to approva
Jul 28
Database lock & unblin
Aug 28
Jul 2026 to Sep 2028 — 27 months and $125,800,000, the largest single commitment in the program.
Stage 4 has three tracks running in parallel and they are gated by different things. The clinical track is paced by participants: sites have to be activated, participants randomized, and then 68 weeks of treatment have to elapse for the last one. No amount of resourcing shortens that.
The CMC track is paced by the calendar in a different way — stability data accrues at one month per month, and process validation cannot begin until registration batches exist. It gates the filing independently of anything the clinical track does, which is a point worth internalizing early: a filing date is a manufacturing date as much as it is a data date.
The regulatory track is mostly assembly, and it is the one that can absorb pressure — up to a point. The submission cannot be written before the data exists, and the statistical analysis plan has to be signed before the database is locked, which is a sequence we do not compress under any circumstances.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
13
Notes: The three-tracks framing is the most useful thing on this slide.

## Slide 15
What we are building
Two pivotal trials and a sub-study, and the evidence they produce
Pivotal 301
1,360 participants · 68 weeks
The primary efficacy and safety trial. Co-primary endpoints: mean percentage weight reduction, and the proportion of participants achieving at least five percent reduction.
Pivotal 302
1,120 participants · 68 weeks
The confirmatory trial. Two adequate and well-controlled trials are the conventional evidentiary standard for a new molecular entity in this indication.
CV sub-study
640 participants · nested
Added by change request CR-02 in April, before this gate. It pre-empts a post-marketing requirement the agency would otherwise be likely to impose, and it is held as a discrete work package so its cost stays visible.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
14
Notes: Expect a question on why 640 for the sub-study. Answer: it pre-empts a post-marketing requirement.

## Slide 16
Who owns what
102 people across 10 working functions, plus a 7-seat Development Committee that carries no deliverable.
Function | People | Owns
Clinical Operations | 24 | Sites, monitoring, enrolment, clinical supply
Technical Operations / CMC | 16 | Process, analytical methods, scale-up, validation
Clinical Development | 12 | Protocols, medical monitoring, clinical study reports
Biostatistics & Data Management | 12 | SAP, EDC, database lock, analysis datasets
Regulatory Affairs | 10 | Strategy, submissions, agency interaction, labeling
Pharmacovigilance & Drug Safety | 8 | Case processing, signal detection, DSUR
Quality Assurance (GxP) | 7 | Audits, CAPA, GxP compliance, inspection readiness
Nonclinical Safety & Pharmacology | 5 | Toxicology, pharmacology, study oversight
Program Management Office | 4 | Governance, planning, risk, reporting
Market Access & Commercial | 4 | Payer evidence, pricing, launch readiness
Function heads own who does the work and how it is done. The program owns what is produced and when. That split is not a compromise — it is the design, and the friction it creates is how a resourcing gap becomes a visible negotiation between two accountable people rather than a quiet slip.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
15
Notes: Name the control account owners in the room.

## Slide 17
The organizations doing most of the work
83% of this program is delivered by organizations that do not report to it.
Meridian Clinical Research
CRO · $93.9M
Runs the pivotal trials: site management, monitoring, data capture. The single largest contract in the program.
Aldergate Biologics
Contract manufacturer
Drug substance and drug product. Single-source for the life of the program — a risk we carry and have named rather than mitigated.
Kestrel Laboratories
Central laboratory
All bioanalytical and safety laboratory work, so that results are comparable across 260 sites.
Thorne & Vale LLP
Regulatory counsel
Submission strategy and agency correspondence review.
The obligations we transfer to Meridian are listed in writing, and the regulation that governs this is unambiguous: any obligation not covered by the written description is deemed not to have been transferred. Silence means we kept it.
That has a practical consequence for everyone in this room. Execution can be contracted; the obligation cannot. If a site is monitored badly, the sponsor is answerable at inspection, and 'our CRO told us it was fine' is not an answer. Our 17% of the budget buys the capability to direct and verify the other 83% — that is what our jobs are.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
16
Notes: The 21 CFR 312.52 point matters. Say it in plain words.

## Slide 18
How we will run this
Cadence, escalation, and the two rules that are not negotiable
Development Committee
Meets at gates and quarterly. Releases money, issues and closes conditions, decides scope.
Monthly status report
Written, to the Committee. RAG against a rule fixed at this gate, and a decisions-requested section.
Dashboard
Continuous leading indicators. Site activation cycle time is the one to watch first.
Escalation
Anything that cannot wait for the monthly report should not be in the monthly report.
Change control
Scope, milestone dates and anything touching the submission are Committee matters at any size.
Data Monitoring Committee
Independent, reports to nobody in this room, and can stop the trial. Safety is outside the Committee's authority.
Two rules are not negotiable and it is worth stating them at kickoff rather than discovering them under pressure. Compliance is never a trade against schedule. And the statistical analysis plan is signed before the database is locked, which is signed before anyone is unblinded — reverse any two of those and the trial result becomes unfalsifiable.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
17
Notes: The two non-negotiables should be said slowly.

## Slide 19
What could go wrong
Named now, at mobilization, while there is still time to act on them
Site activation running long
The plan assumes 18 weeks from selection to green light. It is the assumption most likely to be wrong, and it sits upstream of everything.
CMC readiness for Gate 5
One method transfer has already failed once. Registration batches, stability and process validation all have to land before the filing.
Gross-to-net assumption
Un-refreshed since the original case, and the subject of a recorded abstention at this gate. Gate condition GC-03 addresses it.
Tolerability differentiation
Phase 2 showed 5.1% GI discontinuation against a 4% target. Within the minimum acceptable band, but not yet a differentiating claim.
Single-source manufacture
Accepted deliberately. A second site does not fit the ceiling, so the risk is carried and named rather than mitigated.
VitaFlow · Phase 3 Mobilization Kickoff · 30 June 2026
18
Notes: Naming risks at kickoff is not pessimism. Say so if the room goes quiet.

## Slide 20
What we need from you
Tell us early
A problem raised in week two is a schedule conversation. The same problem raised in month four is a re-baseline.
Hold the definitions
A site is not activated until green light. A query is not closed until the data changes. These are fixed today so they cannot be softened later.
Own your control account
Every work package has one named person who can answer for it without checking. If that is you, it is genuinely you.
Read the profile
The target product profile is on slide 8. Every decision we make for the next two years is measured against it.
We are not being asked whether this drug works — Phase 2 answered that. We are being asked whether it works well enough, in enough people, with a tolerability profile a payer will pay for. That is the question Stage 4 exists to answer.
Notes: End on the question Stage 4 exists to answer, not on the asks.