## 1 Everything Here Was Committed
Value
Committed before approval exists | $16,900,000
Workstreams carrying pre-approval commitment | 6
Longest lead time | 9 months — commercial supply build
Approval to launch | 0.9 months
Largest single exposure | $6,400,000 — commercial supply build

## 2 What Is At Risk and What Kind
Workstream | Owner | Lead time | Committed at risk | Share | What the risk actually is
Commercial supply build | Dr. K. Oyelaran | 9 mo | $6,400,000 | 38% | ⚠ Launch quantity manufactured and released before approval. Product has a shelf life; an approval delay of more than a few months converts inventory into a write-off.
Field force hire and train | J. Barrington | 6 mo | $4,100,000 | 24% | Representatives hired, onboarded and trained. ⚠ Trained on the SOUGHT label, then retrained on the approved one — the second training is the unavoidable cost of the first.
Medical affairs field team | Dr. A. Okoye | 7 mo | $2,300,000 | 14% | Medical science liaisons deployed ahead of launch to respond to unsolicited requests. Recoverable — the capability transfers to any launch.
Promotional material development | J. Barrington | 4 mo | $1,800,000 | 11% | ⚠ Built against the label sought. Anything resting on a claim not granted is destroyed and rebuilt — the single most predictable write-off in a launch.
Patient support program | J. Barrington | 6 mo | $1,400,000 | 8% | Copay assistance infrastructure, adherence support, hub services. Vendor contracted with activation on approval.
Distribution network setup | G. Petrossian | 5 mo | $900,000 | 5% | Wholesaler agreements, specialty pharmacy onboarding, cold-chain qualification at depots. Largely recoverable if launch slips; contracts are dated, not consumed.
Total committed before approval |  |  | $16,900,000 | 100%

## 3 The Decisions and the One Tha
Decision | Status | Reasoning
Build commercial supply before approval | Committed | Not building means a launch delayed by the manufacturing lead time — roughly nine months of a patent life that expires on a fixed date. ⚠ The write-off risk is the smaller of the two numbers.
Train the field force on the sought label | Committed | The alternative is a field force that cannot be deployed for six weeks after approval. Retraining is cheaper than absence.
Build promotional material on the sought claim | ⚠ Partially reversed | ⚠⚠ Reversed in Q1 2029 once the topline made the comparative claim unlikely. Material was rebuilt against the label likely to be granted rather than the one sought — a decision that cost rework and saved more.
Hold pricing until the label is granted | Committed | Price cannot be set against a claim that may not exist. ⚠ It delays payer conversations into a window that was already too narrow.

## 4 Readiness by Workstream
Workstream | Position at assessment | Confidence
Supply and distribution | Launch quantity manufactured, released against qualified methods, positioned at wholesaler depots under validated cold chain. Twelve months of capacity reserved. | Ready
Field force | Hired, onboarded, trained on the sought label. Retraining on the approved label scheduled for the week following the action date. | Ready
Medical affairs | Field team deployed. Unsolicited-request process operating — ⚠ the only route by which off-label information may lawfully be provided, and it must be genuinely reactive. | Ready
Pharmacovigilance | Post-marketing safety system built and operational. ⚠ Not the IND system carried over — marketed-product reporting has different obligations and a different clock. | Ready
Patient support | Hub services and copay infrastructure contracted, activating on approval. | Ready
Payer coverage | ⚠⚠ The formulary cycle for the 2030 plan year closed before approval. Launch proceeds into exception-based access rather than formulary placement. | Not ready

## 5 The Limits of Being Ready
Ready | Still cannot | Why
Supply in the network on day one | Make a plan cover the product | Inventory positioned at a wholesaler is available to be dispensed. It is not available to be reimbursed.
A trained field force | Discuss anything outside the approved label | ⚠ Promotion is bounded by the label. A representative may not raise a comparison the label does not carry, however true the underlying data.
Medical science liaisons in the field | Proactively fill the gap | ⚠⚠ Medical affairs may respond to unsolicited requests. It may not be used as a route to communicate what the sales force is not permitted to say — the distinction is real, it is inspected, and blurring it is a serious matter.
Copay assistance infrastructure | Substitute for coverage | It reduces patient out-of-pocket on a non-preferred tier at the manufacturer's expense. It buys persistence, not access, and it makes each unit less profitable.

## 6 What This Assessment Would Ha
At Gate 5, Sep 2028 | Actionable then?
Payer coverage will not be ready, because the 2030 formulary cycle closes before approval | ⚠ No. The dates were fixed. Knowable, not changeable.
Promotional material built on the comparative claim is likely to be written off | Yes — and it was acted on, in Q1 2029, once the topline was available.
Supply must be built nine months before an approval nobody can guarantee | Yes, and the decision to accept the exposure should be minuted rather than absorbed into a launch budget.
Pricing cannot be set until the label is granted, compressing payer engagement | ⚠ Partially. Engagement on everything except price could have started earlier, and the advisory board program was already behind.

## About
Launch Readiness Assessment
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Launch Readiness Assessment · assessed 15 September 2029, ahead of the 05 October 2029 action date. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.