## 1 What a Milestone Is
Rule | Why it holds
A milestone is binary | Ninety per cent complete is zero per cent complete. Partial credit is what turns a schedule into a narrative, and it is the mechanism by which a program reports green for eighteen months and then slips six.
It has one named owner | Not a function — a person. A milestone owned by “Clinical Operations” is owned by nobody at the moment it is missed.
Its evidence standard is fixed when the milestone is DEFINED | Not when it is claimed. The same discipline the Committee applies to gate conditions, for the same reason: the party who wants the milestone closed should never also be the party who decides what closing it requires.
It is dated from the schedule, not typed in | Every date in the register below is read from the integrated schedule. The two documents cannot disagree, because there is only one set of dates.
A deliverable is a thing; a milestone is a moment | The Statistical Analysis Plan is a deliverable. “SAP approved” is a milestone. Programs that conflate the two end up tracking documents that exist in draft forever.

## 2 The Register
Ref | Date | Milestone | Owner | Type | Evidence standard | At 15 Oct 2026
M-01 | 31 Dec 2022 | Gate 1 — IND-Enabling Readiness | C. Tyrrell | Internal | Minuted Committee decision with the scored criteria attached | Met
M-02 | 30 Jun 2023 | IND submitted | Dr. P. Raghunathan | Regulatory | Agency acknowledgment of receipt with an IND number assigned | Met
M-03 | 30 Jul 2023 | IND in effect | Dr. P. Raghunathan | Statutory | Day 30 elapsed with no clinical hold communicated — silence IS the evidence | Met
M-04 | 30 Sep 2023 | Phase 1 first participant dosed | Dr. R. Molyneux | Internal | First dose recorded in the EDC against a signed consent | Met
M-05 | 13 Apr 2024 | Phase 1 topline & dose selection | Dr. S. Aldridge | Internal | Topline tables reviewed and the dose recommendation signed by the CMO | Met
M-06 | 22 Apr 2024 | End-of-Phase-1 meeting held | Dr. P. Raghunathan | Regulatory | FDA official minutes received — not the sponsor's notes | Met
M-07 | 31 May 2024 | Gate 3 — Phase 2 Readiness | C. Tyrrell | Internal | Minuted Committee decision; Stage 3 tranche released | Met
M-08 | 31 Aug 2024 | Phase 2 first participant randomized | Dr. R. Molyneux | Internal | IRT randomization record against a signed, dated consent form | Met
M-09 | 31 Dec 2024 | Phase 2 last participant randomized | Dr. R. Molyneux | Contractual | IRT record; triggers a CRO milestone payment | Met
M-10 | 24 Oct 2025 | Phase 2 database lock | Dr. F. Achterberg | Internal | Lock certificate countersigned by data management and the study statistician | Met
M-11 | 09 Dec 2025 | Phase 2 dose selection confirmed | Dr. S. Aldridge | Internal | Dose rationale memo accepted by the Committee as Gate 4 evidence | Met
M-12 | 09 Jan 2026 | EOP2 briefing package submitted | Dr. P. Raghunathan | Regulatory | Agency acknowledgment; the 30-day clock before the meeting starts here | Met
M-13 | 19 May 2026 | End-of-Phase-2 meeting held | Dr. P. Raghunathan | Regulatory | FDA official minutes; agreed iPSP due within 60 days | Met
M-14 | 30 Jun 2026 | Gate 4 — Phase 3 Initiation | C. Tyrrell | Internal | Minuted decision, conditions recorded with verification methods fixed at issue | Met
M-15 | 30 Jun 2026 | Phase 3 first site activated | Dr. R. Molyneux | Internal | Green-light letter issued — contract executed, IRB approved, site trained | Met
M-16 | 30 Aug 2026 | Registration batches released | Dr. K. Oyelaran | Internal | Three batch records reviewed and dispositioned by Quality Assurance | Met
M-17 | 30 Sep 2027 | Phase 3 last participant randomized | Dr. R. Molyneux | Contractual | IRT record; largest single CRO milestone payment in the program | —
M-18 | 30 Dec 2027 | Process validation complete | Dr. K. Oyelaran | Internal | PPQ report approved; variability within the Stage 1 prediction | —
M-19 | 30 Jul 2028 | Statistical analysis plan approved | Dr. F. Achterberg | Internal | Signed SAP, dated BEFORE the lock certificate | —
M-20 | 05 Aug 2028 | Pivotal database lock | Dr. F. Achterberg | Internal | Lock certificate; unblinding authorization issued only after it | —
M-21 | 10 Aug 2028 | Pre-NDA meeting held | Dr. P. Raghunathan | Regulatory | FDA official minutes; content and format agreed | —
M-22 | 30 Sep 2028 | Gate 5 — NDA Submission | C. Tyrrell | Internal | Minuted decision; Stage 5 tranche released | —
M-23 | 12 Oct 2028 | NDA submitted | Dr. P. Raghunathan | Regulatory | Submission receipt from the electronic gateway | —
M-24 | 11 Dec 2028 | Filing acceptance | Dr. P. Raghunathan | Statutory | Day-74 letter confirming filing and the review clock | —
M-25 | 12 Jun 2029 | Pre-approval inspection closed | Dr. I. Solberg | Regulatory | Inspection closeout; any Form 483 observation responded to within 15 working days | —
M-26 | 11 Oct 2029 | Action date | FDA | Statutory | The agency's action — nothing the sponsor produces is evidence of this | —
M-27 | 11 Oct 2029 | Gate 6 — Approval & Launch | C. Tyrrell | Internal | Minuted decision taken on approval as an INPUT, not a forecast | —
M-28 | 01 Nov 2029 | First commercial shipment | L. Whitcombe | Contractual | Shipment confirmation against a released, serialized lot | —

## 3 Four Kinds of Milestone and W
Type | Count | Share | What it means for the program
Internal | 15 | 54% | The program can move it. It still costs credibility.
Contractual | 3 | 11% | Moving it costs money — it triggers a payment or a change order.
Regulatory | 7 | 25% | The agency controls the date or the acceptance. The sponsor controls only readiness.
Statutory | 3 | 11% | Arithmetic performed by somebody else. Not movable by anyone in this program.

## 4 The Evidence Standard
Pattern | Example | The reasoning
The evidence is external to the program | “FDA official minutes received — not the sponsor's notes” (M-06, M-13, M-21) | The sponsor's record of a meeting is a recollection. The agency's minutes are the record, they arrive within thirty days, and where the two differ the sponsor's is not the one that counts.
The evidence is an absence | “Day 30 elapsed with no clinical hold communicated” (M-03) | An IND is an exemption, not a permission. Nobody sends a letter saying it worked. Silence is the evidence, which is a genuinely uncomfortable thing to record as a milestone and is exactly why it should be recorded as one.
The evidence is a countersignature | “Lock certificate countersigned by data management and the study statistician” (M-10, M-20) | Two functions with different incentives both have to be willing to sign. A single signature on a database lock is a control that has been designed to be passable.

## 5 Position at the Status Date
Position
Milestones met | 16 of 28
Next milestone due | Phase 3 last participant randomized — 30 Sep 2027, Dr. R. Molyneux
Milestone most at risk | M-17 Phase 3 last participant randomized — 76 participants behind curve, and treatment duration is fixed at 68 weeks after it
Milestones the program could move if it had to | 15

## 6 The One Ordering That Is Not
Ref | Milestone | Date
M-19 | Statistical analysis plan approved | 30 Jul 2028
M-20 | Pivotal database lock | 05 Aug 2028

## About
Milestone & Deliverable Plan
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Milestone & Deliverable Plan · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.