## 1 An NDA Is Not a Document
Position at 15 October 2026
Target submission | 12 October 2028 — 24 months away
Weighted content in hand | 46%
Most advanced module | Module 4 — nonclinical, 95%, finished since Gate 2
Least advanced module | Module 2 — the summaries, 10%, and correctly so
The module carrying the most risk | Module 3 — CMC, 62%, gated by validation and stability

## 2 The Five Modules
| Title | Owner | Content in hand | Gated by | Note
Module 1 | Administrative and Prescribing Information | Dr. P. Raghunathan | ████░░░░░░ 35% | Labeling negotiation, which follows the data | Forms, patent and exclusivity statements, proposed labeling, REMS assessment. ⚠ Mostly assembly, and the one section here that is NOT assembly is the proposed label.
Module 2 | Common Technical Document Summaries | Dr. P. Raghunathan | █░░░░░░░░░ 10% | Every other module — it summarizes them | ⚠⚠ Written LAST and read FIRST. The Clinical Overview (2.5) is roughly 30 pages and is the part of the dossier most likely to be read in full by a reviewer.
Module 3 | Quality — CMC | Dr. K. Oyelaran | ██████░░░░ 62% | Process validation and 24-month stability | ⚠ The module that gates the filing independently of anything clinical. Furthest advanced and carrying the most named risk.
Module 4 | Nonclinical Study Reports | Dr. M. Sørensen | ██████████ 95% | Nothing — the studies are complete | Effectively finished since Gate 2. Reports exist, are signed, and need only to be formatted into the dossier.
Module 5 | Clinical Study Reports | Dr. S. Aldridge | ███░░░░░░░ 28% | Database lock, then 12 weeks to final CSRs | Phase 1 and Phase 2 reports are final. The two pivotal reports and the integrated summaries do not exist and cannot before lock.

## 3 The Sequence That Cannot Be C
Step | What it produces | When
Database lock | Pivotal data frozen | Jul 2028
Unblinding | Only after lock and a signed SAP | Jul 2028
Topline results | First view of whether the claims are supportable | Jul 2028
Clinical study reports | 12 weeks from lock | Sep 2028
Integrated summaries | New analyses, produced in parallel with the CSRs | Sep 2028
Module 2 summaries | Written last, from everything above | Sep 2028
Gate 5 | Committee authorizes submission | Sep 2028
Submission | eCTD to the electronic gateway | Oct 2028

## 4 RefusetoFile
Ground for refuse-to-file | What it means | Position
Incomplete on its face | Required content missing from a module | The most common and the most preventable. A completeness review against the guidance checklist catches it.
No agreed pediatric study plan | PREA requirement unmet | ⚠ Agreed iPSP is in place from the End-of-Phase-2 meeting. This one is closed.
Studies not adequate and well-controlled | Design or conduct inadequate on its face | Judged from the protocol and the CSR, not from the result. Two adequate pivotals is the conventional standard and this program has them.
Data not submitted in the required format | SDTM/ADaM non-conformance | ⚠ Mechanical, and entirely avoidable. Conformance is checked before submission with the same validator the agency uses.
Unsigned or unauthorized | Administrative failure | Rare, humiliating, and the reason the submission checklist has a signature block.

## 5 Data Format Conformance
Requirement | What it involves | When it is checked
SDTM conformance | Study data tabulation model, to the required version | ⚠ Continuously during the study, not at the end. A conformance problem discovered after lock is expensive to fix and cannot be fixed by re-collecting.
ADaM conformance | Analysis datasets traceable back to SDTM | As the analysis programs are written, against the SAP.
define.xml | The machine-readable metadata that makes the datasets interpretable | ⚠ Not documentation about the datasets — it is how they are read. A dataset without it is a large amount of data nobody can use.
Validator run | The same conformance tool the agency uses, run before submission | Every issue it reports is either fixed or explained in a reviewer's guide. An unexplained conformance error invites the question of what else was not checked.

## 6 What This Assessment Is For
This assessment | gate5-readiness
Tracks the dossier — can the submission be assembled | Tracks the gate criteria — may the Committee authorize it
Owned by Regulatory Affairs | Owned by the Program Director
Answers: what is missing, and what is it waiting on | Answers: is the program permitted to proceed
A module at 28% is expected and fine | ⚠ A must-meet criterion unsatisfied produces RECYCLE
Updated continuously as content is produced | Updated monthly, tabled at the gate

## About
NDA Readiness Assessment
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · NDA Readiness Assessment · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.