## 1 Scope of the Baseline
| In this baseline | Not in this baseline
Scope | Internal labor: $36,008,000, 16.6% of base | External: $180,992,000, 83.4% of base
What drives the cost | Hours worked, which correlate with effort | Participants dosed, sites activated, batches made — which do not
Who controls it | The Program Director, through the functions | Contracts, protocols and the pace of 260 independent institutions
Better measured by | This document | Enrolment dashboard and the tranche release mechanism

## 2 Position at the Status Date
Measure | Value | Reading
BAC — budget at completion | $36,008,000 | The internal labor envelope for the whole program
PV — planned value | $15,886,000 | 44.1% of the envelope should have been consumed by now
EV — earned value | $15,487,000 | 43.0% of the envelope's work has actually been done
AC — actual cost | $16,500,000 | What has actually been spent on it
SV — schedule variance | $-399,000 | Work worth this much has not happened when it was planned to
CV — cost variance | $-1,013,000 | The work that HAS been done cost this much more than it was budgeted to
SPI | 0.975 | Slightly behind plan — but read §4 before trusting this number
CPI | 0.939 | Every dollar spent has bought 0.94 dollars of budgeted work

## 3 By Function
Function | PV | EV | AC | SV | CV | CPI
Clinical Operations | $3,318,000 | $3,120,000 | $3,290,000 | $-198,000 | $-170,000 | 0.95
Technical Operations / CMC | $2,867,000 | $2,810,000 | $3,480,000 | $-57,000 | $-670,000 | 0.81
Regulatory Affairs | $1,866,000 | $1,880,000 | $1,845,000 | $14,000 | $35,000 | 1.02
Clinical Development | $1,642,000 | $1,610,000 | $1,660,000 | $-32,000 | $-50,000 | 0.97
Nonclinical Safety & Pharmacology | $1,611,000 | $1,611,000 | $1,585,000 | $0 | $26,000 | 1.02
Biostatistics & Data Management | $1,510,000 | $1,455,000 | $1,520,000 | $-55,000 | $-65,000 | 0.96
Quality Assurance (GxP) | $1,030,000 | $1,015,000 | $1,105,000 | $-15,000 | $-90,000 | 0.92
Pharmacovigilance & Drug Safety | $968,000 | $975,000 | $960,000 | $7,000 | $15,000 | 1.02
Program Management Office | $677,000 | $660,000 | $700,000 | $-17,000 | $-40,000 | 0.94
Development Committee (oversight only) | $211,000 | $211,000 | $205,000 | $0 | $6,000 | 1.03
Market Access & Commercial | $186,000 | $140,000 | $150,000 | $-46,000 | $-10,000 | 0.93
Total | $15,886,000 | $15,487,000 | $16,500,000 | $-399,000 | $-1,013,000 | 0.94

## 4 Why SPI Is the Weakest Number
Why SPI understates it | The mechanism
SPI is denominated in dollars, not time | A schedule variance of $399,000 says that work worth that much has not happened yet. It does not say how late anything is. Two months of slip on a cheap activity and two weeks on an expensive one produce the same number.
It only sees the 16.6% | Enrolment is external. The sponsor's own monitoring and data management effort continues at close to plan whether participants are randomized on curve or not — so the internal envelope barely registers the thing that is actually slipping.
SPI returns to 1.000 at completion, always | When the last work package is done, EV equals PV by definition, however late it is. SPI cannot report a late finish; it reports zero variance on the day you finish, whenever that is.
The critical path is invisible to it | Earned value is indifferent to sequence. A program can be ahead on SPI and still have its single binding constraint slipping, because the constraint is a date, not a dollar.

## 5 Forecast to Completion
Measure | Value | What it assumes
EAC — estimate at completion | $38,363,000 | BAC ÷ CPI. Assumes the 0.939 efficiency seen so far is TYPICAL and continues for the remaining work.
ETC — estimate to complete | $21,863,000 | EAC less what has been spent
VAC — variance at completion | $-2,355,000 | The forecast overrun on internal labor if nothing changes
TCPI — to-complete performance index | 1.052 | The efficiency the REMAINING work must achieve to finish at BAC

## 6 Variance Thresholds What Act
Trigger | Threshold | Response | Who
Routine | CPI 0.95–1.05 at account level | Reported. No action required — this is measurement noise on a 0/100 rule with long work packages. | Control account owner
Explain | CPI below 0.95 at account level, or CV over $250,000 | Written variance analysis: cause, whether it is typical or one-off, and the ETC impact. Not a plan — an explanation. | Control account owner to the PMO
Correct | CPI below 0.90, or forecast VAC over $1,000,000 | Corrective action plan with a named owner and a date by which the index should recover. | Program Director
Re-estimate | TCPI exceeds CPI by more than 0.05 | The BAC is no longer achievable on current performance. Table a revised EAC at the next gate rather than continue reporting against a number the arithmetic has ruled out. | Development Committee

## 7 How This Baseline Is Maintain
Rule | Detail
Earned value is claimed by rule, not by opinion | Work packages under 0/100: nothing is earned until the package is complete against its dictionary acceptance statement. No partial credit, for the same reason milestones are binary.
The baseline moves only with the scope baseline | CR-01 and CR-02 added budget; both were re-baselined into the PMB at the point the Committee approved them, and not before.
Actuals come from the finance system, not from the program | The Program Director does not supply the AC line. A program that reports its own actuals is marking its own homework.
Reported monthly, tabled at every gate | Alongside the budget and the schedule, so the three baselines are always read together.

## About
Performance Measurement Baseline
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Performance Measurement Baseline · baselined 30 June 2026, measured 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.