## 1 Three Numbers Not One
Figure | Amount | What it means
Authorized ceiling | $243,040,000 | The maximum the program may ever spend. Set at charter, changeable only by the Board. Most of it is not spendable today.
Released to date | $201,200,000 | Tranches actually released through Gate 4. This is the program's real spending authority at 15 October 2026.
Spent to date | $101,000,000 | 50% of released authority. The only figure that has left the building.

## 2 Cost Pools
Cost pool | Amount | Share of base
Nonclinical pharmacology & GLP toxicology | $8,500,000 | 3.9%
CMC — early development | $6,200,000 | 2.9%
IND-enabling package & submission | $3,800,000 | 1.8%
Phase 1 clinical | $8,500,000 | 3.9%
Phase 2 clinical | $38,000,000 | 17.5%
Phase 3 clinical | $109,100,000 | 50.3%
NDA preparation & review support | $12,400,000 | 5.7%
CMC scale-up & process validation | $9,200,000 | 4.2%
Regulatory affairs | $7,600,000 | 3.5%
Program management | $5,300,000 | 2.4%
External fees, advisors & other non-labor | $8,400,000 | 3.9%
Base program | $217,000,000 | 100.0%

## 3 Pool by Stage the Reconcilia
Cost pool | S1 | S2 | S3 | S4 | S5 | Pool total
Nonclinical pharmacology & GLP toxicology | $8,500,000 | — | — | — | — | $8,500,000
CMC — early development | $5,200,000 | $1,000,000 | — | — | — | $6,200,000
IND-enabling package & submission | — | $3,800,000 | — | — | — | $3,800,000
Phase 1 clinical | — | $8,500,000 | — | — | — | $8,500,000
Phase 2 clinical | — | — | $38,000,000 | — | — | $38,000,000
Phase 3 clinical | — | — | — | $109,100,000 | — | $109,100,000
NDA preparation & review support | — | — | — | — | $12,400,000 | $12,400,000
CMC scale-up & process validation | — | — | — | $9,200,000 | — | $9,200,000
Regulatory affairs | $800,000 | $1,400,000 | $1,200,000 | $2,800,000 | $1,400,000 | $7,600,000
Program management | $900,000 | $1,000,000 | $1,000,000 | $1,600,000 | $800,000 | $5,300,000
External fees, advisors & other non-labor | $2,000,000 | $500,000 | $1,600,000 | $3,100,000 | $1,200,000 | $8,400,000
Tranche total | $17,400,000 | $16,200,000 | $41,800,000 | $125,800,000 | $15,800,000 | $217,000,000

## 4 Tranche Release
Tranche | Released at | Stage window | Amount | Status
Stage 1 — Nonclinical & CMC | Gate 0 · 01 Mar 2022 | Mar 2022 – Dec 2022 | $17,400,000 | released
Stage 2 — IND & Phase 1 | Gate 1 · 31 Dec 2022 | Jan 2023 – May 2024 | $16,200,000 | released
Stage 3 — Phase 2 | Gate 3 · 31 May 2024 | Jun 2024 – Jun 2026 | $41,800,000 | released
Stage 4 — Phase 3 & NDA | Gate 4 · 30 Jun 2026 | Jul 2026 – Sep 2028 | $125,800,000 | released
Stage 5 — Review & Launch | Gate 5 · 30 Sep 2028 | Oct 2028 – Jun 2029 | $15,800,000 | not yet released
Total | — | — | $217,000,000 | —

## 5 Rate Basis the Internal Ext
Function | FTE | Hours | Cost | Blended rate
Clinical Operations | 24 | 51,900 | $9,861,000 | $190
Technical Operations / CMC | 16 | 30,200 | $5,436,000 | $180
Biostatistics & Data Management | 12 | 22,600 | $4,068,000 | $180
Regulatory Affairs | 10 | 18,900 | $3,969,000 | $210
Clinical Development | 12 | 17,900 | $3,580,000 | $200
Pharmacovigilance & Drug Safety | 8 | 14,200 | $2,556,000 | $180
Quality Assurance (GxP) | 7 | 12,800 | $2,304,000 | $180
Nonclinical Safety & Pharmacology | 5 | 9,400 | $1,692,000 | $180
Program Management Office | 4 | 7,200 | $1,296,000 | $180
Market Access & Commercial | 4 | 5,000 | $850,000 | $170
Development Committee (oversight only) | 7 | 1,320 | $396,000 | $300
Total internal roster | 109 | 191,420 | $36,008,000 | $188

## 6 Vendor Commitments
Vendor | Stage | Work package | Value | Status
Meridian Clinical Research (CRO) | Stage 3 | Phase 2 execution | $22,400,000 | authorized
| Stage 4 | Phase 3 execution, both pivotals + CV sub-study | $68,500,000 | authorized
| Stage 5 | Close-out, clinical study reports | $3,100,000 | not yet authorized
|  | Meridian Clinical Research (CRO) total | $94,000,000
Aldergate Biologics (CMO) | Stage 2 | Phase 1 clinical supply | $1,400,000 | authorized
| Stage 3 | Phase 2 clinical supply | $2,600,000 | authorized
| Stage 4 | Registration batches, process validation, stability | $9,200,000 | authorized
|  | Aldergate Biologics (CMO) total | $13,200,000
Kestrel Laboratories (central lab) | Stage 2 | Phase 1 bioanalytical | $900,000 | authorized
| Stage 3 | Phase 2 central lab and bioanalytical | $3,200,000 | authorized
| Stage 4 | Phase 3 central lab, CV sub-study assays | $8,900,000 | authorized
|  | Kestrel Laboratories (central lab) total | $13,000,000
All contracted commitments |  |  | $120,200,000

## 7 Contingency
Draw | Against | Amount
CR-02 cardiovascular outcomes sub-study | Approved change (D-06) | $7,200,000
I-02 CMC method transfer recovery | Materialised issue | $1,850,000
Total drawn | — | $9,050,000
Reserve remaining | — | $16,990,000

## 8 Spend Variance Forecast (1)
Stage | Tranche released | Actual | Variance | %
Stage 1 — Nonclinical & CMC | $17,400,000 | $17,100,000 | $-300,000 | -1.7%
Stage 2 — IND & Phase 1 | $16,200,000 | $16,600,000 | +$400,000 | +2.5%
Stage 3 — Phase 2 | $41,800,000 | $40,900,000 | $-900,000 | -2.2%
Closed stages 1–3 | $75,400,000 | $74,600,000 | $-800,000 | -1.1%

## 8 Spend Variance Forecast (2)
Measure | Value
Stage 4 tranche | $125,800,000
Stage 4 spend to date | $26,400,000
Consumed | 21%
Stage 4 window | Jul 2026 – Sep 2028
Calendar elapsed | 13%

## 8 Spend Variance Forecast (3)
Component | Amount
Base program | $217,000,000
Contingency drawn to date | $9,050,000
Estimate at completion | $226,050,000
Authorized ceiling | $243,040,000
Headroom against ceiling | $16,990,000

## 9 Cash Phasing
Year | Spend | Share | Cumulative | Note
2022 | $17,400,000 | 8.0% | $17,400,000 | Part year — program starts March
2023 | $11,400,000 | 5.3% | $28,800,000
2024 | $16,500,000 | 7.6% | $45,300,000
2025 | $20,100,000 | 9.3% | $65,400,000
2026 | $38,000,000 | 17.5% | $103,400,000
2027 | $55,900,000 | 25.8% | $159,300,000 | Peak — Phase 3 at full enrolment
2028 | $47,200,000 | 21.8% | $206,500,000
2029 | $10,500,000 | 4.8% | $217,000,000 | Part year — launch November
Total | $217,000,000 | 100.0% | —

## 12 Reconciliation
Identity | Check
Cost pools sum to base | $217,000,000 = $217,000,000 ok
Tranches sum to base | $217,000,000 = $217,000,000 ok
Matrix rows sum to pool totals | 11 of 11 pools reconcile ok
Matrix columns sum to tranches | 5 of 5 stages reconcile ok
Cash phasing sums to base | $217,000,000 = $217,000,000 ok
Closed-stage actuals sum to reported spend | $74,600,000 = $74,600,000 ok
Base plus contingency equals ceiling | $217,000,000 + $26,040,000 = $243,040,000 ok

## About
Program Budget
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Program Budget · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.