## 1 The Grid (1)
Decision | PD Tyrrell | CMO Okoye | CSO Vasquez | REG Raghunathan | CFO Thornbury | MA Barrington | CQO Solberg | DMC Vartanian | Note
Authorize a stage tranche | R | C | C | C | A | I | I | - | ⚠ The PD proposes; the CFO is accountable for releasing money.
Approve the program plan and baselines | A | C | C | C | C | C | I | - | One of only TWO rows where the PD is accountable.
Approve a protocol or protocol amendment | C | A | C | C | I | I | C | I | Medical judgment. The PD coordinates and does not decide.
Set or revise the target product profile | C | C | A | C | C | R | I | - | Scientific ownership, with market access driving the commercial attributes.
Approve the statistical analysis plan | I | C | R | C | - | - | C | A | ⚠⚠ Accountability sits with the DMC chair as the independent party. The sponsor cannot be accountable for the plan that judges its own trial.
Authorize database lock and unblinding | R | C | C | I | - | - | C | A | Same reasoning. The sequence is the integrity of the trial.
Approve a submission to the agency | R | C | C | A | I | I | C | - | Regulatory owns what is said to the agency, and carries the commitments made.
Accept or decline an expedited designation | C | C | C | A | I | C | - | - | A written argument to the agency about our own product.
Approve a change request | R | C | C | C | A | C | I | - | Scope changes cost money; the CFO is accountable for the ceiling.
Draw against contingency | R | I | I | I | A | I | I | - | Proposed by the program, released by finance, with the rejected alternative recorded.
Accept a quality deviation or CAPA | I | C | - | C | - | - | A | - | ⚠ The CQO reports to the CEO, not to this program. Deliberate.
Stop the trial for safety | I | C | I | I | - | - | C | A | ⚠⚠ Outside the Committee's authority entirely. The program cannot manage the body that might stop it.
Approve pricing and the rebate ceiling | C | I | - | I | A | R | - | - | Recommended by market access, accountable to finance.
Approve the launch plan | C | C | - | C | C | A | C | - | Commercial ownership, with regulatory consulted on promotional boundaries.
Accept a post-marketing commitment | R | C | C | A | I | I | C | - | It is a regulatory commitment and it outlives the program.
Close the program | A | C | I | C | C | C | C | - | The second and last of the PD-accountable rows.

## 1 The Grid (2)
| Who | Role
PD | C. Tyrrell | Program Director
CMO | Dr. A. Okoye | Chief Medical Officer / sponsor
CSO | Dr. H. Vasquez | Chief Scientific Officer
REG | Dr. P. Raghunathan | SVP Regulatory Affairs
CFO | M. Thornbury | Chief Financial Officer
MA | J. Barrington | SVP Market Access
CQO | Dr. I. Solberg | Chief Quality Officer
DMC | Prof. E. Vartanian | Data Monitoring Committee chair

## 3 Four Decisions Accountable Ou
Decision | Accountable | Why not the program
Approve the statistical analysis plan | DMC chair | ⚠ The sponsor cannot be accountable for the plan that judges its own trial. The analysis order decides what may be claimed.
Authorize database lock and unblinding | DMC chair | The sequence — SAP signed, then lock, then unblind — is the integrity of the trial. Reverse any two and the result becomes unfalsifiable.
Accept a quality deviation or CAPA | Chief Quality Officer | Reports to the CEO, not to this program. An audit function accountable to the party it audits is not independent.
Stop the trial for safety | DMC chair | ⚠⚠ Entirely outside the Committee's authority. The program cannot manage the body that might stop it.

## 4 The Rules That Keep It Honest
Rule | Here | Why it matters
Exactly one A per row | Enforced at build time | ⚠ Two names in the A column means nobody is accountable. Shared accountability is the most common and most damaging RACI defect, and it usually reflects a decision nobody wanted to make about who decides.
R and A may be the same person, and usually are not | Separated on 13 of 16 rows here | Responsible does the work; Accountable answers for it. Where they separate, the artifact is describing real delegation rather than a job description.
C means their view can change the outcome | Used sparingly | ⚠ If a party is consulted and the answer never changes, they are Informed. Inflating C is how a RACI becomes a courtesy list and stops being read.
I means told after the fact | Not a lesser status | Some of the most senior people on this grid are I on rows they have no business deciding.
A dash means no role at all | Used deliberately | A grid with no blanks has not been thought about. Not everyone belongs on every row.

## 5 When the Grid Does Not Answer
Situation | What happens | Who resolves it
A decision that is not on the grid | It is mapped to the nearest row by type rather than by subject. A novel question about analysis order is an SAP decision; a novel question about money is a tranche decision. ⚠ The grid is a set of decision classes, not a list of questions. | Program Director proposes the mapping; the accountable party for that class confirms it.
R and A disagree | A decides. That is what accountable means, and it is the situation the single-A rule exists for. ⚠ The disagreement is minuted, because a decision taken over a documented objection is a different fact from an unopposed one. | No escalation needed. The grid already answered it.
Two parties both believe they are A | ⚠⚠ A defect in the grid, not a dispute between people. The row is re-drafted and taken to the Committee — not settled informally between the two claimants. | Development Committee, as owner of the governance model.
The accountable party is unavailable | Named deputies exist for every A. ⚠ Accountability delegates to a person, never to a function — "Regulatory Affairs" cannot be accountable at the moment a decision is missed. | The deputy, on the record, with the same authority.
The grid contradicts the charter | The charter wins, and the contradiction is itself reported. | ⚠ A RACI that has drifted from the document it implements is describing how the program behaves rather than how it was authorized to.

## About
RACI Matrix
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · RACI Matrix · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.