## Risks
Ref | Risk | Severity | Category | Owner | Horizon | Response
R-01 | Phase 3 efficacy does not separate sufficiently from approved products in the class | High | Clinical | Dr. S. Aldridge | Jun 2028 | Phase 2 dose-ranging carried a wider dose span than required for selection alone; the top dose was retained into Phase 3.
R-02 | Gastrointestinal tolerability drives discontinuation above the modelled rate | High | Clinical | Dr. S. Aldridge | Dec 2027 | Extended dose-escalation schedule adopted after Phase 2; discontinuation is a monitored endpoint with (Independent) Data Monitoring Committee (DMC) review.
R-03 | Registration-batch manufacture or process validation slips against the New Drug Application (NDA) date | Medium | Chemistry, Manufacturing and Controls (CMC) | Dr. K. Oyelaran | Mar 2028 | Dual-source qualification from Gate 4 (D-05); stability protocol started at the earliest supportable point.
R-04 | A competitor approval changes the evidentiary bar before filing | Medium | Market | J. Barrington | Sep 2028 | Differentiation rests on tolerability rather than magnitude of effect; the comparator sub-study (D-08) exists for this.
R-05 | Phase 3 enrolment runs behind the planned curve | Medium | Clinical | Dr. R. Molyneux | Jun 2027 | Site over-recruitment against plan; obesity clinic partnerships; pre-screening registry.
R-06 | Payer coverage at launch is narrower than the business case assumes | Medium | Commercial | J. Barrington | Mar 2029 | Health-economic evidence package built alongside Phase 3, not after it; payer advisory boards from 2027.
R-07 | Pre-approval inspection finds a deficiency at the contract manufacturer | Low | Quality | Dr. I. Solberg | Jan 2029 | Two internal audits scheduled ahead of the inspection window; QA embedded at site from registration batches.

## Issues
Ref | Issue | Status | Severity | Owner | Raised | Recovery
I-01 | Phase 1 recruitment ran four weeks behind plan | Closed | Medium | Dr. R. Molyneux | 14 Nov 2023 | Two additional units activated. Recovered inside Stage 2; no gate impact.
I-02 | Analytical method transfer to Aldergate did not meet acceptance criteria first pass | Open | High | Dr. K. Oyelaran | 09 Mar 2026 | CMC team embedded on site; re-qualification complete for two of three methods. Contingency drawn.
I-03 | Two Phase 3 sites failed activation on IRB timelines | Open | Low | Dr. R. Molyneux | 02 Sep 2026 | Replacement sites identified from the reserve list; no change to the enrolment curve.

## Assumptions
Ref | Assumption
A-01 | FDA accepts the co-primary endpoints agreed at the End-of-Phase-2 meeting (percent change in body weight and proportion achieving ≥5% reduction) without further modification.
A-02 | Standard 10-month review applies. Neither priority review nor a breakthrough designation is assumed in the plan or the business case.
A-03 | No advisory committee meeting is convened. Budget carries no line for advisory committee preparation.
A-04 | Phase 3 enrolment completes within the planned window at the planned site count, on the recruitment rates observed in Phase 2.
A-05 | Aldergate Biologics has registration-batch capacity available in the Stage 4 window as contracted.
A-06 | Payer coverage for chronic weight management continues to broaden over the launch horizon; the case does not assume Medicare Part D coverage.

## Decisions
Ref | Decision | Rationale
D-01 | File a 505(b)(1) NDA as a new molecular entity rather than a 505(b)(2) | No suitable listed drug to reference; the molecule is novel. 505(b)(2) was assessed and closed at Gate 1.
D-02 | Once-weekly subcutaneous prefilled pen; no oral formulation at launch | Oral bioavailability work would add an estimated 18 months and a second CMC program for a segment the launch case does not require.
D-03 | United States first; EU marketing authorization deferred to Year 4+ | Concentrates regulatory and commercial effort on one pathway; avoids parallel EMA scientific advice and a second CMC dossier during Phase 3.
D-04 | Outsource Phase 2 and Phase 3 execution to a single full-service Contract Research Organization (CRO) | Building internal trial operations for a single asset does not pay back. Single-vendor rather than functional service provider model, for accountability at the trial level.
D-05 | Single-source drug substance through Phase 2; dual-source from Gate 4 | Qualifying a second source before Phase 2 read-out risks spend on an asset that may not proceed.
D-06 | Carry a dedicated cardiovascular outcomes sub-study inside Phase 3 (CR-02) | Aligns with agency expectations for chronic metabolic therapy and pre-empts a post-marketing requirement.
D-07 | Carry class labeling for thyroid C-cell tumors; propose no REMS at filing | Consistent with approved products in the class. A REMS proposal is not supported by the safety database and would be a commercial disadvantage if volunteered.
D-08 | Placebo-controlled pivotal trials with an active-comparator sub-study | Placebo control is required for the registration endpoint; the comparator arm serves market access, not approval.
D-09 | Chair of the Development Committee does not hold a vote | The person accountable for program progress is not the person who decides whether it continues.

## Dependencies
Ref | Dependency
DEP-01 | Investigational New Drug application (IND) acceptance (30-day safety review) before any first-in-human dosing.
DEP-02 | Phase 2 dose selection before Phase 3 protocol finalisation.
DEP-03 | Registration batches manufactured and on stability before NDA submission.
DEP-04 | Process validation complete before the pre-approval inspection.
DEP-05 | Database lock before topline analysis; topline before NDA assembly begins.

## Approved Changes
Ref | Change | Status | Approved | Effect
CR-01 | Add an Asian-population cohort to Phase 2 | Approved | 09 Oct 2024 | Increases N by 50. Supports the later EU and Asia-Pacific strategy without a separate bridging study.
CR-02 | Add a cardiovascular outcomes sub-study to Phase 3 | Approved | 20 Apr 2026 | Adds $6,400,000 and six months to the Phase 3 window. Pre-empts a post-marketing requirement (D-06).

## Gate Conditions
Ref | Condition | Owner | Due | Closed | Status | Addresses
GC-01 | Complete analytical method re-qualification at Aldergate for all three methods | Dr. K. Oyelaran | 18 Dec 2026 | — | open | I-02; the CMC readiness score recorded at Gate 4
GC-02 | Confirm the cardiovascular sub-study protocol with the DMC before first CV-cohort dosing | Dr. S. Aldridge | 30 Nov 2026 | 25 Sep 2026 | closed | CR-02 scope addition
GC-03 | Stand up the payer evidence plan and hold the first advisory boards | J. Barrington | 31 Mar 2027 | — | at-risk | R-06; the market access score recorded at Gate 4

## About
RAIDD Log
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · RAIDD Log · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.