## 1 The Chain Is Not Requirement
Link | What it fixes | When it is set
TPP attribute | What the product must be able to claim to be commercially viable | Gate 0, revised by governance only
Protocol endpoint | What will be measured, in whom, over what period | Before Phase 3 opens. ⚠ Effectively irreversible once participants are enrolled.
SAP analysis | How it will be tested, and in what order | ⚠ Signed before database lock. The testing hierarchy is fixed here.
CSR section | Where the result is reported | After lock, from the locked data
Label claim | What may actually be said | Negotiated with the agency at review — and determined by the four links above

## 2 The Matrix
Ref | TPP attribute | Protocol endpoint | SAP analysis | CSR section | Label target | Weight
T-01 | Mean weight reduction ≥15% at week 68 | Co-primary endpoint, both pivotals | Primary analysis, hierarchy position 1 | §11 Efficacy | §14 Clinical Studies | carries
T-02 | Responder rate ≥80% achieving ≥5% reduction | Co-primary endpoint, both pivotals | Primary analysis, hierarchy position 2 | §11 Efficacy | §14 Clinical Studies | carries
T-03 | Proportion achieving ≥10% reduction | Key secondary | Hierarchy position 3 | §11 Efficacy | §14 Clinical Studies | carries
T-04 | GI-attributed discontinuation ≤4% | Key secondary, vs active comparator | Hierarchy position 4 | §11 Efficacy and §12 Safety | ⚠ Comparative claim SOUGHT — not granted unless positions 1–3 all succeed | complete, does not carry
T-05 | Once-weekly dosing, maintenance within 20 weeks | Fixed by protocol design | Descriptive; exposure summary | §9 Investigational plan | §2 Dosage and Administration | carries
T-06 | No unexpected serious safety signal | Safety monitoring throughout; DMC review | Pooled safety analysis | §12 Safety | §5 Warnings and §6 Adverse Reactions | carries
T-07 | Waist circumference reduction | Secondary | Hierarchy position 5 | §11 Efficacy | ⚠ Below the likely cut — supportive text only | complete, does not carry
T-08 | Patient-reported physical function | Secondary | Hierarchy position 6 | §11 Efficacy | ⚠ Below the likely cut — supportive text only | complete, does not carry
T-09 | Cardiovascular safety adequate for the indication | CV sub-study (CR-02), 640 participants | Separate analysis, not in the hierarchy | Standalone CSR | §5 Warnings — and pre-empts a post-marketing requirement | carries
T-10 | Chronic weight management indication as sought | Enrolled population and inclusion criteria | Population definitions, blind data review | §10 Study participants | §1 Indications and Usage | carries

## 3 A Complete Chain That Does No
Link | T-04 — GI-attributed discontinuation | Status
TPP attribute | ≤4% target, ≤7% minimum acceptable. The differentiator. | ✔ Present since v1.0
Protocol endpoint | Key secondary, measured against an active comparator | ✔ Collected in both pivotals
SAP analysis | Pre-specified, hierarchy position 4 of 6 | ✔ Signed before lock
CSR section | Reported in §11 and §12 | ✔ Will be reported whatever the result
Label claim | ⚠ Comparative tolerability claim in §14 | Only if positions 1–3 all succeed first

## 4 Both Directions
Direction | Found | What it means
Forward — a TPP attribute with no analysis that tests it | 0 | Every attribute in the profile maps to at least one pre-specified analysis. ⚠ This is the direction most programs check, and it is the easier one.
Backward — an analysis serving no TPP attribute | 2 | ⚠ Two exploratory analyses in the SAP trace to no profile attribute. Both are legitimate science; neither can support a claim, and reporting them alongside pre-specified analyses is how a CSR loses a reviewer's trust.
A claim sought with no analysis positioned to deliver it | 0 | The comparative claim IS positioned — at hierarchy position 4. The link exists; it simply may not carry weight.
A protocol endpoint collected but never analyzed | 1 | ⚠ One exploratory biomarker is collected and has no analysis in the SAP. Collecting data nobody will analyze imposes burden on participants for no evidentiary return.

## 5 Using It for Change Impact
Change | What the matrix showed | What it cost to know
CR-01 — add an Asian-population cohort to Phase 2 | Touches T-10 only. The cohort enlarges the population supporting the indication; no endpoint, analysis or claim changes. | A contained change. Approved without re-opening the SAP.
CR-02 — add a cardiovascular sub-study | ⚠ Creates a NEW chain (T-09) end to end — a new endpoint, a separate analysis, a standalone CSR and a §5 label target — without touching any existing chain. | Why it could be added mid-program at all. A change that had altered an existing analysis would have required re-opening the hierarchy.
A protocol amendment adding one assessment | Touches no chain — and touches three work packages and 2,480 participants. | ⚠ The matrix says it is harmless and the WBS says it is expensive. Both are right.
Re-positioning T-04 higher in the hierarchy | Touches T-01, T-02 and T-03 — every chain above it — because testing order is shared state. | The reason it was never done. A local change with program-wide consequence.

## 6 What Traceability Would Have
If the matrix had been built at | It would have shown | Actionable?
Gate 3 — before the Phase 3 protocol was fixed | ⚠ That the differentiating attribute sat below three endpoints it depended on, and that no head-to-head trial was planned to support it | Yes. The endpoint could have been powered differently, or a separate comparative study scoped.
Before the SAP was signed | That hierarchy position 4 made the commercial case conditional on three prior successes | ⚠ Partially. Position could still move, at the cost of risking the efficacy claim — which is why it was placed there.
After database lock | The same thing, definitively | No. By then it is a reporting fact.
At the label negotiation | That the claim was never available | No. And this is when most programs discover it.

## 7 Borrowed From Systems Deliver
Systems traceability | Here
Requirement → design → build → test case → result | TPP → endpoint → analysis → CSR → label claim
A failed test produces a defect and a retest | ⚠ A failed analysis produces nothing. There is no retest; the participants are enrolled and the data are locked.
Coverage is the headline metric | ⚠ Coverage is necessary and nearly meaningless. Weight is the metric — whether the chain can support a claim.
Requirements can be re-baselined mid-build | The TPP can be revised by governance; the protocol cannot, once participants are enrolled under it.
Bidirectional checks are standard practice | Rarely done. ⚠ The backward walk is where the orphans are, in both disciplines.

## About
Requirements Traceability Matrix
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Requirements Traceability Matrix · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.