## 1 What This Plan Commits
Number | Value | The question it answers
Headcount | 109 people | How many individuals are named against this program at some point in its life. It is a roster, not a room. It is the wrong number for capacity planning and the right number for onboarding, training, system access and GxP qualification.
Hours | 191,420 hours | How much effort the program consumes. This is the number that reconciles to cost, because internal labor is charged by the hour against a blended rate.
Concurrent FTE | 20.1 at peak (Stage 4) | How much of the organization is occupied at once. This is the number a functional head actually negotiates over, and it is nowhere near the headcount.

## 2 The Roster by Function
Function | Headcount | Hours | Hrs / head | Blended rate | Internal cost | Scope
Clinical Operations | 24 | 51,900 | 2,162 | $190 | $9,861,000 | Sites, monitoring, enrolment, clinical supply
Technical Operations / CMC | 16 | 30,200 | 1,887 | $180 | $5,436,000 | Process, analytical methods, scale-up, validation
Clinical Development | 12 | 17,900 | 1,491 | $200 | $3,580,000 | Protocols, medical monitoring, clinical study reports
Biostatistics & Data Management | 12 | 22,600 | 1,883 | $180 | $4,068,000 | SAP, EDC, database lock, analysis datasets
Regulatory Affairs | 10 | 18,900 | 1,890 | $210 | $3,969,000 | Strategy, submissions, agency interaction, labeling
Pharmacovigilance & Drug Safety | 8 | 14,200 | 1,775 | $180 | $2,556,000 | Case processing, signal detection, DSUR
Quality Assurance (GxP) | 7 | 12,800 | 1,828 | $180 | $2,304,000 | Audits, CAPA, GxP compliance, inspection readiness
Nonclinical Safety & Pharmacology | 5 | 9,400 | 1,880 | $180 | $1,692,000 | Toxicology, pharmacology, study oversight
Program Management Office | 4 | 7,200 | 1,800 | $180 | $1,296,000 | Governance, planning, risk, reporting
Market Access & Commercial | 4 | 5,000 | 1,250 | $170 | $850,000 | Payer evidence, pricing, launch readiness
Development Committee (oversight only) | 7 | 1,320 | 188 | $300 | $396,000 | Gate decisions, funding release, condition closure
Total | 109 | 191,420 | 1,756 | $188 | $36,008,000

## 3 Headcount Is Not Effort
Stage | Window | Duration | Hours | Concurrent FTE
Stage 1 | Mar 2022 – Dec 2022 | 10.1 months | 17,180 | 9.8
Stage 2 | Jan 2023 – May 2024 | 17.0 months | 23,840 | 8.1
Stage 3 | Jun 2024 – Jun 2026 | 25.0 months | 31,320 | 7.2
Stage 4 | Jul 2026 – Sep 2028 | 27.0 months | 94,180 | 20.1
Stage 5 | Oct 2028 – Jun 2029 | 9.0 months | 24,900 | 16.0

## 4 Phasing by Stage
Function | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Total
Clinical Operations | — | 3,200 | 9,800 | 34,600 | 4,300 | 51,900
Technical Operations / CMC | 6,400 | 4,200 | 3,600 | 13,400 | 2,600 | 30,200
Clinical Development | 600 | 2,400 | 4,100 | 8,600 | 2,200 | 17,900
Biostatistics & Data Management | 300 | 2,100 | 4,400 | 12,300 | 3,500 | 22,600
Regulatory Affairs | 1,900 | 3,800 | 2,400 | 6,100 | 4,700 | 18,900
Pharmacovigilance & Drug Safety | 400 | 1,600 | 2,400 | 7,600 | 2,200 | 14,200
Quality Assurance (GxP) | 1,300 | 1,900 | 1,800 | 5,600 | 2,200 | 12,800
Nonclinical Safety & Pharmacology | 5,200 | 2,900 | 800 | 400 | 100 | 9,400
Program Management Office | 900 | 1,300 | 1,200 | 2,800 | 1,000 | 7,200
Market Access & Commercial | — | 200 | 600 | 2,300 | 1,900 | 5,000
Development Committee (oversight only) | 180 | 240 | 220 | 480 | 200 | 1,320
Stage total | 17,180 | 23,840 | 31,320 | 94,180 | 24,900 | 191,420
Share of program hours | 9.0% | 12.5% | 16.4% | 49.2% | 13.0% | 100.0%
Share of program money | 8.0% | 7.5% | 19.3% | 58.0% | 7.3% | 100.0%

## 5 What the Internal Roster Actu
| Amount | Share of base
Internal roster — salary, benefits, overhead recovery | $36,008,000 | 16.6%
External — CRO, CMO, central lab, sites, fees, advisors, counsel | $180,992,000 | 83.4%
Base program | $217,000,000 | 100.0%

## 6 How a Person Is Actually Assi
Question | Who decides | Instrument
Who does the work — which named individual | Function head | Line management. The Program Director has no vote here and should not want one.
How the work is done — method, standard, review | Function head | Functional SOPs, which outlive the program.
What is produced and when | Program Director | Charter, work breakdown structure, milestone commitments, gate conditions.
How much effort is available | Negotiated, and escalated when it fails | This plan. Its whole purpose is to make the negotiation reference a number.

## 8 Resource Risks
Risk | Exposure | Response
Key-person concentration | 102 working staff across 10 functions leaves several single points of failure — most acutely in Regulatory Affairs (10 people carrying every agency commitment) and the Program Management Office (4). | Named deputy for every control account owner; the gate pack cannot be tabled by one person.
Stage 4 concurrency | 20.1 FTE sustained across 27.0 months is the longest continuous demand in the program, and it overlaps the CMC validation peak. | Phased against the CMC critical path rather than the clinical one; CMC hours are protected at gate review because CMC gates the filing independently.
Attrition through a {F.PROGRAM_YEARS:.0f}-year program | The program outlasts typical tenure. Turnover costs qualification and re-training, not merely recruitment — and in a GxP environment an unqualified person cannot perform the task at all. | Documented handover as a deliverable, not a courtesy; training records maintained as essential documents in the TMF.
The plan not being re-baselined | The most likely failure and the least dramatic. A stale resource plan is indistinguishable from a current one until it is needed. | Re-tabled at every gate with the budget; stage columns compared to actuals.

## About
Resource Plan
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Resource Plan · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.