## 1 A Register Lists a Report Rea
Question | The register | This report
What are the risks? | ✔ Seven, with owners and responses | Not repeated
How much are we exposed to? | ✘ Ratings are High/Medium/Low | ✔ $271,700,000, probability × impact
Is it getting better or worse? | ✘ A register is a snapshot | ✔ Eight quarters of trend
Which risks are actually managed? | ✘ Every entry has a response, which is not the same | ✔ 4 managed, 1 explicitly not
What is it missing? | ✘ By construction, a register cannot know | ✔ §6

## 2 Exposure
Ref | Risk | Category | Probability | Impact if it happens | Exposure | Share | Kind
R-01 | Phase 3 efficacy does not separate sufficiently from approved products in the class | Clinical | 25% | $340,000,000 | $85,000,000 | 31% | value
R-06 | Payer coverage at launch is narrower than the business case assumes | Commercial | 45% | $180,000,000 | $81,000,000 | 30% | value
R-02 | Gastrointestinal tolerability drives discontinuation above the modelled rate | Clinical | 35% | $210,000,000 | $73,500,000 | 27% | value
R-04 | A competitor approval changes the evidentiary bar before filing | Market | 20% | $95,000,000 | $19,000,000 | 7% | value
R-05 | Phase 3 enrolment runs behind the planned curve | Clinical | 55% | $9,600,000 | $5,280,000 | 2% | schedule
R-03 | Registration-batch manufacture or process validation slips against the NDA date | CMC | 30% | $14,400,000 | $4,320,000 | 2% | schedule
R-07 | Pre-approval inspection finds a deficiency at the contract manufacturer | Quality | 15% | $24,000,000 | $3,600,000 | 1% | schedule
Total |  |  |  |  | $271,700,000 | 100%

## 4 Managed or Merely Recorded
Ref | Managed? | What the response actually does
R-01 | Partially — the dose span was widened in Phase 2, and nothing further can be done now. | ⚠ The largest exposure in the register and the least actionable. If the effect size does not separate, the commercial case fails and no program action recovers it.
R-06 | Partially — evidence package built alongside Phase 3; payer advisory boards from 2027. | Gate condition GC-03 exists for this. The evidence can be generated; the formulary cycle cannot be accelerated.
R-02 | Yes — escalation extended to 20 weeks, discontinuation is a monitored endpoint with DMC review. | The mitigation was a real trade: a slower escalation delays time to maintenance dose in exchange for tolerability.
R-04 | No — the program cannot influence a competitor's approval. | ⚠ Recorded and monitored, not managed. Naming it as unmanaged is more useful than listing a mitigation that does not mitigate.
R-05 | Yes — reserve site list, obesity clinic partnerships, pre-screening registry. | Two months of slip. ⚠ The highest-probability risk in the register, and the mitigations act on a five-month lag.
R-03 | Yes — stability started at the earliest supportable point; QA embedded at the site. | Three months of slip at the stated burn rate. Already partially realized through the method-transfer failure.
R-07 | Yes — two internal audits ahead of the inspection window. | Five months of slip if a deficiency requires re-inspection, which is the lowest probability in the register and one of the larger schedule impacts.

## 5 Risks That Became Issues
Risk | Became | What happened | Assessment
R-03 | I-02 | Analytical method transfer failed acceptance on first pass | ⚠ Converted. The risk was registered, rated Medium, and mitigated with dual-source qualification — and it happened anyway, at the one supplier the program has.
R-05 | — | Enrolment behind curve | Converting. Not yet an issue in the register, and the leading indicators crossed their thresholds eleven months before the status report escalated it.

## 6 The Registers Blind Spots
Blind spot | Why it is not in the register
Risks nobody named | Every register is a list of the things the people who wrote it thought of. The Phase 2 competitor read-out that reset the evidentiary bar is not in this register because nobody at Gate 4 expected it.
Correlated risks | ⚠ Exposure is summed as though the risks are independent. They are not: R-01, R-02 and R-06 share a root — if the effect size disappoints, tolerability matters more AND payers pay less. The true tail is worse than the arithmetic.
Risks inside the mitigation | The extended escalation schedule mitigates R-02 by delaying time to maintenance dose — which is itself a commercial risk nobody has registered.
Risks owned by somebody else | The CRO, the CMO and 260 sites each carry risks that become the sponsor's on materialization and appear in no sponsor register until they do.

## About
Risk Report
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Risk Report · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.