## Slide 1
VitaFlow Development Program
Steering Committee — Stage 4 checkpoint
Vitalis Therapeutics Inc. Stage 4 of 5 · 15 October 2026
Notes: Stage 4 checkpoint. Twenty minutes: five on the ask, ten on enrolment, five on decisions.

## Slide 2
What we are asking for
Decisions before discussion — the rest of this deck is the evidence
1
Approve a revised estimate at completion for the internal labor envelope
TCPI 1.052 against CPI 0.939 — the BAC is no longer achievable on current performance and the variance threshold set at Gate 4 has been breached.
This meeting
2
Authorize release of the second tranche of reserve sites (16 of 34)
The first release has not recovered the curve. Recovery remains forecast at half of planned delivery.
This meeting
3
Note the escalation of Enrolment to red under the three-period amber rule
No decision required. Recorded so that the change is a matter of rule rather than of anyone's judgment, including mine.
Noting only
VitaFlow · Steering Committee · 15 October 2026
2
Notes: Take the decisions first. If the Committee agrees D-1 and D-2 in five minutes, the rest of the deck is context rather than persuasion.

## Slide 3
The program at a glance
Authorized $243,040,000 · 7.6 years to approval
$243,040,000
Authorized ceiling
1,684
Randomized of 2,480
0.94
Cost performance index
1
Areas outside target
Where the money goes
83% of this program is delivered by organizations that do not report to it — Meridian, Aldergate, Kestrel and 260 independent sites. The 17% spent on our own people buys the capability to direct the rest. That is why the levers available to this Committee are contractual and financial rather than operational.
VitaFlow · Steering Committee · 15 October 2026
3
Notes: The 83/17 split is the framing for everything that follows.

## Slide 4
Status by area
Green: on plan or a closed action. Amber: action in progress with a recovery date. Red: no action, or the action has failed. Amber for 3 periods turns red automatically.
Enrolment
1,684 randomized against a curve of 1,760 — 76 behind. Activation running 22 weeks against a planned 18.
4 periods at this status
CMC readiness
2 of 3 registration batches; 2 of 3 methods re-qualified; stability at 18 of 24 months. 3 of 7 Gate 5 CMC criteria assessed at risk.
2 periods at this status
Market access evidence
Two of five remaining advisory boards still unscheduled against the GC-03 plan.
2 periods at this status
Internal cost
CPI 0.939; forecast overrun on the internal labor envelope of $2,355,000.
1 periods at this status
Safety
214 SAEs; 3 seven-day and 41 fifteen-day expedited reports, 100% on time. IB at v4.
9 periods at this status
Regulatory
7 information requests answered; 0 major amendments; agreed iPSP in place.
6 periods at this status
Data management
18,400 queries raised, 6-day median close; 17 SAE discrepancies found, 0 open.
5 periods at this status
Governance
GC-02 closed 25 Sep. GC-01 and GC-03 open and within their due dates.
8 periods at this status
VitaFlow · Steering Committee · 15 October 2026
4
Notes: Enrolment went red on the three-period rule, not on my judgment. Say that.

## Slide 5
Enrolment is the red
76 participants behind curve. Activation running 22 weeks against a planned 18.
Chart: Cumulative randomizations against curve
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Plan | 420 | 545 | 675 | 810 | 950 | 1090 | 1230 | 1370 | 1500 | 1620 | 1700 | 1760
Actual | 412 | 528 | 648 | 772 | 898 | 1022 | 1148 | 1272 | 1392 | 1500 | 1596 | 1684
76
participants behind the curve at the status date
22 wks
site activation, against 18 planned — the origin of the shortfall
1 for 1
treatment is fixed at 68 weeks, so a month of enrolment slip is a month of filing slip
VitaFlow · Steering Committee · 15 October 2026
5
Notes: Do not let this become a discussion about trying harder.

## Slide 6
There is no lever that acts this quarter
The shortfall is structural, not an effort problem
1
Adding monitors
Does not activate a site faster. The delay is in contract execution and IRB review, neither of which a monitor touches.
2
Adding sites
Each new site carries the same 22-week activation lead time before it randomizes anybody. The effect lands in about five months.
3
Increasing screening
Screen-failure is flat at 40% and within plan. This is a site problem, not a screening problem.
The only lever with any effect is the reserve site list, and the recovery plan is forecast on it delivering half of what it promises — because that is what the first release actually delivered.
VitaFlow · Steering Committee · 15 October 2026
6
Notes: Expect a challenge on adding sites. The answer is the five-month lead time, not unwillingness.

## Slide 7
Financial position
Within ceiling. The number that matters is CPI, not spend against release.
Chart: Ceiling, released, spent (US$m)
| Ceiling | Released | Spent
US$m | 243 | 201.2 | 101
0.939
cost performance index on internal labor — every dollar buys 94 cents of budgeted work
$2,355,000
forecast overrun on the internal labor envelope. A revised EAC is decision D-1.
$16,990,000
contingency uncommitted of $26,040,000. Watch the rate, not the balance.
VitaFlow · Steering Committee · 15 October 2026
7
Notes: If asked why spend looks low against release: the tranche arrived in June.

## Slide 8
The early warning was eleven months ago
Leading indicators moved long before enrolment turned red on the status report
Chart: 
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Activation cycle time (weeks) | 18.5 | 19 | 19.4 | 20.1 | 20.3 | 21 | 21.4 | 21.8 | 22 | 22.1 | 22.3 | 22.4
Sites reaching green light (per month) | 9 | 8 | 8 | 7 | 7 | 6 | 6 | 5 | 6 | 5 | 5 | 4
Both crossed their thresholds in February and have deteriorated every month since. They sit about five months upstream of randomization — which is the interval by which the shortfall then followed them. The information was on the dashboard roughly a year before the milestone register could have shown it.
VitaFlow · Steering Committee · 15 October 2026
8
Notes: This is the slide that shows the warning was visible.

## Slide 9
Gate 5 readiness · 30 Sep 2028
CMC gates the filing independently of anything clinical
Registration batches
2 of 3 manufactured. Third scheduled within 30 days.
Analytical methods
2 of 3 re-qualified after the transfer failure. Method 3 re-run 30 Sep.
ICH stability
18 of 24 months elapsed. Runs on the calendar; cannot be compressed.
Process validation (PPQ)
Q1–Q2 2027. Needs registration batches, not stability data.
Clinical package
Gated by database lock, which is gated by last-participant-in.
Regulatory package
7 information requests answered, zero major amendments.
VitaFlow · Steering Committee · 15 October 2026
9
Notes: CMC is the independent path to the filing date.

## Slide 10
Next ninety days
What the Committee should expect to be asked at the next report
Next 30 days
Method 3 re-qualification report signed
Third registration batch manufactured
Two advisory boards scheduled against GC-03
Next 90 days
GC-01 due 18 December
Enrolment measurable against the revised curve
Contingency position re-tabled
Revised EAC reported against the new baseline
At the next report
Whether the shortfall has begun to consume float in the Phase 3 window
Whether the filing date still holds
Second reserve release effectiveness
VitaFlow · Steering Committee · 15 October 2026
10
Notes: Set the expectation that the filing-date question arrives next report.

## Slide 11
Decisions requested
D-1
Approve a revised estimate at completion for the internal labor envelope
This meeting
D-2
Authorize release of the second tranche of reserve sites (16 of 34)
This meeting
D-3
Note the escalation of Enrolment to red under the three-period amber rule
Noting only
This Committee cannot make a site activate faster. It can decide what the program is measured against, and whether to spend reserve on a recovery that is forecast to work half as well as planned.
Notes: Close on the ask. Do not reopen the enrolment discussion here.