## 1 What a WBS Is For
Rule | Statement | Why it matters
The 100% rule | The WBS captures 100% of the scope and nothing outside it | If work is not in the WBS it is not in the program. This is the test that makes a WBS useful rather than decorative.
Deliverable-oriented | Nodes are things, not activities | “Registration batches” not “manufacture batches”. Activities belong in the schedule; the WBS defines what is produced.
Mutually exclusive | No scope appears in two places | Overlap makes cost roll-up meaningless and creates two owners for one deliverable.
Decomposed to a manageable package | Assignable, estimable, trackable | Decomposition stops where a single owner can be held accountable for a discrete result.
Control accounts at Level 2 | Where scope, schedule and cost intersect | Each Level 2 node has one accountable owner and one budget.

## 2 Level 2 Control Accounts
WBS | Deliverable | Scope | Budget | % of base
1.1 | Nonclinical Package | Pharmacology, PK/ADME, safety pharmacology, GLP toxicology, genotoxicity | $8,500,000 | 3.9%
1.2 | CMC — Early Development | Route selection, formulation, analytical method development, clinical supply | $6,200,000 | 2.9%
1.3 | IND Package | Investigator's Brochure, Module 3/4 authoring, Form 1571, submission | $3,800,000 | 1.8%
1.4 | Phase 1 Clinical | Protocol, single site, 64 volunteers, PK/safety read-out, CSR | $8,500,000 | 3.9%
1.5 | Phase 2 Clinical | Dose-ranging, 480 participants, 36 weeks, dose selection for pivotal | $38,000,000 | 17.5%
1.6 | Phase 3 Clinical | Two pivotals plus CV sub-study, 2,480 randomized, 260 sites, 68 weeks | $109,100,000 | 50.3%
1.7 | CMC Scale-Up & Validation | Technology transfer, registration batches, PPQ, stability, method transfer | $9,200,000 | 4.2%
1.8 | NDA Preparation & Review | Integrated summaries, datasets, publishing, review response, inspection support | $12,400,000 | 5.7%
1.9 | Regulatory Affairs | Strategy, agency meetings, IND maintenance, labeling negotiation | $7,600,000 | 3.5%
1.10 | Program Management | Governance, planning, risk, reporting, gate packages, vendor oversight | $5,300,000 | 2.4%
1.11 | Advisors & Other | Regulatory counsel, scientific advisory board, user fees, insurance | $8,400,000 | 3.9%
| 1.0 Program total |  | $217,000,000 | 100.0%

## 3 Level 3 Complete Decomp (1)
WBS | Work package | Scope | Budget
1.1.1 | Primary pharmacology | Receptor binding, in vivo efficacy models | $1,100,000
1.1.2 | Safety pharmacology | Core battery — CNS, CV, respiratory | $900,000
1.1.3 | Pharmacokinetics & ADME | Absorption, distribution, metabolism, excretion | $1,400,000
1.1.4 | GLP repeat-dose toxicology | Rodent and non-rodent. Extended after the Pre-IND meeting — +$1.2M, +11 weeks | $3,200,000
1.1.5 | Genotoxicity | Ames, chromosomal aberration, in vivo micronucleus | $700,000
1.1.6 | Reproductive toxicology | Fertility, embryo-fetal development | $1,200,000
| 1.1 total |  | $8,500,000

## 3 Level 3 Complete Decomp (2)
WBS | Work package | Scope | Budget
1.2.1 | Route selection & process development | Synthetic route, scale demonstration, impurity profiling | $1,900,000
1.2.2 | Formulation development | Aqueous solution, excipient screening, pen compatibility | $1,300,000
1.2.3 | Analytical method development | Assay, purity, aggregation, identity — validated under ICH Q2 | $1,500,000
1.2.4 | Clinical supply, Phase 1–2 | GMP manufacture, labeling, distribution | $1,100,000
1.2.5 | Early stability | Supporting clinical use period only | $400,000
| 1.2 total |  | $6,200,000

## 3 Level 3 Complete Decomp (3)
WBS | Work package | Scope | Budget
1.3.1 | Investigator's Brochure | First edition; the expectedness yardstick | $400,000
1.3.2 | Module 3 authoring | Quality — safety of clinical supply | $900,000
1.3.3 | Module 4 authoring | Nonclinical study reports | $1,100,000
1.3.4 | Module 2 summaries | Overviews and summaries | $700,000
1.3.5 | Publishing & submission | eCTD assembly, Form 1571, gateway | $400,000
1.3.6 | Pre-IND meeting | Briefing package, meeting, minutes reconciliation | $300,000
| 1.3 total |  | $3,800,000

## 3 Level 3 Complete Decomp (4)
WBS | Work package | Scope | Budget
1.4.1 | Protocol & start-up | Single-site Phase 1 unit, IRB, contracting | $900,000
1.4.2 | Unit costs & conduct | 64 volunteers, 12 weeks, confinement periods | $4,800,000
1.4.3 | Bioanalysis | PK sample analysis, method validation | $1,200,000
1.4.4 | Data management & statistics | EDC, cleaning, PK/PD analysis | $800,000
1.4.5 | Clinical study report | ICH E3 CSR | $800,000
| 1.4 total |  | $8,500,000

## 3 Level 3 Complete Decomp (5)
WBS | Work package | Scope | Budget
1.5.1 | Protocol & start-up | Protocol, SAP, eCRF, IRT, country selection | $3,100,000
1.5.2 | Site activation | Contracting, IRB, initiation — 48 sites | $4,200,000
1.5.3 | Enrolment & conduct | 480 participants, 36 weeks, per-participant and site payments | $21,400,000
1.5.4 | Investigational supply | Manufacture, labeling, distribution, accountability | $3,300,000
1.5.5 | Data management & biostatistics | EDC, lock, analysis, TLFs | $3,600,000
1.5.6 | CSR & dose selection | Dose selection for the pivotal program — the Gate 3 deliverable | $2,400,000
| 1.5 total |  | $38,000,000

## 3 Level 3 Complete Decomp (6)
WBS | Work package | Scope | Budget
1.6.1 | Protocol & start-up | Protocol, SAP, eCRF, IRT build, country and site selection | $6,800,000
1.6.2 | Site activation | Contracting, IRB, regulatory documents, initiation — 260 sites | $11,400,000
1.6.3 | Enrolment & conduct | Per-participant costs, site payments, monitoring visits, central lab | $58,900,000
1.6.4 | Investigational supply | Manufacture, labeling, distribution, accountability, destruction — 41,600 kits | $9,300,000
1.6.5 | CV outcomes sub-study | CR-02 scope addition — 640 participants, adjudication committee | $7,200,000
1.6.6 | Data management & biostatistics | EDC, cleaning, coding, reconciliation, lock, analysis, TLFs | $8,600,000
1.6.7 | Safety & pharmacovigilance | Case processing, DMC, DSUR, signal detection | $4,100,000
1.6.8 | Clinical study reports | Two pivotal CSRs plus sub-study | $2,800,000
| 1.6 total |  | $109,100,000

## 3 Level 3 Complete Decomp (7)
WBS | Work package | Scope | Budget
1.7.1 | Technology transfer to Aldergate | Process transfer, engineering batches | $1,800,000
1.7.2 | Analytical method transfer | I-02 originated here — two of three methods failed first-pass acceptance | $900,000
1.7.3 | Registration batches | Three commercial-scale batches for the dossier | $2,400,000
1.7.4 | Process validation (PPQ) | Three consecutive qualification batches, media fills | $2,600,000
1.7.5 | Stability program | ICH Q1A long-term, accelerated, in-use, thermal cycling | $900,000
1.7.6 | Device design verification | Pen functional testing, human factors validation | $600,000
| 1.7 total |  | $9,200,000

## 3 Level 3 Complete Decomp (8)
WBS | Work package | Scope | Budget
1.8.1 | Integrated summaries | ISS and ISE — new analyses, not compilations | $3,900,000
1.8.2 | Datasets & define.xml | SDTM, ADaM, reviewer's guides | $2,400,000
1.8.3 | Module authoring & publishing | eCTD assembly and technical validation | $2,700,000
1.8.4 | Review response | Information requests, meetings, amendments | $2,100,000
1.8.5 | Inspection support | Mock inspections, storyboards, PAI support | $1,300,000
| 1.8 total |  | $12,400,000

## 3 Level 3 Complete Decomp (9)
WBS | Work package | Scope | Budget
1.9.1 | Regulatory strategy & planning | Pathway, designations assessed, geographic scope | $900,000
1.9.2 | Agency meetings | Four Type B meetings: packages, conduct, minutes | $1,300,000
1.9.3 | IND maintenance | 99 submissions — amendments, safety reports, annual reports | $1,600,000
1.9.4 | Labeling development & negotiation | Proposed labeling through to agreed text | $1,400,000
1.9.5 | Pediatric plan (PREA) | iPSP preparation, agreement, deferral negotiation | $700,000
1.9.6 | Regulatory operations & publishing | Submission management, gateway, archive | $1,700,000
| 1.9 total |  | $7,600,000

## 3 Level 3 Complete Decomp (10)
WBS | Work package | Scope | Budget
1.10.1 | Governance & gate management | Committee, gate packages, decision records | $1,200,000
1.10.2 | Planning & schedule control | WBS, schedule, baseline maintenance | $900,000
1.10.3 | Risk & issue management | RAID, conditions, contingency administration | $700,000
1.10.4 | Vendor oversight | CRO and CMO governance, KPI review, audits | $1,100,000
1.10.5 | Reporting & performance measurement | Dashboards, status reporting, EVM | $800,000
1.10.6 | Program closure | Handover, archive, closure report, team release | $600,000
| 1.10 total |  | $5,300,000

## 3 Level 3 Complete Decomp (11)
WBS | Work package | Scope | Budget
1.11.1 | Regulatory counsel | Thorne & Vale LLP | $1,400,000
1.11.2 | Scientific advisory board | External expert input at key decision points | $900,000
1.11.3 | PDUFA user fee | Statutory application fee, paid at submission | $4,300,000
1.11.4 | Insurance & indemnity | Clinical trial liability across eight countries | $1,100,000
1.11.5 | Translation & localization | Protocol, consent and labeling materials | $700,000
| 1.11 total |  | $8,400,000

## 5 Resource Model
Function | Headcount | Hours | % of roster | Scope | Note
Clinical Operations | 24 | 51,900 | 22.0% | Sites, monitoring, enrolment, clinical supply | Largest function. Scales with site count, not with program value — and it oversees a CRO rather than executing the trial itself.
Technical Operations / CMC | 16 | 30,200 | 14.7% | Process, analytical methods, scale-up, validation | Peaks late, when clinical is winding down. CMC gates the filing independently.
Clinical Development | 12 | 17,900 | 11.0% | Protocols, medical monitoring, clinical study reports | Small headcount, high rate — medical monitors are physicians.
Biostatistics & Data Management | 12 | 22,600 | 11.0% | SAP, EDC, database lock, analysis datasets | Under-resourced in most programs relative to what the filing actually needs.
Regulatory Affairs | 10 | 18,900 | 9.2% | Strategy, submissions, agency interaction, labeling | Highest blended rate in the program. Ten people carry every commitment made to the agency.
Pharmacovigilance & Drug Safety | 8 | 14,200 | 7.3% | Case processing, signal detection, DSUR | Carries an expedited-reporting clock that has no tolerance band.
Quality Assurance (GxP) | 7 | 12,800 | 6.4% | Audits, CAPA, GxP compliance, inspection readiness | Independent of every function it audits; the CQO reports to the CEO, not to this program.
Nonclinical Safety & Pharmacology | 5 | 9,400 | 4.6% | Toxicology, pharmacology, study oversight | Front-loaded — near zero after Gate 2, which is why headcount alone misstates its importance.
Program Management Office | 4 | 7,200 | 3.7% | Governance, planning, risk, reporting | 3.7% of headcount coordinating the other 96.3%.
Market Access & Commercial | 4 | 5,000 | 3.7% | Payer evidence, pricing, launch readiness | Joint-smallest, latest to staff, and lowest hours per head — while carrying the longest-lead assumption in the business case.
Total | 109 | 191,420 | 100%

## 7 How This WBS Is Used
Use | How
Scope control | New work must be assigned a WBS node. Work that fits no node is a change, and goes to change control rather than into someone's week.
Cost roll-up | Actuals are booked to work packages and roll to control accounts and to the program. The budget and this structure are the same numbers.
Schedule development | Activities are derived from work packages, not invented alongside them. The schedule decomposes 1.x nodes into sequenced activities with durations.
Responsibility assignment | Each control account has one accountable owner. The RACI matrix maps functions to nodes.
Risk association | Every risk in the RAID Log attaches to a WBS node, so exposure can be read by deliverable rather than only by register.
Contingency reasoning | A draw is assessed against the node it protects. CR-02 sits at 1.6.5; I-02 at 1.7.

## About
Work Breakdown Structure
Vitalis Therapeutics Inc. · VitaFlow (VTX-401) · Work Breakdown Structure · status 15 October 2026. Fictional program.
Generated from the published artifact. Figures derive from a single locked fact base that asserts its own arithmetic on load.