ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-001  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-001 | Date Submitted | 20 Jul 2026 |
| --- | --- | --- | --- |
| Submitted By | C. Tyrrell | Role | Program Manager |
| Category | Schedule | Priority | Low |

2. Change Description

Add a formal Project Kickoff Meeting to the WBS.

The original WBS transitioned directly from Charter approval into Requirements Gathering with no formal kickoff. This risked misaligned stakeholder expectations at the very start of the program.

3. Justification / Expected Benefit

A formal kickoff aligns the Steering Committee, sponsors, and delivery team on scope, goals, and ways of working before detailed work begins.

4. Impact Assessment

| Schedule Impact | +1 days |
| --- | --- |
| Cost Impact | $0 |
| Scope Detail | None |
| Quality Impact | None |
| Risk Impact | Low — reduces early stakeholder misalignment risk |

5. Financial Impact

Budgetary Impact of This Change: No budgetary impact ($0)

6. Alternatives Considered

Informal kickoff via email — rejected, insufficient for stakeholder alignment on a $7M program.

7. Recommendation

Approve

8. Outcome If Approved

Kickoff meeting is added to Day 0 of the schedule. Steering Committee, sponsors, and the delivery team are formally aligned on scope, goals, and working norms before Requirements Gathering begins.

9. Outcome If Not Approved

Program proceeds directly into Requirements Gathering with no formal alignment session. The 1-day schedule saving is retained, but the risk of early stakeholder misunderstanding about scope and goals goes unaddressed.

10. Decision & Approval

| Approval Authority | PM (informational) | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 22 Jul 2026 |  |  |

_________________________________          Date: ____________

C. Tyrrell, Program Manager — Signature (delegated approval authority per PM Plan §16)

11. Documents Updated

WBS

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-002  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-002 | Date Submitted | 25 Jul 2026 |
| --- | --- | --- | --- |
| Submitted By | F. Jones | Role | Lead Business Analyst |
| Category | Schedule | Priority | Medium |

2. Change Description

Add a walkthrough + 3-day feedback + recirculation + 3-day sign-off pattern to both the Requirements and Design gates.

The original WBS had single-pass approval with no allowance for stakeholder feedback cycles, creating rework risk if requirements or design were rejected without a defined revision path.

3. Justification / Expected Benefit

Reduces the risk of late-stage requirement disputes; a defined feedback cycle is standard practice for gate reviews on a program this size.

4. Impact Assessment

| Schedule Impact | +6 days |
| --- | --- |
| Cost Impact | $0 |
| Scope Detail | None |
| Quality Impact | Improves — catches misunderstandings before Build begins |
| Risk Impact | Reduces Medium risk of downstream rework |

5. Financial Impact

Budgetary Impact of This Change: No budgetary impact ($0)

6. Alternatives Considered

Keep single-pass approval (status quo) — rejected, high rework risk if a gate is contested.

7. Recommendation

Approve

8. Outcome If Approved

Both the Requirements and Design gates gain a structured walkthrough, 3-day feedback window, recirculation, and 3-day sign-off cycle. Total schedule impact: +6 days.

9. Outcome If Not Approved

Gates remain single-pass approval. The 6-day schedule saving is retained, but any rejected requirement or design would trigger unplanned rework with no defined recovery path — elevating the risk of hidden schedule slippage later in the program.

10. Decision & Approval

| Approval Authority | Steering Committee | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 28 Jul 2026 |  |  |

_________________________________          Date: ____________

G. Whitfield, Executive Sponsor — Signature

_________________________________          Date: ____________

S. Ryan, Change Control Board Representative (on behalf of the Steering Committee) — Signature

11. Documents Updated

WBS, PM Plan

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-003  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-003 | Date Submitted | 05 Aug 2026 |
| --- | --- | --- | --- |
| Submitted By | W. Donnelly | Role | Vendor/Procurement Manager |
| Category | Scope | Priority | Medium |

2. Change Description

Add explicit RFP drafting and SOW finalization subtasks to the vendor selection tracks.

The original WBS jumped straight from “Issue RFP” to “Vendor Selected” with no visible document-creation steps, understating real procurement effort.

3. Justification / Expected Benefit

Makes procurement effort visible and estimable, protecting schedule integrity for the vendor selection window.

4. Impact Assessment

| Schedule Impact | No change |
| --- | --- |
| Cost Impact | $0 |
| Scope Detail | Adds 2 explicit subtasks (Draft RFP, Draft/Finalize SOW) — no change to overall program scope |
| Quality Impact | N/A |
| Risk Impact | Low — improves estimating accuracy |

5. Financial Impact

Budgetary Impact of This Change: No budgetary impact ($0)

6. Alternatives Considered

Leave procurement drafting implicit — rejected, hides real effort from the schedule.

7. Recommendation

Approve

8. Outcome If Approved

Two explicit subtasks (Draft RFP, Draft/Finalize SOW) are added to the WBS, making real procurement effort visible without changing overall program scope.

9. Outcome If Not Approved

Procurement drafting effort remains implicit in the schedule. No visible schedule change, but estimating accuracy for vendor selection stays understated, risking a false sense of schedule buffer during Phase 1.

10. Decision & Approval

| Approval Authority | PM (informational) | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 06 Aug 2026 |  |  |

_________________________________          Date: ____________

C. Tyrrell, Program Manager — Signature (delegated approval authority per PM Plan §16)

11. Documents Updated

WBS, PM Plan

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-004  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-004 | Date Submitted | 12 Aug 2026 |
| --- | --- | --- | --- |
| Submitted By | R. Whitfield | Role | QA/Test Lead, Onshore |
| Category | Quality / Schedule | Priority | High |

2. Change Description

Add Security & Penetration Testing, system-wide Performance/Load Testing, and DR/Failover Testing to the Testing phase.

The original Testing phase covered functional, system, and UAT testing only — it omitted security, performance, and disaster-recovery testing, a significant gap for a platform handling PII and financial transactions.

3. Justification / Expected Benefit

Required for a system processing financial transactions and PII; reduces the risk of a post-go-live security or performance incident.

4. Impact Assessment

| Schedule Impact | +12 days |
| --- | --- |
| Cost Impact | +$45,000 |
| Scope Detail | Adds 3 new testing workstreams to Phase 5 |
| Quality Impact | Significantly improves — closes a major testing gap |
| Risk Impact | Reduces High risk of a post-go-live security or performance incident |

5. Financial Impact

Budgetary Impact of This Change: +$45,000

6. Alternatives Considered

Defer to a post-go-live hardening sprint — rejected, unacceptable risk for a live financial system.

7. Recommendation

Approve

8. Outcome If Approved

Security & Penetration Testing, system-wide Performance/Load Testing, and DR/Failover Testing are added to Phase 5. Schedule impact: +12 days. Cost impact: +$45,000 (external penetration testing vendor and performance testing tooling).

9. Outcome If Not Approved

Testing phase remains functional/system/UAT only. The platform would go live without security, performance, or DR validation — a significant and, for a system handling PII and financial transactions, likely unacceptable risk exposure at Go-Live.

10. Decision & Approval

| Approval Authority | Steering Committee | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 15 Aug 2026 |  |  |

_________________________________          Date: ____________

G. Whitfield, Executive Sponsor — Signature

_________________________________          Date: ____________

S. Ryan, Change Control Board Representative (on behalf of the Steering Committee) — Signature

11. Documents Updated

WBS, PM Plan

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-005  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-005 | Date Submitted | 20 Aug 2026 |
| --- | --- | --- | --- |
| Submitted By | C. Tyrrell | Role | Program Manager |
| Category | Schedule / Cost | Priority | Medium |

2. Change Description

Add a 3-week vendor Warranty Support period, Legacy System Decommissioning, and a formal Production Support Transition ahead of Closeout.

The original WBS moved directly from Go-Live to Closeout with no vendor warranty period, no legacy decommissioning tasks, and no formal support handover — leaving post-go-live defects and legacy system costs unaddressed.

3. Justification / Expected Benefit

Protects against early-life defects without additional emergency spend; ensures legacy systems are properly retired and support responsibilities are clearly handed over.

4. Impact Assessment

| Schedule Impact | +21 days |
| --- | --- |
| Cost Impact | +$85,000 |
| Scope Detail | Adds Warranty, Decommissioning, and Transition workstreams to Phase 6 |
| Quality Impact | Improves post-go-live stability |
| Risk Impact | Reduces Medium risk of unsupported early-life defects |

5. Financial Impact

Budgetary Impact of This Change: +$85,000

6. Alternatives Considered

Time-and-materials post-go-live support with no warranty — rejected, unpredictable cost exposure.

7. Recommendation

Approve

8. Outcome If Approved

A 3-week vendor Warranty Support period, Legacy System Decommissioning, and a formal Production Support Transition are added ahead of Closeout. Schedule impact: +21 days. Cost impact: +$85,000 (vendor warranty fee and decommissioning labor).

9. Outcome If Not Approved

Program moves directly from Go-Live to Closeout. Any early-life defects would require unbudgeted emergency support, and legacy systems would continue accruing cost indefinitely with no formal decommissioning plan.

10. Decision & Approval

| Approval Authority | Steering Committee | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 22 Aug 2026 |  |  |

_________________________________          Date: ____________

G. Whitfield, Executive Sponsor — Signature

_________________________________          Date: ____________

S. Ryan, Change Control Board Representative (on behalf of the Steering Committee) — Signature

11. Documents Updated

WBS, PM Plan, RAIDD Log

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-006  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-006 | Date Submitted | 28 Aug 2026 |
| --- | --- | --- | --- |
| Submitted By | N. Sharma | Role | Compliance / Legal Representative |
| Category | Compliance | Priority | High |

2. Change Description

Add a SOX Control Impact Assessment and pre-go-live SOX compliance testing and sign-off.

The program touches financial systems (Billing, Payment Processing, Commission Management) subject to SOX controls; the original scope had no formal SOX assessment or testing gate.

3. Justification / Expected Benefit

Legally required for financial-system changes at a public company; avoids audit findings and regulatory exposure.

4. Impact Assessment

| Schedule Impact | +8 days |
| --- | --- |
| Cost Impact | +$60,000 |
| Scope Detail | Adds a SOX assessment and compliance testing workstream |
| Quality Impact | N/A directly, but reduces audit/compliance risk |
| Risk Impact | Reduces High risk of a SOX audit finding |

5. Financial Impact

Budgetary Impact of This Change: +$60,000

6. Alternatives Considered

Assess SOX impact post-go-live — rejected, unacceptable regulatory risk for a public company.

7. Recommendation

Approve

8. Outcome If Approved

A SOX Control Impact Assessment and pre-go-live compliance testing/sign-off are added. Schedule impact: +8 days. Cost impact: +$60,000 (compliance/audit labor and external SOX assessment support). Program demonstrates compliance readiness for financial-system changes.

9. Outcome If Not Approved

Program proceeds without a formal SOX assessment. This exposes ACME Company to potential audit findings and regulatory risk post-go-live, given the platform's handling of Billing, Payment Processing, and Commission Management.

10. Decision & Approval

| Approval Authority | Steering Committee | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 29 Aug 2026 |  |  |

_________________________________          Date: ____________

G. Whitfield, Executive Sponsor — Signature

_________________________________          Date: ____________

S. Ryan, Change Control Board Representative (on behalf of the Steering Committee) — Signature

11. Documents Updated

WBS, PM Plan, RAIDD Log, Resource Register

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-007  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-007 | Date Submitted | 02 Sep 2026 |
| --- | --- | --- | --- |
| Submitted By | R. Whitfield | Role | QA/Test Lead, Onshore |
| Category | Resource | Priority | Medium |

2. Change Description

Add an Offshore QA Coordination Lead role and split onshore/offshore QA execution responsibilities.

The original resource plan assumed a single onshore QA team; testing volume and timeline require additional offshore QA capacity with dedicated coordination to manage handoffs across time zones.

3. Justification / Expected Benefit

Increases QA throughput without extending the Testing phase; manages time-zone handoff risk explicitly rather than informally.

4. Impact Assessment

| Schedule Impact | No change |
| --- | --- |
| Cost Impact | +$120,000 |
| Scope Detail | Adds 1 new role to the Resource Register |
| Quality Impact | Improves — dedicated coordination reduces handoff defects |
| Risk Impact | Reduces Medium risk of QA throughput shortfall |

5. Financial Impact

Budgetary Impact of This Change: +$120,000

6. Alternatives Considered

Onshore-only QA scale-up — rejected, higher cost and slower to staff.

7. Recommendation

Approve

8. Outcome If Approved

An Offshore QA Coordination Lead role is added and onshore/offshore QA execution responsibilities are formally split. Cost impact: +$120,000 (new offshore FTE across the program engagement window). No schedule impact — adds capacity in parallel.

9. Outcome If Not Approved

QA remains onshore-only. Testing throughput may fall short of what's needed for the Testing phase timeline, risking schedule pressure or reduced test coverage under time constraints.

10. Decision & Approval

| Approval Authority | PM (informational) | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 03 Sep 2026 |  |  |

_________________________________          Date: ____________

C. Tyrrell, Program Manager — Signature (delegated approval authority per PM Plan §16)

11. Documents Updated

WBS, PM Plan, Resource Register

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-008  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-008 | Date Submitted | 10 Sep 2026 |
| --- | --- | --- | --- |
| Submitted By | C. Tyrrell | Role | Program Manager |
| Category | Compliance / Cost / Stakeholder | Priority | Medium |

2. Change Description

Add a Data Privacy/PII Assessment, formal Cost Baseline approval, external Customer Communications, and Post-Go-Live CX Monitoring — all scheduled in parallel.

Several cross-cutting workstreams were identified as missing during PM Plan v2.0 development: a formal privacy/PII assessment (given member/policy data conversion), a formally-approved cost baseline for EVM tracking, and customer-facing communications and monitoring around the cutover.

3. Justification / Expected Benefit

Closes a privacy compliance gap, establishes a defensible cost baseline, and protects customer experience through a major system transition.

4. Impact Assessment

| Schedule Impact | No change |
| --- | --- |
| Cost Impact | +$95,000 |
| Scope Detail | Adds 4 parallel workstreams |
| Quality Impact | N/A directly; improves customer experience outcomes |
| Risk Impact | Reduces Medium risk across privacy, cost governance, and customer satisfaction |

5. Financial Impact

Budgetary Impact of This Change: +$95,000

6. Alternatives Considered

Handle informally without dedicated workstreams — rejected, insufficient accountability for cross-cutting concerns.

7. Recommendation

Approve

8. Outcome If Approved

Four parallel workstreams are added: Data Privacy/PII Assessment, formal Cost Baseline approval, external Customer Communications, and Post-Go-Live CX Monitoring. Cost impact: +$95,000. No schedule impact — scheduled fully in parallel with existing work.

9. Outcome If Not Approved

Privacy compliance for the data conversion remains unassessed, no formally-approved cost baseline exists for EVM tracking, and customer experience through the cutover is not actively managed — leaving three distinct governance gaps unaddressed.

10. Decision & Approval

| Approval Authority | Steering Committee | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 12 Sep 2026 |  |  |

_________________________________          Date: ____________

G. Whitfield, Executive Sponsor — Signature

_________________________________          Date: ____________

S. Ryan, Change Control Board Representative (on behalf of the Steering Committee) — Signature

11. Documents Updated

WBS, PM Plan, Resource Register

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-009  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-009 | Date Submitted | 15 Jul 2026 |
| --- | --- | --- | --- |
| Submitted By | C. Tyrrell | Role | Program Manager |
| Category | Governance | Priority | High |

2. Change Description

Formalize Steering Committee membership and decision-rights tiering.

The program lacked a named governance body at Charter approval; decisions were being made ad hoc between the PM and Sponsor with no formal escalation or approval structure.

3. Justification / Expected Benefit

Establishes clear decision authority for scope, budget, and schedule changes — required before any subsequent change request could be properly authorized.

4. Impact Assessment

| Schedule Impact | No change |
| --- | --- |
| Cost Impact | $0 |
| Scope Detail | Governance/process only — no deliverable scope change |
| Quality Impact | N/A |
| Risk Impact | Reduces High risk of governance ambiguity and unauthorized scope changes |

5. Financial Impact

Budgetary Impact of This Change: No budgetary impact ($0)

6. Alternatives Considered

Informal sponsor check-ins — rejected, insufficient accountability for a $7M program.

7. Recommendation

Approve

8. Outcome If Approved

The Steering Committee is formally established with named members and decision-rights tiering. No cost or schedule impact.

9. Outcome If Not Approved

Program continues without a named governance body. Decisions on scope, budget, and schedule changes would lack a clear, authorized approval path — a significant governance risk for a $7M program, and would call into question the validity of any subsequent change request's approval authority.

10. Decision & Approval

| Approval Authority | Executive Sponsor | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 18 Jul 2026 |  |  |

_________________________________          Date: ____________

G. Whitfield, Executive Sponsor — Signature

11. Documents Updated

PM Plan, RAIDD Log

ACME Company · Enrollment & Claims Platform Modernization

Change Request Document

Form No. CR-010  ·  Rev. 1.0

Status: Implemented

1. Request Information

| CR Number | CR-010 | Date Submitted | 15 Sep 2026 |
| --- | --- | --- | --- |
| Submitted By | E. Kowalski | Role | PMO/Governance Analyst |
| Category | Resource | Priority | Medium |

2. Change Description

Split the combined Change/Training role into distinct Change Manager and Training Lead roles; add Customer Experience Manager and Internal Audit/SOX Compliance Lead.

The original resource plan bundled Change Management and Training into a single role and had no dedicated Internal Audit/SOX resource despite CR-006's compliance scope; the CX Manager added under CR-008 needed formal resourcing.

3. Justification / Expected Benefit

A single combined Change/Training role was unrealistic given program scale; SOX scope requires a dedicated audit resource, not a shared one.

4. Impact Assessment

| Schedule Impact | No change |
| --- | --- |
| Cost Impact | +$310,000 |
| Scope Detail | Adds/splits 4 roles in the Resource Register |
| Quality Impact | N/A |
| Risk Impact | Reduces Medium risk of role overload and compliance coverage gaps |

5. Financial Impact

Budgetary Impact of This Change: +$310,000

6. Alternatives Considered

Keep the combined role and add contractor surge support only for SOX — rejected, insufficient continuity for either function.

7. Recommendation

Approve

8. Outcome If Approved

The combined Change/Training role is split into Change Manager and Training Lead; Customer Experience Manager and Internal Audit/SOX Compliance Lead are added. Cost impact: +$310,000 (four incremental/adjusted FTE costs across their respective engagement windows).

9. Outcome If Not Approved

A single combined Change/Training resource would remain overloaded relative to program scale, and SOX compliance testing (CR-006) would lack a dedicated audit resource — risking coverage gaps in both change management and compliance testing.

10. Decision & Approval

| Approval Authority | PM (informational) | Decision | Approved |
| --- | --- | --- | --- |
| Date Decided | 16 Sep 2026 |  |  |

_________________________________          Date: ____________

C. Tyrrell, Program Manager — Signature (delegated approval authority per PM Plan §16)

11. Documents Updated

Resource Register, WBS, PM Plan