CHANGE CONTROL LOG

Enrollment & Claims Platform Modernization

Prepared by: C. Tyrrell, Program Manager

Version 1.0  |  Draft

Date: July 27, 2026

This document is illustrative and fictional, created for professional portfolio demonstration purposes only.

# Purpose

This Change Control Log records every formal change request made against the program's baselines (scope, schedule, cost) since Project Management Plan approval. It is the authoritative record of what changed, why, who approved it, and — critically for a program with this many interdependent artifacts — which other program documents were updated as a result.

Approval authority for each change follows the decision-rights tiering defined in the Project Management Plan, Section 16 (Governance & Decision Authority): task-level sequencing changes may be approved by the Program Manager directly, while any change affecting a phase-gate milestone, the cost baseline, or a contractual/compliance obligation requires Steering Committee approval.

# Change Log

| CR ID | Title | Category | Impact Summary | Approval Authority | Documents Updated | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CR-001 | Add Project Kickoff Meeting | Schedule | Formal kickoff was missing between Charter sign-off and Requirements Gathering; adds 1 day. | PM (informational) | WBS | Implemented |
| CR-002 | Formalize Requirements & Design Sign-off cycles | Schedule | Added walkthrough + 3-day feedback + recirculation + 3-day sign-off pattern to both gates; adds 6 days total. | Steering Committee | WBS, PM Plan | Implemented |
| CR-003 | Add explicit RFP drafting & SOW finalization tasks | Scope | Vendor selection tracks lacked visible document-creation steps; added Draft RFP and Draft/Finalize SOW subtasks. | PM (informational) | WBS, PM Plan | Implemented |
| CR-004 | Add Security, Performance, and DR testing | Quality / Schedule | Testing phase lacked Security & Penetration Testing, system-wide Performance/Load Testing, and DR/Failover Testing. | Steering Committee | WBS, PM Plan | Implemented |
| CR-005 | Add Warranty Support & Legacy Decommissioning | Schedule / Cost | Added 3-week vendor Warranty period, Legacy System Decommissioning, and formal Production Support Transition before Closeout. | Steering Committee | WBS, PM Plan, RAIDD Log | Implemented |
| CR-006 | Add SOX Control Impact Assessment & Compliance Testing | Compliance | Program touches financial systems (Billing, Payment, Commission); added SOX assessment and pre-go-live control testing/sign-off. | Steering Committee | WBS, PM Plan, RAIDD Log, Resource Register | Implemented |
| CR-007 | Add offshore QA Coordination role & dual-shore model | Resource | Added Offshore QA Coordination Lead and split onshore/offshore QA execution responsibilities. | PM (informational) | WBS, PM Plan, Resource Register | Implemented |
| CR-008 | Add Privacy Assessment, Cost Baseline, and CX tracks (parallel) | Compliance / Cost / Stakeholder | Added Data Privacy/PII Assessment, Cost Baseline approval, external Customer Communications, and Post-Go-Live CX Monitoring — all scheduled in parallel with no net schedule impact. | Steering Committee | WBS, PM Plan, Resource Register | Implemented |
| CR-009 | Establish Steering Committee governance structure | Governance | Formalized program governance with a named Steering Committee and decision-rights tiering. | Executive Sponsor | PM Plan, RAIDD Log | Implemented |
| CR-010 | Expand Resource Register (Change Mgr, Training Lead, CX Mgr, SOX Lead) | Resource | Split combined change/training role into distinct Change Manager and Training Lead; added Customer Experience Manager and Internal Audit/SOX Compliance Lead. | PM (informational) | Resource Register, WBS, PM Plan | Implemented |

# How to Use This Log

- Every change request receives a sequential CR ID and is logged here regardless of whether it is ultimately approved, deferred, or rejected.

- The "Documents Updated" column exists specifically because this program's artifacts are interdependent — a single approved change (e.g., adding SOX testing) typically requires corresponding updates to the WBS, the Project Management Plan, the RAIDD Log, and sometimes the Resource Register in the same change cycle.

- Change requests that are still pending Steering Committee review are not implemented in any downstream document until formally approved.