## Slide 1
PROGRAM KICKOFF
Enrollment & Claims
Platform Modernization
Twelve months. Six integrations. One modern platform. Here's how we get there, together.
August 4, 2026
Kickoff Date
C. Tyrrell
Program Manager
20
Team Members
1

## Slide 2
AGENDA
What We'll Cover Today
1
Welcome & Introductions
2
Why This Program Matters
3
Objectives & Success Criteria
4
Scope: In and Out
5
Team & Organization
6
Timeline & Milestones
7
Budget Overview
8
How We'll Work Together
9
Risks We're Watching
10
Next Steps & Q&A
2

## Slide 3
WELCOME
Glad You're Here
Today, twenty people from nine disciplines become one team with one deadline.
Over the next 12 months we'll replace the legacy enrollment and claims platform with something faster, cleaner, and built to last — Program Management, Architecture, Data Conversion, QA, Change Management, Compliance, and Executive Sponsorship, all pulling the same direction. Quick round of introductions: name, role, and what you're most excited (or nervous) about.
20
NAMED TEAM MEMBERS
12
MONTHS TO GO-LIVE
6
MAJOR INTEGRATIONS
3

## Slide 4
THE BUSINESS CASE
Why We're Doing This
Every workaround we've patched onto the legacy platform is a little more risk we're carrying forward.
Six critical business integrations run today on aging, brittle connections. This program upgrades the core platform, converts our data with full accuracy, and rebuilds all six integrations clean — full detail lives in the Program Charter.
$7.062M
APPROVED BUDGET
Aug '27
TARGET GO-LIVE
4

## Slide 5
OBJECTIVES
What Success Looks Like
1
Zero unplanned extended outages during cutover
2
≥ 99.5% record-level accuracy on data conversion
3
All 6 integrations fully tested before Go-Live
4
On budget, on schedule — $7.062M, Aug 2027
5
Zero open Critical/High security findings at Go-Live
Full detail: Project Charter
5

## Slide 6
SCOPE
Where the Lines Are
IN SCOPE
Core platform version upgrade
Data conversion: member/policy, provider/producer, historical claims
6 new integrations: Billing, Underwriting, Claims Admin, Commission Mgmt, Data Warehouse, Payment Processing
Security, performance, DR testing; SOX impact assessment
Change management, training, hypercare/warranty period
OUT OF SCOPE
Data migration outside the workstreams above
Ongoing production support beyond the vendor warranty period
New product or underwriting-rules changes not required by the upgrade
6

## Slide 7
TEAM
Everyone Who's In the Room
C. Tyrrell
Program Manager
F. Jones
Lead Business Analyst
J. Albert
Solution Architect
DELIVERY & QA LEADS
M. Alvarez
System Upgrade Lead
T. McCormick
Data Conversion Lead
R. Whitfield
QA / Test Lead
P. Sundaram
Offshore QA Contributor
INTEGRATION DEVELOPERS
D. Okafor
Billing
S. Lindqvist
Underwriting
K. Delgado
Claims Admin
P. Novak
Commission Mgmt
A. Reyes
Data Warehouse
B. Sato
Payment Processing
CHANGE, TRAINING & CX
L. Bergström
Change Mgr (OCM Lead)
H. Osei
Training Lead
V. Alaoui
Customer Exp. Mgr
COMPLIANCE, AUDIT & PMO
N. Sharma
Compliance / Legal
G. Fenwick
Internal Audit / SOX
W. Donnelly
Vendor / Procurement
E. Kowalski
PMO / Governance
All 20 named leads, same as the Resource Plan and Org Chart — nobody on this program is a name you'll only find in a spreadsheet.
7

## Slide 8
TIMELINE
The Road to Go-Live
Kickoff
Aug 4
Requirements Complete
Nov 3
System Upgrade Validated
Jan 5
Data Conversion Sign-off
Mar 16
Integration Build Complete
May 11
UAT Sign-off
Aug 10
Go-Live
Aug 24 '27
Full interactive schedule: WBS/Gantt Console
8

## Slide 9
BUDGET
Where the Money Goes
Chart: 
| Labor (Named Leads + Team) | Vendor/Licensing | Contingency Reserve | Infrastructure/Other
Budget | 63 | 20 | 10 | 7
$7.062M
TOTAL BUDGET
The contingency reserve grows with the budget as changes are approved — it doesn't sit fixed while scope moves around it.
Full detail, the 20-person rate card, and reconciliation: Program Budget
9

## Slide 10
WORKING TOGETHER
How We'll Stay in Sync
Cadence | Forum | Purpose
Weekly | Program Status Review | Schedule, budget, RAIDD review
Monthly | Steering Committee | Executive update, decisions requested
As needed | Change Control Board | Any Tier 2/3 scope, cost, or schedule change
Full governance model, decision rights, and escalation path: Program Governance Model
10

## Slide 11
EYES OPEN
Risks We're Watching From Day One
!
Historical claims data quality could extend Data Conversion
Highest-rated risk at Charter approval
!
Platform vendor SOW finalization delay
Could push back environment provisioning
!
Offshore/onshore QA coordination gaps
Could reduce testing throughput if not actively managed
!
Key resource attrition (Solution Architect capacity)
Could disrupt technical decision continuity
Full risk register: RAIDD Log
11

## Slide 12
NEXT STEPS
What Happens Next
1
Detailed WBS and schedule baseline finalized within 2 weeks
2
Legacy data assessment kickoff for all six integration areas
3
First Steering Committee update scheduled for early September
12

## Slide 13
Let's Build Something Better.
C. Tyrrell, Program Manager
Enrollment & Claims Platform Modernization
13