## Lessons Learned
Lessons Learned Register
Per PMBOK/PRINCE2: what happened, why it happened (root cause), impact, and a specific recommendation -- not a single vague "lesson" field.
ID | Category | Phase | What Happened | Root Cause | Impact | Recommendation | Owner | Status | Target/Implementation | Keywords
LL-01 | Data Quality | Initiation / Requirements | Historical claims data quality issues (duplicate records, inconsistent formatting) were not identified until Data Conversion planning began in Phase 3, several months after Requirements sign-off. | No formal data quality assessment was performed during Initiation; the WBS assumed clean source data based on the legacy system's documentation, which had not been validated against actual production data. | Contributed to R-001 (Score 9, High/High). $150,000 of contingency was pre-approved for a possible third Data Conversion Dry Run (D-002), plus additional data profiling effort added to Phase 3. | Conduct a formal data quality assessment during Initiation for any program involving legacy data conversion -- profile a representative sample of source data before finalizing the schedule baseline, not after. | T. McCormick | Implemented | Adopted into PMO Initiation checklist | data quality, data conversion, legacy migration, risk identification
LL-02 | Governance | Initiation | The program began Requirements Gathering before a Steering Committee was formally established, leaving no defined decision-making body for the first several weeks. | Charter approval did not require governance structure sign-off as a precondition for starting execution work. | Approximately 3 weeks of decision-authority ambiguity; two early scope questions were resolved informally between the PM and Sponsor without a documented governance trail. | Require Steering Committee membership and decision-rights tiering to be finalized and documented as part of Charter approval itself, not as a follow-on change request. | C. Tyrrell | Implemented | Charter template updated | governance, steering committee, decision rights, charter
LL-03 | Compliance | Planning | Security, performance, and disaster-recovery testing were absent from the original Testing phase scope, discovered during PM Plan development rather than during initial scope definition. | The original scope was drafted by functional business stakeholders without formal input from Compliance or Security functions at the Requirements stage. | +12 days to the Testing phase and +$45,000 in cost, identified late enough to require a formal change request rather than being absorbed into the original baseline. | For any program touching regulated data (PII, financial transactions), require formal Compliance and Security sign-off on the Testing scope during Planning, before the schedule and cost baseline are set. | R. Whitfield | Implemented | Planning checklist updated | security testing, compliance, SOX, scope gap
LL-04 | Resourcing | Execution (Testing) | Onshore-only QA staffing proved insufficient for the testing volume once the Testing phase began, requiring a mid-program addition of offshore QA capacity. | Original resource planning did not stress-test QA throughput against the full six-integration testing scope; capacity was planned against an earlier, smaller draft of the integration count. | +$120,000 for the new Offshore QA Coordination Lead role and offshore team. No net schedule impact -- the change added capacity in parallel -- but required an unplanned resourcing change mid-execution. | Stress-test QA/testing capacity against the FINAL, fully-scoped testing plan before baselining the resource plan, not against an early, potentially-incomplete scope draft. | P. Sundaram | Implemented | Resource planning template updated | QA capacity, offshore, resourcing, testing throughput
LL-05 | Vendor Management | Execution (Integration Build) | The vendor-provided test environment initially lacked production-representative data volume, delaying the start of meaningful integration testing. | The vendor SOW specified a test environment but did not specify minimum data volume or representativeness requirements. | Approximately 1-2 weeks of delayed/reduced-value integration testing before the vendor provisioned an expanded environment; no net schedule impact since it was absorbed by schedule float. | Vendor SOWs for system integration programs should explicitly specify test environment data volume and representativeness requirements as a contractual line item, not an assumed default. | W. Donnelly | Implemented | SOW template updated | vendor management, SOW, test environment, data volume
LL-06 | Risk Management | Execution (Data Conversion) | When early signs suggested R-001 might require a third Data Conversion Dry Run, the Steering Committee approved $150,000 in contingency utilization within days, without a lengthy new-request cycle. | A contingency drawdown threshold had been pre-authorized when R-001 was first identified, rather than waiting for the risk to fully materialize before seeking approval. | Positive -- avoided what could have been a multi-week delay waiting for a new funding request and Steering Committee cycle, had the third Dry Run actually been needed. | For any High-scored risk (RAIDD score >=7), pre-authorize a specific contingency response threshold at the time the risk is identified, rather than waiting for a formal escalation if/when it materializes. | C. Tyrrell | Implemented | Now standard practice in Project Governance Model §8 | risk management, contingency, pre-authorization, positive practice
LL-07 | Change Management | Execution | The originally-combined Change Manager/Training Lead role was split into two distinct roles after the incumbent showed signs of overload managing both functions simultaneously. | The original Resource Register combined Change Management and Training into a single role without validating the combined workload against the program's actual training and communications volume. | +$310,000 for the expanded Resource Register (including CX Manager and SOX Compliance Lead roles added under the same change); approximately 2-3 weeks of reduced Change Management output during the transition. | Scope Organizational Change Management and Training as distinct roles from the outset for programs of this scale, rather than combining by default and splitting only after strain becomes visible. | L. Bergström | Implemented | PMO resourcing guidance updated | change management, training, role design, resourcing
LL-08 | Schedule | Planning | A structured feedback-and-recirculation window was added to the Requirements and Design gates before either gate was actually contested. | The original WBS had single-pass approval with no allowance for stakeholder feedback cycles; this was identified as a risk during PM Plan development, before it caused an actual problem. | Positive -- added 6 days to the schedule upfront, but is credited with catching and resolving stakeholder misunderstandings at both gates before Build began, avoiding what could have been much costlier rework later. | Build a structured feedback cycle into gate reviews for major deliverables from the start of schedule baselining, rather than waiting for a near-miss to prompt the change. | F. Jones | Implemented | Now a standard WBS template element | gate reviews, requirements sign-off, design sign-off, positive practice