PROJECT MANAGEMENT PLAN

Enrollment & Claims Platform Modernization

Prepared by: C. Tyrrell, Program Manager

Version 2.0  |  Draft

Date: July 27, 2026

This document is illustrative and fictional, created for professional portfolio demonstration purposes only.

## Document Control

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 1.0 | 2026-07-27 | C. Tyrrell | Initial draft — all PMBOK subsidiary plans established |
| 2.0 | 2026-07-27 | C. Tyrrell | Expanded with budget breakdown, RACI, stakeholder register, KPIs, risk matrix, escalation matrix, assumptions/constraints, and appendices |

# Table of Contents

1. Introduction & Purpose

2. Project Overview

3. Project Management Approach

4. Scope Management Plan

5. Requirements Management Plan

6. Schedule Management Plan

7. Cost Management Plan

8. Quality Management Plan

9. Resource Management Plan

10. Communications Management Plan

11. Risk Management Plan

12. Procurement Management Plan

13. Stakeholder Engagement Plan

14. Change Management Plan

15. Configuration Management Plan

16. Governance & Decision Authority

17. Process Improvement & Lessons Learned

18. Assumptions, Constraints & Dependencies

19. Baselines Summary

20. Appendices

21. Approval

# 1. Introduction & Purpose

This Project Management Plan (PMP) defines how the Enrollment & Claims Platform Modernization program will be executed, monitored, and controlled. It integrates the subsidiary management plans described in PMBOK — Scope, Requirements, Schedule, Cost, Quality, Resource, Communications, Risk, Procurement, Stakeholder Engagement, Change, and Configuration Management — into a single governing document for the program.

This plan is a companion to the Project Charter, Requirements Document, Work Breakdown Structure (WBS), RAIDD Log, and Change Control Log, and should be read alongside those artifacts rather than in isolation. Appendix references to each companion document appear in Section 20.

# 2. Project Overview

## 2.1 Business Case Summary

The program upgrades the core enrollment and claims platform, converts member, provider, and historical claims data to the upgraded environment, and builds new integrations to Billing, Underwriting, Claims Administration, Commission Management, Data Warehouse/Reporting, and Payment Processing systems. The objective is to modernize the platform's technical foundation while maintaining uninterrupted business operations.

## 2.2 Objectives & Success Criteria

- Complete platform upgrade, data conversion, and all six integrations with zero unplanned production outages during cutover.

- Achieve UAT sign-off with a first-cycle pass rate of 90% or higher (see KPI table, Section 8.1).

- Complete SOX control testing and Compliance sign-off prior to go-live, with zero unresolved critical findings.

- Achieve 95% or higher training completion among impacted end users prior to go-live.

## 2.3 High-Level Scope

- In scope: Platform upgrade; conversion of member, provider, and historical claims data; six integration builds; security, performance, DR, and SOX/privacy compliance testing; end-user training; production cutover and warranty support.

- Out of scope: Form Distribution/Correspondence, Compliance workflow automation, New Business, and Premium Payments integrations are future-phase candidates.

## 2.4 Key Milestones

| Milestone | Target Date |
| --- | --- |
| Project Kickoff | 2026-08-04 |
| Requirements & Vendor Selection Complete | 2026-11-03 |
| System Upgrade Validated | 2027-01-05 |
| Data Conversion Sign-off | 2027-03-16 |
| Integration Build Complete | 2027-05-11 |
| Testing Complete / UAT Sign-off | 2027-08-10 |
| Go-Live (Production Cutover) | 2027-08-24 |
| Production Support Handover / Closeout | 2027-11-02 |

# 3. Project Management Approach

This program follows a hybrid waterfall/agile methodology, tailored deliberately rather than defaulting to a single framework. Requirements, vendor selection, and design follow a gated waterfall approach — appropriate given the regulated, SOX-relevant systems in scope, where formal sign-off and audit trail matter more than speed of iteration. Integration Build follows iterative, sprint-based agile execution across six parallel tracks, since each integration can be built, demonstrated, and refined independently without waiting on the others. Testing returns to a phased, gated model consistent with regulatory obligations.

## 3.1 Phase Summary

| Phase | Duration | Start | Target End | Key Deliverable | Dependency |
| --- | --- | --- | --- | --- | --- |
| 1. Initiation & Requirements | 71 days | 2026-08-04 | 2026-11-03 | Approved requirements, selected vendors, signed SOWs | None — program start |
| 2. System Upgrade | 45 days | 2026-11-04 | 2027-01-05 | Upgraded platform, validated in Staging | Phase 1 complete |
| 3. Data Conversion | 50 days | 2027-01-06 | 2027-03-16 | Converted & reconciled member, provider, claims data | Phase 2 complete |
| 4. Integration Build | 90 days | 2027-01-06 | 2027-05-11 | Six integrations built and unit-tested | Phase 2 complete (Claims track also needs Phase 3) |
| 5. Testing | 155 days | 2027-01-06 | 2027-08-10 | Functional, System, Security, Performance, DR, SOX, and UAT sign-off | Phases 3 & 4 complete |
| 6. Cutover & Hypercare | 60 days | 2027-08-11 | 2027-11-02 | Production go-live, warranty, decommissioning, support handover | Phase 5 complete |
| 7. Change Mgmt & Training | 240 days | 2026-08-31 | 2027-08-24 | Trained end users, go-live communications | Runs parallel to Phases 1-6 |
| 8. Program Governance & Risk | 260 days | 2026-08-17 | 2027-08-24 | Ongoing status reporting, risk register, cost tracking | Runs parallel to Phases 1-6 |

# 4. Scope Management Plan

Scope is defined and controlled through the WBS, which serves as the scope baseline (315 line items across 8 phases, per Section 3.1).

- Scope definition: requirements gathered by workstream and consolidated into the Requirements Document.

- Scope validation: each phase gate requires formal business and technical sign-off before downstream work proceeds.

- Scope control: change requests are logged as Decisions in the RAIDD Log and Change Control Log, and routed through Change Management (Section 14).

# 5. Requirements Management Plan

Distinct from Scope Management, this describes how requirements specifically are planned, traced, and controlled for change.

- Requirements gathered via structured workshops by workstream, consolidated into the Requirements Document.

- Requirements are prioritized using a MoSCoW model (Must have / Should have / Could have / Won't have this phase) during workshop consolidation.

- A Requirements Traceability Matrix (WBS 1.2.9) links each requirement to its design element, test case, and UAT scenario.

- Requirements are baselined at Requirements Sign-off (WBS 1.5); changes after that point are treated as scope changes.

# 6. Schedule Management Plan

The schedule baseline is maintained in the Project Plan Console and spans 331 working days from Kickoff to Closeout (see Section 3.1 for phase-level detail).

- Gated phases use finish-to-start dependencies; Integration Build uses fixed two-week sprints across six parallel tracks.

- A schedule contingency buffer of 5% is held at the program level (not allocated to any single phase) to absorb minor slippage without requiring Steering Committee escalation.

- System Upgrade is a hard prerequisite for Data Conversion and Integration Build; no downstream work is scheduled before Upgrade Validation & Sign-off.

- Schedule performance is reviewed weekly by the PM and reported monthly to the Steering Committee.

# 7. Cost Management Plan

A cost baseline is established early (WBS 8.3.1B) and tracked on an ongoing basis (WBS 8.3.2).

## 7.1 Budget Breakdown

| Category | Budget | % of Total |
| --- | --- | --- |
| Platform Upgrade — vendor license & implementation | $1,850,000 | 28% |
| Integration Middleware — vendor license & implementation | $620,000 | 9% |
| Internal labor (PM, BA, Architecture, Governance) | $1,240,000 | 19% |
| Offshore & onshore QA labor | $780,000 | 12% |
| Development labor (6 integration tracks) | $1,340,000 | 20% |
| Infrastructure / cloud environment costs | $410,000 | 6% |
| Training & change management | $180,000 | 3% |
| Contingency reserve (10%) | $642,000 | 10% |
| Total Program Budget | $7,062,000 | 100% |

## 7.2 Performance Measurement Baseline

Cost and schedule performance are measured together using a Performance Measurement Baseline (PMB). Earned Value Management (CPI/SPI) is calculated monthly at the phase level; a value below 0.90 triggers a formal variance analysis reported to the Steering Committee (see KPI targets, Section 8.1).

- Vendor invoices are managed and reconciled against the SOW by the Vendor/Procurement Manager.

# 8. Quality Management Plan

Quality is managed through a layered testing strategy, each layer validating a different level before proceeding to the next: Unit → Functional → System → Security & Penetration → Performance & Load → DR/Failover → SOX Compliance → UAT.

## 8.1 Quality Metrics & KPIs

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Schedule Performance Index (SPI) | ≥ 0.95 | Monthly, via Performance Measurement Baseline |
| Cost Performance Index (CPI) | ≥ 0.95 | Monthly, via Performance Measurement Baseline |
| Data Conversion Accuracy | ≥ 99.5% record match | Reconciliation reports (WBS 3.7.1) |
| Critical/High Defect Escape Rate to UAT | ≤ 5% | Defect tracking, Functional vs. UAT phase |
| UAT Pass Rate (first cycle) | ≥ 90% | UAT execution results (WBS 5.4) |
| Security Findings — Critical/High Open at Go-Live | 0 | Security & Penetration Test results (WBS 5.2A) |
| Training Completion Rate (impacted users) | ≥ 95% prior to go-live | Training Lead completion tracking |
| Hypercare Severity-1 Incidents | ≤ 2 | Production monitoring during Hypercare (WBS 6.3) |

# 9. Resource Management Plan

The program team is organized around named roles. QA follows a dual onshore/offshore model: the onshore Test Lead owns strategy and defect triage; the Offshore QA Coordination Lead owns day-to-day execution.

| Name | Role |
| --- | --- |
| C. Tyrrell | Program Manager |
| F. Jones | Lead Business Analyst |
| J. Albert | Solution Architect |
| T. McCormick | Data Conversion Lead |
| R. Whitfield | QA / Test Lead (Onshore) |
| P. Sundaram | Offshore QA Coordination Lead |
| M. Alvarez | System Upgrade Lead (Platform Engineer) |
| D. Okafor | Developer — Billing Integration |
| S. Lindqvist | Developer — Underwriting Integration |
| K. Delgado | Developer — Claims Administration Integration |
| P. Novak | Developer — Commission Management Integration |
| A. Reyes | Developer — Data Warehouse/Reporting Integration |
| B. Sato | Developer — Payment Processing Integration |
| L. Bergström | Change Manager (OCM Lead) |
| H. Osei | Training Lead |
| V. Alaoui | Customer Experience Manager |
| N. Sharma | Compliance / Legal Representative |
| G. Fenwick | Internal Audit / SOX Compliance Lead |
| W. Donnelly | Vendor / Procurement Manager |
| E. Kowalski | PMO / Governance Analyst |

## 9.1 Reporting Structure

All track developers and the Data Conversion Lead report to the Solution Architect for technical direction and to the Program Manager for schedule/status. QA (both onshore and offshore) reports to the onshore Test Lead. The Change Manager, Training Lead, and Customer Experience Manager report directly to the Program Manager. The Program Manager reports to the Steering Committee.

## 9.2 Responsibility Assignment (RACI)

| Deliverable / Decision | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Requirements Sign-off | F. Jones | C. Tyrrell | Steering Committee, Business Units | N. Sharma |
| Vendor Selection & SOW | W. Donnelly | C. Tyrrell | Steering Committee | N. Sharma, J. Albert |
| System Upgrade Validation | M. Alvarez | C. Tyrrell | J. Albert | R. Whitfield |
| Data Conversion Sign-off | T. McCormick | C. Tyrrell | F. Jones | Business Data Owners |
| Integration Build (per track) | Track Developer | J. Albert | C. Tyrrell | R. Whitfield |
| Security & Pen Test Sign-off | R. Whitfield | N. Sharma | M. Alvarez | G. Fenwick |
| SOX Compliance Sign-off | G. Fenwick | N. Sharma | C. Tyrrell | Steering Committee |
| UAT Sign-off | R. Whitfield | C. Tyrrell | Business Units | Steering Committee |
| Go-Live / Cutover Decision | C. Tyrrell | Steering Committee | All Track Leads | All Stakeholders |

## 9.3 Physical & Material Resources

Cloud infrastructure environments (Dev, Test, Staging, Production, DR), vendor platform licenses, and offshore QA workstation/network provisioning are acquired during Environment Provisioning (WBS 2.1) and released during Legacy Decommissioning (WBS 6.5), both owned by the System Upgrade Lead.

# 10. Communications Management Plan

What is communicated, to whom, how often, through what method, and who owns it:

| Communication | Audience | Frequency | Method | Owner |
| --- | --- | --- | --- | --- |
| Weekly Project Status Report | Steering Committee, PMO | Weekly | Written report | C. Tyrrell |
| Monthly Steering Committee Review | Steering Committee | Monthly | Meeting | C. Tyrrell |
| Sprint Review / Demo | Development teams, PM | Every 2 weeks | Meeting | Track Lead |
| Risk & Issue Review | PMO, Risk Owners | Monthly | Meeting + RAIDD Log | E. Kowalski |
| End-User Training Communications | Impacted business units | Per training schedule | Email / Sessions | H. Osei |
| External Customer Communications | Policyholders / Customers | Pre-go-live | Notices, portal updates | V. Alaoui |
| Go-Live Readiness Briefing | All stakeholders | Prior to cutover | Meeting | C. Tyrrell |

## 10.1 Escalation Matrix

| Level | Trigger | Escalates To | Response Time |
| --- | --- | --- | --- |
| Level 1 — Team | Task-level blocker, single workstream | Track Lead / PM | Same business day |
| Level 2 — Program | Cross-workstream issue, minor schedule/cost risk | Program Manager | Within 2 business days |
| Level 3 — Steering Committee | Phase-gate at risk, baseline impact, compliance exposure | Steering Committee | Next scheduled or emergency session |

# 11. Risk Management Plan

Risks, Actions, Issues, Decisions, and Dependencies are tracked in the RAIDD Log. Risks are scored using a Probability × Impact model.

## 11.1 Impact Definitions

| Impact Level | Definition | Score |
| --- | --- | --- |
| High | Schedule slip > 15 days, or cost overrun > 10%, or compliance/regulatory exposure | 9 |
| Medium | Schedule slip 5–15 days, or cost overrun 3–10% | 6 |
| Low | Schedule slip < 5 days, or cost overrun < 3%, easily absorbed | 3 |

## 11.2 Response Strategies

| Strategy | Definition | Example on This Program |
| --- | --- | --- |
| Avoid | Change the plan to eliminate the risk entirely | Selecting a backup vendor before negotiation stalls (R-003) |
| Mitigate | Reduce probability or impact through proactive action | Daily offshore/onshore standups to reduce coordination risk (R-002) |
| Transfer | Shift risk ownership/impact to a third party | Vendor Warranty Support period shifts post-go-live defect risk to vendor |
| Accept | Acknowledge the risk and take no proactive action, or plan contingency only | Key resource attrition — cross-training as contingency, not prevention (R-006) |

- The Risk Register (RAIDD Log) is reviewed monthly with the Steering Committee; high-priority risks are reviewed weekly by the PM.

- Some risks persist for the program's life and are tracked as Monitoring, Accepted, or Transferred rather than Closed.

# 12. Procurement Management Plan

Two vendor procurements are required: Platform Upgrade and Integration Middleware. Both follow the same sequence: define evaluation criteria, issue RFP, vendor demonstrations, score responses and reference checks, contract negotiation, and finalize the SOW.

- Contract type: Fixed-price for defined implementation deliverables; time-and-materials for post-go-live warranty support beyond the standard 3-week warranty period.

- Vendor performance is managed against SOW milestones and reviewed at each sprint review for the Integration Middleware vendor, and at each environment promotion for the Platform Upgrade vendor.

- The Vendor/Procurement Manager owns both procurements; Legal reviews contract terms prior to execution.

# 13. Stakeholder Engagement Plan

Stakeholders are classified by power and interest to determine engagement approach:

| Stakeholder | Power | Interest | Strategy | Primary Engagement Method |
| --- | --- | --- | --- | --- |
| Executive Sponsor | High | High | Manage Closely | Monthly Steering Committee |
| CIO / VP, IT | High | High | Manage Closely | Monthly Steering Committee |
| VP, Underwriting | High | Medium | Keep Satisfied | Monthly Steering Committee, Workshops |
| VP, Claims Administration | High | Medium | Keep Satisfied | Monthly Steering Committee, Workshops |
| VP, Finance | Medium | High | Keep Satisfied | Monthly cost variance review |
| End Users (Underwriting/Claims/Billing staff) | Low | High | Keep Informed | Training sessions, go-live comms |
| Policyholders / Customers | Low | High | Keep Informed | External customer communications |
| Platform & Middleware Vendors | Medium | Medium | Keep Informed | Sprint reviews, SOW governance |

# 14. Change Management Plan

Requests to change scope, schedule, cost, or approach follow a defined process:

- 1. Change is identified and logged with a Change Request ID in the Change Control Log.

- 2. The Program Manager assesses schedule, cost, and scope impact.

- 3. Changes within PM delegated authority are approved directly and logged for visibility; all others are routed to the Steering Committee per the Governance table (Section 16).

- 4. Approved changes are reflected in the WBS, PM Plan, and any other affected document, with the specific documents updated recorded in the Change Control Log.

# 15. Configuration Management Plan

Formal configuration management is maintained over code, environment configurations, and controlled documents — especially important given the SOX-relevant systems in scope.

- Version control with mandatory peer review prior to promotion between environments (Dev → Test → Staging → Production).

- No code/configuration change is promoted to Production without a documented change request, testing evidence, and sign-off consistent with SOX control requirements.

- Controlled documents use a Major.Minor version scheme (e.g., v2.0); a major version increment reflects Steering Committee re-approval, a minor increment reflects PM-level clarifications.

- Jointly owned by the System Upgrade Lead and the Internal Audit/SOX Compliance Lead.

# 16. Governance & Decision Authority

Decision-making authority is tiered so not every decision requires full Steering Committee review:

| Decision Type | Approval Authority | Escalation Threshold |
| --- | --- | --- |
| Intra-workstream task sequencing | Program Manager | None — informational only |
| Scope change | PM recommends; Steering Committee approves | Any change to baselined requirements |
| Schedule change | Steering Committee | Any phase-gate milestone shift |
| Cost variance | PM monitors; Steering Committee approves | CPI or SPI below 0.90 |
| Vendor contract / SOW change | Vendor/Procurement Mgr recommends; Steering Committee approves | Any SOW amendment |

## 16.1 Meeting Cadence

- Steering Committee: monthly, first week of each month, 60 minutes.

- Program-level status/risk review: weekly, led by the Program Manager.

- Sprint reviews: every two weeks, per integration track.

# 17. Process Improvement & Lessons Learned

Lessons learned are captured continuously, not only at closeout. Each phase-gate sign-off includes a short retrospective logged in the RAIDD Log and reviewed by the PM for improvements applicable to later phases. A consolidated review also occurs at Project Closeout.

# 18. Assumptions, Constraints & Dependencies

## 18.1 Assumptions

- Vendor contracts for both Platform Upgrade and Integration Middleware will be executed within the planned procurement window.

- Business SMEs will be available for scheduled requirements workshops and UAT cycles without significant conflict.

- No major regulatory change affecting SOX or data privacy requirements will occur mid-program.

## 18.2 Constraints

- The program must not introduce unplanned downtime to existing production Underwriting, Claims, or Billing operations during cutover.

- SOX control testing and Compliance sign-off must be complete before Production Cutover, per regulatory obligation.

- Offshore QA execution is bound by the offshore vendor's contracted capacity; surge capacity requires advance notice (see RAIDD Log, R-007).

## 18.3 External Dependencies

- Platform Upgrade and Integration Middleware vendors must deliver per their respective SOWs on schedule.

- Legacy system decommissioning depends on Compliance confirming data retention requirements are satisfied.

# 19. Baselines Summary

- Scope Baseline: the WBS (315 line items across 8 phases).

- Schedule Baseline: 331 working days from Kickoff (2026-08-04) to Closeout (2027-11-02).

- Cost Baseline: $7,062,000 total program budget (Section 7.1), approved by the Steering Committee prior to System Upgrade.

# 20. Appendices

This Plan is one of several companion artifacts produced for this program. Each is maintained and version-controlled separately, per the Configuration Management Plan (Section 15).

| Appendix | Document | Description |
| --- | --- | --- |
| Appendix A | Work Breakdown Structure / Project Plan Console | Full 315-line-item schedule with dependencies and resource assignments |
| Appendix B | RAIDD Log | Risks, Actions, Issues, Decisions, and Dependencies register |
| Appendix C | Resource Register | Full list of program roles and named owners |
| Appendix D | Change Control Log | Record of all formal change requests and their cross-document impact |
| Appendix E | Requirements Document | Detailed functional and non-functional requirements by workstream |
| Appendix F | Test Plan | Detailed test strategy, test cases, and entry/exit criteria per test phase |
| Appendix G | Statement of Work (SOW) — Platform & Middleware Vendors | Contracted scope, deliverables, and acceptance criteria per vendor |

# 21. Approval

This Project Management Plan requires review and approval by the Steering Committee prior to the start of Phase 2 (System Upgrade).

_________________________________          Date: ____________

C. Tyrrell, Program Manager

_________________________________          Date: ____________

Executive Sponsor, Steering Committee