## Overview
Enrollment & Claims Platform Modernization
Project Budget — Illustrative Portfolio Piece
Program Manager | C. Tyrrell
Budget As Of | 15 Jan 2027
Total Program Budget (incl. contingency) | 7062000
Base Budget (pre-contingency) | 6420000
Contingency Reserve (10% of base) | 642000
Spent to Date (all-in) | 3050000
Forecast at Completion (EAC) | 7210000
Budget Status | On Track
Note:
This is an illustrative program budget built to demonstrate PM financial-tracking tooling and reporting design. All figures are fictional. Labor costs on the Resource Rate Card tab reflect blended bill rates for NAMED LEADS only; the Internal Labor, QA Labor, and Development Labor budget categories also include additional unnamed team members supporting each named lead, which is why category totals exceed the sum of named-resource estimates shown on that tab.

## Budget Summary
Budget Summary by Category
Category | Baseline | Spent to Date | Forecast at Completion | Variance ($) | Variance (%)
Platform Upgrade — Vendor License & Implementation | 1850000 | 1700000 | 1850000 | 0 | 0%
Integration Middleware — Vendor License & Implementation | 620000 | 310000 | 620000 | 0 | 0%
Internal Labor (PM / BA / Architecture / Governance) | 1240000 | 490000 | 1388000 | 148000 | 11.94%
Offshore & Onshore QA Labor | 780000 | 195000 | 780000 | 0 | 0%
Development Labor — 6 Integration Tracks | 1340000 | 100000 | 1340000 | 0 | 0%
Infrastructure / Cloud Environment Costs | 410000 | 130000 | 410000 | 0 | 0%
Training & Change Management | 180000 | 63000 | 180000 | 0 | 0%
Subtotal (Base Budget) | 6420000 | 2988000 | 6568000 | 148000 | 2.305%
Contingency Reserve (10% of base) | 642000 | 62000 | 642000 | 0 | 0% | Spent to Date = contingency drawn so far (held against R-001); Remaining = Baseline − Drawn
Contingency Remaining (Today) | 580000
TOTAL PROGRAM BUDGET | 7062000 | 3050000 | 7210000 | 148000 | 2.096%
Note: The full +$148K forecast variance is attributed to Internal Labor, reflecting Data Conversion Lead time held in reserve in case Dry Run 3 is required for R-001 (historical claims data quality). No other category is currently forecast to vary from baseline.

## Resource Rate Card
Resource Rate Card & Labor Cost Detail
Rates are BLENDED bill rates for NAMED LEADS. Category totals on Budget Summary also include additional unnamed team members supporting each lead.
Resource | Role | Blended Rate ($/hr) | Active Days | Avg. Utilization % | Hours | Est. Labor Cost | Actual to Date | % Spent
C. Tyrrell | Program Manager | 175 | 331 | 90% | 2383.2 | 417060 | 125118 | 30%
F. Jones | Lead Business Analyst | 140 | 200 | 70% | 1120 | 156800 | 47040 | 30%
J. Albert | Solution Architect | 165 | 250 | 80% | 1600 | 264000 | 79200 | 30%
M. Alvarez | System Upgrade Lead / Platform Engineer | 155 | 116 | 90% | 835.2 | 129456 | 38836.8 | 30%
T. McCormick | Data Conversion Lead | 150 | 200 | 85% | 1360 | 204000 | 61200 | 30%
R. Whitfield | QA / Test Lead (Onshore) | 125 | 300 | 75% | 1800 | 225000 | 67500 | 30%
P. Sundaram | Offshore QA Coordination Lead | 65 | 250 | 70% | 1400 | 91000 | 27300 | 30%
D. Okafor | Developer — Billing Integration | 130 | 150 | 100% | 1200 | 156000 | 46800 | 30%
S. Lindqvist | Developer — Underwriting Integration | 130 | 150 | 100% | 1200 | 156000 | 46800 | 30%
K. Delgado | Developer — Claims Administration Integration | 130 | 150 | 100% | 1200 | 156000 | 46800 | 30%
P. Novak | Developer — Commission Management Integration | 130 | 138 | 100% | 1104 | 143520 | 43056 | 30%
A. Reyes | Developer — Data Warehouse/Reporting Integration | 130 | 138 | 100% | 1104 | 143520 | 43056 | 30%
B. Sato | Developer — Payment Processing Integration | 130 | 138 | 100% | 1104 | 143520 | 43056 | 30%
L. Bergström | Change Manager (OCM Lead) | 145 | 240 | 80% | 1536 | 222720 | 66816 | 30%
H. Osei | Training Lead | 110 | 240 | 63% | 1209.6 | 133056 | 39916.8 | 30%
V. Alaoui | Customer Experience Manager | 120 | 200 | 20% | 320 | 38400 | 11520 | 30%
N. Sharma | Compliance / Legal Representative | 180 | 260 | 30% | 624 | 112320 | 33696 | 30%
G. Fenwick | Internal Audit / SOX Compliance Lead | 150 | 200 | 30% | 480 | 72000 | 21600 | 30%
W. Donnelly | Vendor / Procurement Manager | 145 | 150 | 50% | 600 | 87000 | 26100 | 30%
E. Kowalski | PMO / Governance Analyst | 135 | 260 | 25% | 520 | 70200 | 21060 | 30%
TOTAL (Named Leads Only) |  |  |  |  | 22700 | 3121572 | 936471.6 | 30%
Rate basis: blended bill rates benchmarked against 2026 U.S. IT/PM consulting market data. 'Active Days' = working days across the phases each resource is engaged; 'Avg. Utilization %' = average allocation to this program during that window. 'Actual to Date' applies a flat 30% consumption rate to each named lead's full-program estimate as of 15 Jan 2027, as a simplifying illustrative assumption since individual resource-level actuals aren't separately tracked in this model.

## Non-Labor Cost Detail
Non-Labor Cost Detail
Platform Upgrade — Vendor License & Implementation
| Core enrollment/claims platform version upgrade (vendor SOW) | 1450000
| Upgrade-related environment refresh (dev/test) | 250000
| Vendor project management & cutover support | 150000
| Subtotal | 1850000
Integration Middleware — Vendor License & Implementation
| Middleware platform license (event-driven integration layer) | 420000
| Middleware implementation & configuration services | 200000
| Subtotal | 620000
Infrastructure / Cloud Environment Costs
| Non-production environment compute & storage (Dev/Test/Staging) | 260000
| Network & security appliance upgrades | 150000
| Subtotal | 410000
Training & Change Management
| Training content development & LMS setup | 100000
| Change readiness communications & job aids | 80000
| Subtotal | 180000
These line items are illustrative detail supporting the category totals on the 'Budget Summary' tab; amounts here are independent inputs (not formula-linked) since this is a portfolio demonstration rather than a live cost system.

## Baseline History
Budget Baseline History
How the current baseline was reached from the original pre-change baseline, via the 10 approved Change Requests.
Category | Original Baseline | Change Requests Applied | Current Baseline
Platform Upgrade (Vendor) | 1765000 | CR-005 +$85,000 | 1850000
Integration Middleware (Vendor) | 620000 | — | 620000
Internal Labor | 775000 | CR-006 +$60,000; CR-008 +$95,000; CR-010 +$310,000 | 1240000
Offshore & Onshore QA Labor | 615000 | CR-004 +$45,000; CR-007 +$120,000 | 780000
Development Labor | 1340000 | — | 1340000
Infrastructure / Cloud Environment | 410000 | — | 410000
Training & Change Management | 180000 | — | 180000
Subtotal (Base Budget) | 5705000 | +$715,000 (6 CRs) | 6420000
Contingency Reserve (10% of base) | 570500 | +$71,500 (proportional to base growth) | 642000
TOTAL PROGRAM BUDGET | 6275500 | +$786,500 | 7062000
Four CRs carried no cost impact (CR-001, CR-002, CR-003, CR-009) and are not shown. Of the six that did, each is mapped to the single category it most directly affects. The Contingency Reserve is a fixed 10% of the base budget, so as approved changes grew the base, the reserve grew proportionally — a secondary effect of the CRs, not a separate change of its own. Full CR-by-CR detail is in the Change Control Log.