## Summary
Cost-Benefit Analysis
Enrollment & Claims Platform Modernization — ACME Company
Program Manager | C. Tyrrell
Analysis Date | 15 Jan 2027
Initial Investment | 7062000
Annual Ongoing Cost (Year 1+) | 950000
Annual Gross Benefit (at full realization) | 2530000
Discount Rate | 8%
Simple Payback Period | ~5.6 years (undiscounted)
Discounted Payback Period | ~7.5 years
10-Year Simple ROI | 98.7%
10-Year NPV @ 8% | 1934819
Recommendation:
Approve. The program reaches positive discounted cash flow within its expected useful life (~7.5 years), and produces a positive 10-year NPV of approximately $1.93M at an 8% discount rate. Full financial detail is on the Benefits Detail, Costs Detail, and Cash Flow Analysis tabs.

## Benefits Detail
Quantified Annual Benefits (at full realization)
Benefit Category | Annual Value | Basis / Rationale
Labor Efficiency (Claims Processing) | 1200000 | Reduced manual claims processing time from platform automation and streamlined workflows
Error / Rework Reduction | 450000 | Fewer claims errors and appeals reduce rework and downstream correction costs
Compliance Risk Avoidance | 300000 | Risk-adjusted avoidance of potential regulatory penalty exposure from improved SOX-aligned controls
Legacy System Decommissioning Savings | 380000 | Retired legacy license, maintenance, and support fees
Customer Retention / Satisfaction | 200000 | Faster claims turnaround reduces churn-driven revenue loss (conservative estimate)
TOTAL ANNUAL BENEFIT (Full Realization) | 2530000
Benefit realization ramps over the first two years as change adoption matures: 50% in Year 1, 80% in Year 2, 100% from Year 3 onward. See the Cash Flow Analysis tab for the full realization schedule.

## Costs Detail
Cost Detail
One-Time Implementation Cost (Year 0)
Category | Amount | Notes
Platform Upgrade (Vendor) | 1850000 | See Project Budget for full category breakdown
Integration Middleware (Vendor) | 620000
Internal Labor | 1240000
QA Labor | 780000
Development Labor | 1340000
Infrastructure / Cloud | 410000
Training & Change Management | 180000
Contingency Reserve | 642000
TOTAL IMPLEMENTATION COST | 7062000
Ongoing Annual Cost (Year 1+)
Category | Annual Amount | Notes
Software Licensing / Subscription Renewal | 180000 | Annual platform and third-party license renewal
Hosting / Cloud Infrastructure | 220000 | Production and DR environment hosting
Vendor Maintenance & Support (Post-Warranty) | 150000 | Annual vendor support contract after the initial warranty period
Internal Support / Operations Staff | 300000 | Allocated FTE time for ongoing platform support
Periodic Enhancements / Minor Change Requests | 100000 | Assumed ongoing enhancement budget
TOTAL ANNUAL ONGOING COST | 950000

## Cash Flow Analysis
10-Year Cash Flow & NPV Analysis
Discount Rate | 8%
Annual Gross Benefit (Full Realization) | 2530000
Annual Ongoing Cost | 950000
Initial Investment (Year 0) | 7062000
Year | Realization % | Benefit | Ongoing Cost | Net Cash Flow | Discount Factor | Discounted Net | Cumulative Discounted
0 |  |  |  | -7062000 | 1 | -7062000 | -7062000
1 | 50% | 1265000 | 950000 | 315000 | 0.92593 | 291666.6667 | -6770333.3333
2 | 80% | 2024000 | 950000 | 1074000 | 0.85734 | 920781.893 | -5849551.4403
3 | 100% | 2530000 | 950000 | 1580000 | 0.79383 | 1254254.9408 | -4595296.4995
4 | 100% | 2530000 | 950000 | 1580000 | 0.73503 | 1161347.1674 | -3433949.3321
5 | 100% | 2530000 | 950000 | 1580000 | 0.68058 | 1075321.4513 | -2358627.8808
6 | 100% | 2530000 | 950000 | 1580000 | 0.63017 | 995668.0105 | -1362959.8703
7 | 100% | 2530000 | 950000 | 1580000 | 0.58349 | 921914.8245 | -441045.0458
8 | 100% | 2530000 | 950000 | 1580000 | 0.54027 | 853624.8375 | 412579.7917
9 | 100% | 2530000 | 950000 | 1580000 | 0.50025 | 790393.3681 | 1202973.1598
10 | 100% | 2530000 | 950000 | 1580000 | 0.46319 | 731845.7112 | 1934818.871
10-YR TOTALS |  |  |  | 6967000 |  |  | 1934818.871
Cumulative Discounted (column H) crosses positive between Year 7 and Year 8 — the discounted payback point. The undiscounted Net Cash Flow (column E) crosses positive between Year 5 and Year 6. Both are within the platform's expected useful life.