Enrollment & Claims Platform Modernization

Program Dashboard — Portfolio Demo

Program Manager: C. Tyrrell     |     Status As Of: 15 Jan 2027     |     Phase: 3 & 4 — Data Conversion / Integration Build (Entry)     |     Overall Health: Yellow

# Executive Summary

Enrollment & Claims Platform Modernization has completed Initiation, Requirements & Vendor Selection, and System Upgrade Validation, and is now entering Data Conversion and Integration Build in parallel — roughly 37% through the 331-day baseline schedule. The program is currently in Yellow status due to a high-severity data quality risk (R-001) in the historical claims data, which could extend the Data Conversion timeline if root-cause cleansing isn't sufficient before Dry Run 2. The get-to-Green strategy is to complete early data profiling and automated cleansing rules ahead of schedule, escalate any systemic issues to the Business Data Owner immediately, and hold a third Dry Run in reserve if reconciliation tolerance isn't met. No change to the Data Conversion Sign-off milestone (16 Mar 2027) is being proposed at this time.

## Program Health at a Glance

| Metric | Status/Value | Detail |
| --- | --- | --- |
| Overall Status | Yellow | Historical claims data quality risk (R-001) |
| Schedule | 37% | 123 of 331 working days elapsed |
| Budget | 43% | $3.05M of $7.06M baseline spent |
| Open Risks (High) | 1 | R-001, unmitigated |
| Next Milestone | Data Conversion Sign-off | Targeted 16 Mar 2027 |

## Milestone Timeline

| Milestone | Date | Status |
| --- | --- | --- |
| Project Kickoff | 04 Aug 26 | Complete |
| Requirements & Vendor Selection Complete | 03 Nov 26 | Complete |
| System Upgrade Validated | 05 Jan 27 | Complete |
| Data Conversion / Integration Build | In progress | Current |
| Integration Build Complete | 11 May 27 | Upcoming |
| Testing / UAT Sign-off | 10 Aug 27 | Upcoming |
| Go-Live | 24 Aug 27 | Upcoming |

## Top Risks (from RAIDD Log)

| ID | Description | Owner |
| --- | --- | --- |
| R-001 | Historical claims data quality issues may extend Data Conversion timeline (Score 9, High/High) | T. McCormick |
| R-003 | Vendor SOW negotiation delay could push Environment Provisioning start (Score 6, Medium/High) | W. Donnelly |
| R-002 | Offshore/onshore QA coordination gaps could slow defect turnaround (Score 4, Medium/Medium) | R. Whitfield |

## Budget Snapshot

| Metric | Amount |
| --- | --- |
| Spent to Date | $3.05M |
| Forecast at Completion | $7.21M |
| Contingency Remaining | $0.58M of $0.642M |
| Variance to Baseline | +2.1% |

## WBS Phase Progress (315 line items, 8 phases)

| Phase | % Complete | Status |
| --- | --- | --- |
| 1. Initiation & Requirements | 100% | Closed |
| 2. System Upgrade | 100% | Closed |
| 3. Data Conversion | 16% | In progress |
| 4. Integration Build (Agile) | 9% | In progress |
| 5. Testing (Functional-UAT) | 5% | Prep only |
| 6. Cutover & Hypercare | 0% | Not started |
| 7. Change Mgmt & Training | 37% | In progress (parallel) |
| 8. Program Governance & Risk | 42% | In progress (parallel) |

## RAIDD Summary

| Category | Count | Note |
| --- | --- | --- |
| Risks | 6 | 1 high (R-001), 2 medium |
| Issues | 5 | 1 open (I-003), 4 resolved/closed |
| Actions | 6 | 3 in progress, 3 complete |
| Decisions | 5 | All approved |
| Dependencies | 5 | 1 at risk (DEP-003), 4 on track |

## Resource Utilization (Current Period)

| Resource | Role | Utilization |
| --- | --- | --- |
| C. Tyrrell | Program Manager | 100% |
| F. Jones | Lead Business Analyst | 60% |
| J. Albert | Solution Architect | 90% |
| M. Alvarez | System Upgrade Lead | 70% |
| T. McCormick | Data Conversion Lead | 100% |
| R. Whitfield | QA / Test Lead (Onshore) | 65% |
| P. Sundaram | Offshore QA Coordination Lead | 50% |
| W. Donnelly | Vendor / Procurement Manager | 40% |
| N. Sharma | Compliance / Legal | 30% |
| G. Fenwick | Internal Audit / SOX Compliance Lead | 35% |
| E. Kowalski | PMO / Governance Analyst | 25% |
| L. Bergström | Change Manager (OCM Lead) | 40% |
| H. Osei | Training Lead | 20% |
| V. Alaoui | Customer Experience Manager | 20% |

Illustrative program data — built to demonstrate PM tooling and reporting design, not a real client engagement.