Project Governance Model

Enrollment & Claims Platform Modernization

ACME Company     |     Version 1.0     |     15 Jan 2027

# 1. Purpose & Governance Principles

This document establishes the decision-making authority, escalation paths, and accountability structure for the Enrollment & Claims Platform Modernization program. It is distinct from the Project Management Plan: the PM Plan describes how the work will be executed; this document defines who has the authority to decide, and how disputes or exceptions are resolved when the plan needs to change.

Five principles guide this governance model:

- Transparency — decisions and their rationale are documented and visible to all relevant stakeholders.

- Accountability — every decision has a single accountable owner, even when multiple people are consulted.

- Timely Decision-Making — defined escalation timeframes prevent issues stalling at the wrong authority level.

- Proportionality — governance oversight scales with the risk and impact of the decision.

- Single Source of Truth — this document is the authoritative reference for decision rights across the program.

## 2. Governance Structure

| Body | Composition | Function |
| --- | --- | --- |
| Executive Sponsor | G. Whitfield, VP of Operations | Ultimate accountability for the program's business outcome; final authority on strategic direction |
| Steering Committee | 8 members | Collective decision-making body for changes exceeding the PM's delegated authority |
| PMO | S. Ryan, Director, PMO | Owns and maintains this framework; facilitates Change Control Board reviews |
| Program Manager | C. Tyrrell | Day-to-day execution authority within delegated limits |

## Steering Committee Roster

| Name | Role | Voting |
| --- | --- | --- |
| G. Whitfield | Executive Sponsor (VP of Operations) | Yes |
| A. Marchetti | CIO / VP of Information Technology | Yes |
| R. Castellano | VP, Underwriting | Yes |
| J. Boudreaux | VP, Claims Administration | Yes |
| S. Whitcombe | VP, Finance | Yes |
| N. Sharma | Chief Compliance Officer / General Counsel | Yes |
| S. Ryan | Director, PMO | Yes |
| C. Tyrrell | Program Manager (briefs the committee) | No |

For the full reporting-line structure, including matrixed/loaned resources shown with dotted-line relationships, see the companion Organizational Chart.

## 3. Roles, Responsibilities & Decision Rights

Every decision on this program falls into one of three authority tiers — the same model applied across the Change Control Log, RAIDD Log, and PM Plan Section 16.

| Tier | Authority | Decisions Covered |
| --- | --- | --- |
| Tier 1 | Program Manager (informational) | Task-level schedule adjustments with no milestone impact; resource assignment; scope clarifications |
| Tier 2 | Steering Committee | Any cost impact to baseline; schedule impact to a major milestone; scope changes affecting a deliverable; compliance-related changes |
| Tier 3 | Executive Sponsor | Governance structure changes; program-level scope changes; cost baseline changes exceeding contingency; continuation/cancellation |

## 3.1 Governance-Process RACI Matrix

This matrix covers governance-process activities only — approving changes, accepting risk, authorizing exceptions. It is deliberately narrower than, and complementary to, the deliverable sign-off RACI already defined in PM Plan §9.2 (Requirements Sign-off, Vendor Selection, UAT Sign-off, Go-Live Decision, etc.). The two matrices should never duplicate the same row — if an activity is already governed by PM Plan §9.2, it is intentionally not repeated here.

| Governance Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Approve Tier 2 Change Request | PMO Director | Steering Committee | PM, affected Leads | All Stakeholders |
| Approve Tier 3 Change Request | PMO Director | Executive Sponsor | Steering Committee | All Stakeholders |
| Accept High-Scored Risk (≥7) | Program Manager | Steering Committee | Risk Owner, PMO | Executive Sponsor |
| Authorize SOX Exception | Chief Compliance Officer | Executive Sponsor | Steering Committee | Program Manager |
| Approve Vendor SOW Change | Vendor/Procurement Mgr | Steering Cmte / PM | PMO Director | Executive Sponsor |
| Quarterly Governance Review | PMO Director | Steering Committee | Program Manager | Executive Sponsor |

## 4. Escalation Process

| Trigger | Threshold | Escalates To | Timeframe |
| --- | --- | --- | --- |
| Cost variance | >50% of contingency drawn | Steering Committee (notify) | Next reporting cycle |
| Cost variance | Exceeds total contingency | Steering Committee (approval) | 5 business days |
| Schedule slip | Major milestone at risk | Steering Committee (notify) | 5 business days |
| Schedule slip | >10 business days | Steering Committee (re-baseline) | 10 business days |
| Risk score | RAIDD score ≥7 (High/High) | Steering Committee | Next reporting cycle |
| Compliance finding | Any SOX control finding | Compliance Officer + Steering Committee | 2 business days |

Standard escalation path: Team Member → Workstream Lead → Program Manager → PMO Director / Steering Committee → Executive Sponsor. Issues unresolved at the PM level within 5 business days (2 for Critical/High items) escalate automatically.

## 5. Meeting Cadence & Reporting

| Cadence | Forum | Purpose |
| --- | --- | --- |
| Weekly | PM + Workstream Leads sync | Informal status alignment |
| Weekly | Status Report to Steering Committee | Written progress, risk, and budget update |
| Monthly | Steering Committee meeting | Formal review; decisions voted on; minutes recorded |
| Quarterly | Governance framework review | See Section 13 |
| Ad hoc | Change Control Board | Convened for any Tier 2/3 change request |

## 6. Change Control Governance

All formal changes to scope, schedule, or cost baselines follow the tiered authority model in Section 3, formalized through the program's Change Control Log. This document is the authoritative source for why those tiers exist; the Change Control Log is the operational record of every request evaluated against them.

## 7. Vendor Governance

The program carries two major vendor contracts — Platform Upgrade ($1,850,000) and Integration Middleware ($620,000) — combined, roughly 35% of the base budget. This section defines vendor-specific decision authority, distinct from the general Change Control tiers in Section 6.

| Activity | Authority |
| --- | --- |
| Vendor SOW change, no cost/schedule impact | Vendor/Procurement Manager, informational to PM |
| Vendor SOW change, with cost or schedule impact | Steering Committee (Tier 2, per Section 3) |
| Vendor performance review | Conducted quarterly by the Vendor/Procurement Manager; reported to the PMO |
| Vendor dependency at risk | Automatically visible to the Steering Committee via the RAIDD Log |
| Vendor contract dispute | Vendor/Procurement Manager → PM → PMO Director → Executive Sponsor (final authority) |
| Vendor warranty & support handover | Owned by the Vendor/Procurement Manager, per CR-005 terms |

## 8. Stage Gates & Phase Approval Criteria

Each of the program's 8 WBS phases has a formal gate that must be passed before the next phase begins in earnest — modeled on the stage-gate approach common in regulated, multi-stakeholder programs.

Every gate requires two things, not one: the specific go/no-go criteria below, and continued business justification — a brief reconfirmation that the assumptions underlying the Cost-Benefit Analysis still hold. A gate can meet every schedule and quality criterion and still legitimately not pass if the business case has materially changed. This principle is drawn from PRINCE2's continued-business-justification requirement and applies at every gate below, not only Go-Live.

| Gate | Go/No-Go Criteria | Approval |
| --- | --- | --- |
| Requirements & Vendor Selection Complete | Vendor SOW signed; requirements baseline approved | Steering Committee |
| System Upgrade Validated | Platform upgrade tested and validated | Steering Committee |
| Data Conversion Sign-off | ≥99.5% record-match accuracy achieved | Steering Committee |
| Integration Build Complete | All 6 integrations pass unit/integration testing | PM, reported to Steering Committee |
| Testing Complete / UAT Sign-off | UAT pass rate ≥90%; zero open Critical/High findings; SOX testing passed | Steering Committee |
| Go-Live | All prior gates passed; formal readiness review complete | Executive Sponsor + Steering Committee |
| Closeout | Warranty period complete; lessons learned documented | PMO |

## 9. Independent Assurance

Performance Monitoring (Section 12) is self-reported: the Program Manager and PMO track and report status upward through the normal chain. Independent Assurance is a distinct, separate check — performed by someone outside the reporting chain being assessed — to catch an incomplete or overly optimistic self-report before it reaches the Steering Committee.

| Element | Detail |
| --- | --- |
| Who performs it | PMO Director, or a PMO team member not directly assigned to this program; the Executive Sponsor may designate an independent reviewer from outside the PMO |
| Frequency | Before each Stage Gate (Section 8); at the midpoint of any phase exceeding 90 days |
| Scope | Spot-check reported EVM figures against underlying data; review RAIDD Log completeness; confirm Change Control Log entries match actual approved changes |
| Findings | Reported directly to the Steering Committee — not filtered through the Program Manager |

## 10. Risk & Issue Governance

The RAIDD Log records what the risks and issues are; this section defines who has authority to accept, fund, or escalate a response.

| Risk Score | Authority |
| --- | --- |
| 1–3 (Low) | Program Manager may accept and manage without further approval |
| 4–6 (Medium) | Program Manager manages; reported to Steering Committee next cycle |
| 7–9 (High) | Requires Steering Committee visibility and response plan approval |

## 11. Compliance & Regulatory Oversight

Because the program touches financial systems subject to SOX controls, compliance sign-off carries a standing exception to the normal authority tiering:

Compliance Veto Authority: SOX compliance sign-off (owned by the Chief Compliance Officer and the Internal Audit/SOX Compliance Lead) cannot be waived or overridden by schedule or budget pressure at the Program Manager or Steering Committee level. Only the Executive Sponsor, in consultation with the Chief Compliance Officer, may authorize an exception, and any exception must be documented with rationale in the governance review record (Section 13).

## 12. Performance Monitoring

The Steering Committee monitors program health against the quality KPIs defined in PM Plan Section 8, reported monthly via the Steering Committee Deck:

- Schedule Performance Index (SPI) and Cost Performance Index (CPI) ≥ 0.95

- Data Conversion Accuracy ≥ 99.5%

- Critical/High Defect Escape Rate to UAT ≤ 5%

- UAT Pass Rate (first cycle) ≥ 90%

- Critical/High security findings open at Go-Live: 0

- Training Completion ≥ 95% prior to Go-Live

- Hypercare Severity-1 Incidents ≤ 2

## 13. Governance of This Framework

This document is owned by the PMO Director and reviewed quarterly. Amendments to the decision-rights tiers, escalation thresholds, or stage-gate criteria require Steering Committee approval; amendments to meeting cadence or reporting format may be approved by the PMO Director alone.

| Version | Date | Summary | Approved By |
| --- | --- | --- | --- |
| 1.0 | 15 Jan 2027 | Initial governance model established | Steering Committee |

## 14. Approval

This governance model is approved for use across the Enrollment & Claims Platform Modernization program.

_________________________________          Date: ____________

G. Whitfield, Executive Sponsor

_________________________________          Date: ____________

S. Ryan, Director, PMO

_________________________________          Date: ____________

C. Tyrrell, Program Manager

Illustrative program data — created to demonstrate PMBOK/PRINCE2-informed program governance practice, not a real client engagement.