## WBS
Enrollment & Claims Platform Modernization — Work Breakdown Structure
Full export from the Project Plan Console (web tool) — 315 line items across 8 phases. % Complete as of 15 Jan 2027.
WBS ID | Task Name | Phase | Start | Finish | Duration (d) | % Complete | Assignee
1 | Initiation & Requirements | Initiation & Requirements | 2026-07-28 | 2026-11-03 | 71 | 100% | C. Tyrrell
1.1 | Project Charter & Business Case | Initiation & Requirements | 2026-07-28 | 2026-08-03 | 5 | 100% | C. Tyrrell
1.1.1 | Draft business case & objectives | Initiation & Requirements | 2026-07-28 | 2026-07-29 | 2 | 100% | C. Tyrrell
1.1.2 | Identify executive sponsor & governance structure | Initiation & Requirements | 2026-07-30 | 2026-07-30 | 1 | 100% | C. Tyrrell
1.1.3 | Define high-level scope & success criteria | Initiation & Requirements | 2026-07-31 | 2026-07-31 | 1 | 100% | C. Tyrrell
1.1.4 | Charter review & executive sign-off | Initiation & Requirements | 2026-08-03 | 2026-08-03 | 1 | 100% | C. Tyrrell
1.1B | Project Kickoff Meeting | Initiation & Requirements | 2026-08-04 | 2026-08-04 | 1 | 100% | C. Tyrrell
1.1B.1 | Prepare kickoff deck (scope, team, milestones) | Initiation & Requirements | 2026-08-04 | 2026-08-04 | 1 | 100% | C. Tyrrell
1.1B.2 | Conduct kickoff meeting with steering committee & core team | Initiation & Requirements | 2026-08-04 | 2026-08-04 | 1 | 100% | C. Tyrrell
1.2 | Stakeholder Requirements Gathering | Initiation & Requirements | 2026-08-05 | 2026-08-25 | 15 | 100% | F. Jones
1.2.1 | Identify stakeholder groups | Initiation & Requirements | 2026-08-05 | 2026-08-05 | 1 | 100% | F. Jones
1.2.2 | Requirements workshops — Underwriting | Initiation & Requirements | 2026-08-06 | 2026-08-07 | 2 | 100% | F. Jones
1.2.3 | Requirements workshops — Claims Administration | Initiation & Requirements | 2026-08-10 | 2026-08-11 | 2 | 100% | F. Jones
1.2.4 | Requirements workshops — Billing & Finance | Initiation & Requirements | 2026-08-12 | 2026-08-13 | 2 | 100% | F. Jones
1.2.5 | Requirements workshops — Compliance/Legal | Initiation & Requirements | 2026-08-14 | 2026-08-17 | 2 | 100% | F. Jones
1.2.6 | Requirements workshops — Customer Service & New Business | Initiation & Requirements | 2026-08-18 | 2026-08-19 | 2 | 100% | F. Jones
1.2.7 | Document functional requirements | Initiation & Requirements | 2026-08-20 | 2026-08-21 | 2 | 100% | F. Jones
1.2.8 | Document non-functional requirements (security, performance, compliance) | Initiation & Requirements | 2026-08-24 | 2026-08-24 | 1 | 100% | F. Jones
1.2.9 | Build requirements traceability matrix | Initiation & Requirements | 2026-08-25 | 2026-08-25 | 1 | 100% | F. Jones
1.2B | SOX Control Impact Assessment | Initiation & Requirements | 2026-08-26 | 2026-09-01 | 5 | 100% | G. Fenwick
1.2B.1 | Identify SOX-relevant systems & financial data flows | Initiation & Requirements | 2026-08-26 | 2026-08-27 | 2 | 100% | G. Fenwick
1.2B.2 | Assess control impact of upgrade, conversions & integrations | Initiation & Requirements | 2026-08-28 | 2026-08-31 | 2 | 100% | G. Fenwick
1.2B.3 | Document required control changes & obtain Internal Audit input | Initiation & Requirements | 2026-09-01 | 2026-09-01 | 1 | 100% | G. Fenwick
1.2C | Data Privacy / PII Impact Assessment | Initiation & Requirements | 2026-08-26 | 2026-09-01 | 5 | 100% | N. Sharma
1.2C.1 | Identify PII/PHI data elements in scope (member, provider, claims) | Initiation & Requirements | 2026-08-26 | 2026-08-27 | 2 | 100% | N. Sharma
1.2C.2 | Assess privacy/regulatory impact of conversions & integrations | Initiation & Requirements | 2026-08-28 | 2026-08-31 | 2 | 100% | N. Sharma
1.2C.3 | Document required privacy controls & sign-off | Initiation & Requirements | 2026-09-01 | 2026-09-01 | 1 | 100% | N. Sharma
1.3 | Vendor Selection — Platform Upgrade | Initiation & Requirements | 2026-09-02 | 2026-09-21 | 14 | 100% | W. Donnelly
1.3.0 | Draft RFP document (Platform Upgrade) | Initiation & Requirements | 2026-09-02 | 2026-09-03 | 2 | 100% | W. Donnelly
1.3.1 | Define vendor evaluation criteria | Initiation & Requirements | 2026-09-04 | 2026-09-04 | 1 | 100% | W. Donnelly
1.3.2 | Issue RFP to platform vendors | Initiation & Requirements | 2026-09-07 | 2026-09-07 | 1 | 100% | W. Donnelly
1.3.3 | Vendor demos & Q&A sessions | Initiation & Requirements | 2026-09-08 | 2026-09-10 | 3 | 100% | W. Donnelly
1.3.4 | Score vendor responses | Initiation & Requirements | 2026-09-11 | 2026-09-14 | 2 | 100% | W. Donnelly
1.3.5 | Reference checks | Initiation & Requirements | 2026-09-15 | 2026-09-15 | 1 | 100% | W. Donnelly
1.3.6 | Contract negotiation | Initiation & Requirements | 2026-09-16 | 2026-09-17 | 2 | 100% | W. Donnelly
1.3.7 | Draft & finalize SOW with selected platform vendor | Initiation & Requirements | 2026-09-18 | 2026-09-21 | 2 | 100% | W. Donnelly
1.4 | Vendor Selection — Integration Middleware | Initiation & Requirements | 2026-09-02 | 2026-09-21 | 14 | 100% | W. Donnelly
1.4.0 | Draft RFP document (Integration Middleware) | Initiation & Requirements | 2026-09-02 | 2026-09-03 | 2 | 100% | W. Donnelly
1.4.1 | Define integration architecture requirements | Initiation & Requirements | 2026-09-04 | 2026-09-07 | 2 | 100% | W. Donnelly
1.4.2 | Issue RFP to middleware vendors | Initiation & Requirements | 2026-09-08 | 2026-09-08 | 1 | 100% | W. Donnelly
1.4.3 | Vendor demos & technical evaluation | Initiation & Requirements | 2026-09-09 | 2026-09-11 | 3 | 100% | W. Donnelly
1.4.4 | Score vendor responses | Initiation & Requirements | 2026-09-14 | 2026-09-15 | 2 | 100% | W. Donnelly
1.4.5 | Contract negotiation | Initiation & Requirements | 2026-09-16 | 2026-09-17 | 2 | 100% | W. Donnelly
1.4.6 | Draft & finalize SOW with selected middleware vendor | Initiation & Requirements | 2026-09-18 | 2026-09-21 | 2 | 100% | W. Donnelly
1.5 | Requirements Sign-off | Initiation & Requirements | 2026-09-22 | 2026-10-01 | 8 | 100% | F. Jones
1.5.1 | Requirements walkthrough with SMEs & business owners | Initiation & Requirements | 2026-09-22 | 2026-09-22 | 1 | 100% | F. Jones
1.5.2 | SME & business owner feedback period | Initiation & Requirements | 2026-09-23 | 2026-09-25 | 3 | 100% | F. Jones
1.5.3 | Recirculate updated requirements for review | Initiation & Requirements | 2026-09-28 | 2026-09-28 | 1 | 100% | F. Jones
1.5.4 | Final review & formal sign-off | Initiation & Requirements | 2026-09-29 | 2026-10-01 | 3 | 100% | F. Jones
1.6 | Solution Architecture & Design | Initiation & Requirements | 2026-10-02 | 2026-10-22 | 15 | 100% | J. Albert
1.6.1 | Define target-state architecture | Initiation & Requirements | 2026-10-02 | 2026-10-06 | 3 | 100% | J. Albert
1.6.2 | Design data conversion approach | Initiation & Requirements | 2026-10-07 | 2026-10-08 | 2 | 100% | J. Albert
1.6.3 | Design integration architecture (API/file-based) | Initiation & Requirements | 2026-10-09 | 2026-10-13 | 3 | 100% | J. Albert
1.6.4 | Design security & access model | Initiation & Requirements | 2026-10-14 | 2026-10-15 | 2 | 100% | J. Albert
1.6.5 | Design disaster recovery/failover approach | Initiation & Requirements | 2026-10-16 | 2026-10-19 | 2 | 100% | J. Albert
1.6.6 | Technical design walkthroughs with stakeholders | Initiation & Requirements | 2026-10-20 | 2026-10-21 | 2 | 100% | J. Albert
1.6.7 | Finalize design documentation | Initiation & Requirements | 2026-10-22 | 2026-10-22 | 1 | 100% | J. Albert
1.7 | Design Sign-off (incl. Compliance/Legal Review) | Initiation & Requirements | 2026-10-23 | 2026-11-03 | 8 | 100% | J. Albert
1.7.1 | Architecture & design walkthrough with SMEs & business owners | Initiation & Requirements | 2026-10-23 | 2026-10-23 | 1 | 100% | J. Albert
1.7.2 | SME & business owner feedback period | Initiation & Requirements | 2026-10-26 | 2026-10-28 | 3 | 100% | J. Albert
1.7.3 | Recirculate updated design documents for review | Initiation & Requirements | 2026-10-29 | 2026-10-29 | 1 | 100% | J. Albert
1.7.4 | Final review & formal design sign-off | Initiation & Requirements | 2026-10-30 | 2026-11-03 | 3 | 100% | J. Albert
2 | System Upgrade | System Upgrade | 2026-11-04 | 2027-01-05 | 45 | 100% | M. Alvarez
2.1 | Environment Provisioning | System Upgrade | 2026-11-04 | 2026-11-17 | 10 | 100% | M. Alvarez
2.1.1 | Provision infrastructure (servers/cloud environment) | System Upgrade | 2026-11-04 | 2026-11-06 | 3 | 100% | M. Alvarez
2.1.2 | Configure network & security groups | System Upgrade | 2026-11-09 | 2026-11-10 | 2 | 100% | M. Alvarez
2.1.3 | Install base platform software | System Upgrade | 2026-11-11 | 2026-11-13 | 3 | 100% | M. Alvarez
2.1.4 | Configure environment monitoring & logging | System Upgrade | 2026-11-16 | 2026-11-17 | 2 | 100% | M. Alvarez
2.2 | Core Platform Upgrade / Migration | System Upgrade | 2026-11-18 | 2026-12-15 | 20 | 100% | M. Alvarez
2.2.1 | Backup current production environment | System Upgrade | 2026-11-18 | 2026-11-18 | 1 | 100% | M. Alvarez
2.2.2 | Apply platform upgrade — Dev environment | System Upgrade | 2026-11-19 | 2026-11-24 | 4 | 100% | M. Alvarez
2.2.3 | Smoke test Dev environment | System Upgrade | 2026-11-25 | 2026-11-26 | 2 | 100% | M. Alvarez
2.2.4 | Apply platform upgrade — Test environment | System Upgrade | 2026-11-27 | 2026-12-02 | 4 | 100% | M. Alvarez
2.2.5 | Smoke test Test environment | System Upgrade | 2026-12-03 | 2026-12-04 | 2 | 100% | M. Alvarez
2.2.6 | Apply platform upgrade — Staging environment | System Upgrade | 2026-12-07 | 2026-12-10 | 4 | 100% | M. Alvarez
2.2.7 | Configuration & parameter tuning | System Upgrade | 2026-12-11 | 2026-12-15 | 3 | 100% | M. Alvarez
2.3 | Regression Testing (Existing Functionality) | System Upgrade | 2026-12-16 | 2026-12-29 | 10 | 100% | M. Alvarez
2.3.1 | Execute regression suite — core functions | System Upgrade | 2026-12-16 | 2026-12-21 | 4 | 100% | M. Alvarez
2.3.2 | Execute regression suite — reporting functions | System Upgrade | 2026-12-22 | 2026-12-24 | 3 | 100% | M. Alvarez
2.3.3 | Log & triage defects | System Upgrade | 2026-12-25 | 2026-12-28 | 2 | 100% | M. Alvarez
2.3.4 | Retest resolved defects | System Upgrade | 2026-12-29 | 2026-12-29 | 1 | 100% | M. Alvarez
2.4 | Upgrade Validation & Sign-off | System Upgrade | 2026-12-30 | 2027-01-05 | 5 | 100% | M. Alvarez
2.4.1 | Performance benchmarking vs. baseline | System Upgrade | 2026-12-30 | 2026-12-31 | 2 | 100% | M. Alvarez
2.4.2 | Business stakeholder validation | System Upgrade | 2027-01-01 | 2027-01-04 | 2 | 100% | M. Alvarez
2.4.3 | Formal upgrade sign-off | System Upgrade | 2027-01-05 | 2027-01-05 | 1 | 100% | M. Alvarez
3 | Data Conversion | Data Conversion | 2027-01-06 | 2027-03-16 | 50 | 16% | T. McCormick
3.1 | Data Mapping — Member/Policy Data | Data Conversion | 2027-01-06 | 2027-01-19 | 10 | 80% | T. McCormick
3.1.1 | Inventory source data fields | Data Conversion | 2027-01-06 | 2027-01-07 | 2 | 100% | T. McCormick
3.1.2 | Identify target system field requirements | Data Conversion | 2027-01-08 | 2027-01-11 | 2 | 100% | T. McCormick
3.1.3 | Build field-level mapping document | Data Conversion | 2027-01-12 | 2027-01-14 | 3 | 100% | T. McCormick
3.1.4 | Identify data quality issues in source | Data Conversion | 2027-01-15 | 2027-01-15 | 1 | 100% | T. McCormick
3.1.5 | Define transformation rules | Data Conversion | 2027-01-18 | 2027-01-18 | 1 | 0% | T. McCormick
3.1.6 | Business SME review & sign-off | Data Conversion | 2027-01-19 | 2027-01-19 | 1 | 0% | T. McCormick
3.2 | Data Mapping — Provider/Producer Data | Data Conversion | 2027-01-06 | 2027-01-19 | 10 | 80% | T. McCormick
3.2.1 | Inventory source provider/producer fields | Data Conversion | 2027-01-06 | 2027-01-07 | 2 | 100% | T. McCormick
3.2.2 | Identify target system field requirements | Data Conversion | 2027-01-08 | 2027-01-11 | 2 | 100% | T. McCormick
3.2.3 | Build field-level mapping document | Data Conversion | 2027-01-12 | 2027-01-14 | 3 | 100% | T. McCormick
3.2.4 | Identify data quality issues | Data Conversion | 2027-01-15 | 2027-01-15 | 1 | 100% | T. McCormick
3.2.5 | Define transformation rules | Data Conversion | 2027-01-18 | 2027-01-18 | 1 | 0% | T. McCormick
3.2.6 | Business SME review & sign-off | Data Conversion | 2027-01-19 | 2027-01-19 | 1 | 0% | T. McCormick
3.3 | Data Mapping — Historical Claims | Data Conversion | 2027-01-06 | 2027-01-26 | 15 | 53% | T. McCormick
3.3.1 | Inventory source claims data fields | Data Conversion | 2027-01-06 | 2027-01-07 | 2 | 100% | T. McCormick
3.3.2 | Identify target system field requirements | Data Conversion | 2027-01-08 | 2027-01-11 | 2 | 100% | T. McCormick
3.3.3 | Build field-level mapping document | Data Conversion | 2027-01-12 | 2027-01-15 | 4 | 100% | T. McCormick
3.3.4 | Identify data quality issues (large historical volume) | Data Conversion | 2027-01-18 | 2027-01-20 | 3 | 0% | T. McCormick
3.3.5 | Define transformation rules | Data Conversion | 2027-01-21 | 2027-01-22 | 2 | 0% | T. McCormick
3.3.6 | Business SME review & sign-off | Data Conversion | 2027-01-25 | 2027-01-26 | 2 | 0% | T. McCormick
3.4 | Conversion Build & Cleansing | Data Conversion | 2027-01-27 | 2027-02-23 | 20 | 0% | T. McCormick
3.4.1 | Build extract scripts (source system) | Data Conversion | 2027-01-27 | 2027-02-01 | 4 | 0% | T. McCormick
3.4.2 | Build cleansing/scrubbing rules | Data Conversion | 2027-02-02 | 2027-02-08 | 5 | 0% | T. McCormick
3.4.2.1 | Define null-handling rules | Data Conversion | 2027-02-02 | 2027-02-02 | 1 | 0% | T. McCormick
3.4.2.2 | Define deduplication rules | Data Conversion | 2027-02-03 | 2027-02-03 | 1 | 0% | T. McCormick
3.4.2.3 | Define standardization rules (formats, codes) | Data Conversion | 2027-02-04 | 2027-02-04 | 1 | 0% | T. McCormick
3.4.2.4 | Build cleansing scripts | Data Conversion | 2027-02-05 | 2027-02-05 | 1 | 0% | T. McCormick
3.4.2.5 | Unit test cleansing scripts | Data Conversion | 2027-02-08 | 2027-02-08 | 1 | 0% | T. McCormick
3.4.3 | Build transformation logic | Data Conversion | 2027-02-09 | 2027-02-15 | 5 | 0% | T. McCormick
3.4.4 | Build load scripts (target system) | Data Conversion | 2027-02-16 | 2027-02-19 | 4 | 0% | T. McCormick
3.4.5 | Unit test conversion scripts | Data Conversion | 2027-02-22 | 2027-02-22 | 1 | 0% | T. McCormick
3.4.6 | Peer/technical review of conversion code | Data Conversion | 2027-02-23 | 2027-02-23 | 1 | 0% | T. McCormick
3.5 | Conversion Dry Run 1 | Data Conversion | 2027-02-24 | 2027-03-02 | 5 | 0% | T. McCormick
3.5.1 | Execute full extract from source | Data Conversion | 2027-02-24 | 2027-02-24 | 1 | 0% | T. McCormick
3.5.2 | Execute cleansing & transformation pass | Data Conversion | 2027-02-25 | 2027-02-25 | 1 | 0% | T. McCormick
3.5.3 | Execute load into target (test environment) | Data Conversion | 2027-02-26 | 2027-02-26 | 1 | 0% | T. McCormick
3.5.4 | Record volume/counts (source vs. loaded) | Data Conversion | 2027-03-01 | 2027-03-01 | 1 | 0% | T. McCormick
3.5.5 | Identify failed records & log defects | Data Conversion | 2027-03-02 | 2027-03-02 | 1 | 0% | T. McCormick
3.6 | Conversion Dry Run 2 (post-fixes) | Data Conversion | 2027-03-03 | 2027-03-09 | 5 | 0% | T. McCormick
3.6.1 | Apply defect fixes from Dry Run 1 | Data Conversion | 2027-03-03 | 2027-03-04 | 2 | 0% | T. McCormick
3.6.2 | Re-execute extract, transform, load | Data Conversion | 2027-03-05 | 2027-03-08 | 2 | 0% | T. McCormick
3.6.3 | Validate fixes resolved | Data Conversion | 2027-03-09 | 2027-03-09 | 1 | 0% | T. McCormick
3.7 | Data Reconciliation & Sign-off | Data Conversion | 2027-03-10 | 2027-03-16 | 5 | 0% | T. McCormick
3.7.1 | Run reconciliation reports (source vs. target) | Data Conversion | 2027-03-10 | 2027-03-10 | 1 | 0% | T. McCormick
3.7.2 | Spot-check sample records for accuracy | Data Conversion | 2027-03-11 | 2027-03-11 | 1 | 0% | T. McCormick
3.7.3 | Business SME validation of converted data | Data Conversion | 2027-03-12 | 2027-03-12 | 1 | 0% | T. McCormick
3.7.4 | Document known exceptions/variances | Data Conversion | 2027-03-15 | 2027-03-15 | 1 | 0% | T. McCormick
3.7.5 | Formal sign-off (Conversion Lead & Business Owner) | Data Conversion | 2027-03-16 | 2027-03-16 | 1 | 0% | T. McCormick
4 | Integration Build (Agile) | Integration Build (Agile) | 2027-01-06 | 2027-05-11 | 90 | 9% | C. Tyrrell
4.1 | Billing Integration — Sprints 1-2 | Integration Build (Agile) | 2027-01-06 | 2027-02-02 | 20 | 40% | D. Okafor
4.1.1 | Interface design & spec review | Integration Build (Agile) | 2027-01-06 | 2027-01-11 | 4 | 100% | D. Okafor
4.1.2 | Build inbound interface (Billing → Platform) | Integration Build (Agile) | 2027-01-12 | 2027-01-18 | 5 | 80% | D. Okafor
4.1.2.1 | Define message schema/payload | Integration Build (Agile) | 2027-01-12 | 2027-01-12 | 1 | 100% | D. Okafor
4.1.2.2 | Build listener/endpoint | Integration Build (Agile) | 2027-01-13 | 2027-01-13 | 1 | 100% | D. Okafor
4.1.2.3 | Build field mapping & transformation logic | Integration Build (Agile) | 2027-01-14 | 2027-01-15 | 2 | 100% | D. Okafor
4.1.2.4 | Code review | Integration Build (Agile) | 2027-01-18 | 2027-01-18 | 1 | 0% | D. Okafor
4.1.3 | Build outbound interface (Platform → Billing) | Integration Build (Agile) | 2027-01-19 | 2027-01-25 | 5 | 0% | D. Okafor
4.1.4 | Unit test interface endpoints | Integration Build (Agile) | 2027-01-26 | 2027-01-27 | 2 | 0% | D. Okafor
4.1.5 | Sprint 1 review/demo | Integration Build (Agile) | 2027-01-28 | 2027-01-28 | 1 | 0% | D. Okafor
4.1.6 | Error handling & performance testing | Integration Build (Agile) | 2027-01-29 | 2027-02-01 | 2 | 0% | D. Okafor
4.1.7 | Integration test w/ converted data & Sprint 2 review | Integration Build (Agile) | 2027-02-02 | 2027-02-02 | 1 | 0% | D. Okafor
4.2 | Underwriting Integration — Sprints 1-2 | Integration Build (Agile) | 2027-01-06 | 2027-02-02 | 20 | 40% | S. Lindqvist
4.2.1 | Interface design & spec review | Integration Build (Agile) | 2027-01-06 | 2027-01-11 | 4 | 100% | S. Lindqvist
4.2.2 | Build inbound interface (Underwriting → Platform) | Integration Build (Agile) | 2027-01-12 | 2027-01-18 | 5 | 80% | S. Lindqvist
4.2.3 | Build outbound interface (Platform → Underwriting) | Integration Build (Agile) | 2027-01-19 | 2027-01-25 | 5 | 0% | S. Lindqvist
4.2.4 | Unit test interface endpoints | Integration Build (Agile) | 2027-01-26 | 2027-01-27 | 2 | 0% | S. Lindqvist
4.2.5 | Sprint 1 review/demo | Integration Build (Agile) | 2027-01-28 | 2027-01-28 | 1 | 0% | S. Lindqvist
4.2.6 | Error handling & performance testing | Integration Build (Agile) | 2027-01-29 | 2027-02-01 | 2 | 0% | S. Lindqvist
4.2.7 | Integration test & Sprint 2 review | Integration Build (Agile) | 2027-02-02 | 2027-02-02 | 1 | 0% | S. Lindqvist
4.3 | Claims Administration Integration — Sprints 3-4 | Integration Build (Agile) | 2027-03-17 | 2027-04-13 | 20 | 0% | K. Delgado
4.3.1 | Interface design & spec review | Integration Build (Agile) | 2027-03-17 | 2027-03-22 | 4 | 0% | K. Delgado
4.3.2 | Build inbound interface (Claims → Platform) | Integration Build (Agile) | 2027-03-23 | 2027-03-29 | 5 | 0% | K. Delgado
4.3.3 | Build outbound interface (Platform → Claims) | Integration Build (Agile) | 2027-03-30 | 2027-04-05 | 5 | 0% | K. Delgado
4.3.4 | Unit test interface endpoints | Integration Build (Agile) | 2027-04-06 | 2027-04-07 | 2 | 0% | K. Delgado
4.3.5 | Sprint 3 review/demo | Integration Build (Agile) | 2027-04-08 | 2027-04-08 | 1 | 0% | K. Delgado
4.3.6 | Error handling & performance testing | Integration Build (Agile) | 2027-04-09 | 2027-04-12 | 2 | 0% | K. Delgado
4.3.7 | Integration test w/ converted claims data & Sprint 4 review | Integration Build (Agile) | 2027-04-13 | 2027-04-13 | 1 | 0% | K. Delgado
4.4 | Commission Management Integration — Sprints 3-4 | Integration Build (Agile) | 2027-01-06 | 2027-02-02 | 20 | 40% | P. Novak
4.4.1 | Interface design & spec review | Integration Build (Agile) | 2027-01-06 | 2027-01-11 | 4 | 100% | P. Novak
4.4.2 | Build inbound interface (Commission → Platform) | Integration Build (Agile) | 2027-01-12 | 2027-01-18 | 5 | 80% | P. Novak
4.4.3 | Build outbound interface (Platform → Commission) | Integration Build (Agile) | 2027-01-19 | 2027-01-25 | 5 | 0% | P. Novak
4.4.4 | Unit test interface endpoints | Integration Build (Agile) | 2027-01-26 | 2027-01-27 | 2 | 0% | P. Novak
4.4.5 | Sprint 3 review/demo | Integration Build (Agile) | 2027-01-28 | 2027-01-28 | 1 | 0% | P. Novak
4.4.6 | Error handling & performance testing | Integration Build (Agile) | 2027-01-29 | 2027-02-01 | 2 | 0% | P. Novak
4.4.7 | Integration test & Sprint 4 review | Integration Build (Agile) | 2027-02-02 | 2027-02-02 | 1 | 0% | P. Novak
4.5 | Data Warehouse/Reporting Integration — Sprints 5-6 | Integration Build (Agile) | 2027-04-14 | 2027-05-11 | 20 | 0% | A. Reyes
4.5.1 | Define reporting data model/schema | Integration Build (Agile) | 2027-04-14 | 2027-04-19 | 4 | 0% | A. Reyes
4.5.2 | Build ETL feed to Data Warehouse | Integration Build (Agile) | 2027-04-20 | 2027-04-27 | 6 | 0% | A. Reyes
4.5.3 | Build standard report templates | Integration Build (Agile) | 2027-04-28 | 2027-05-03 | 4 | 0% | A. Reyes
4.5.4 | Unit test ETL & reports | Integration Build (Agile) | 2027-05-04 | 2027-05-05 | 2 | 0% | A. Reyes
4.5.5 | Sprint 5 review/demo | Integration Build (Agile) | 2027-05-06 | 2027-05-06 | 1 | 0% | A. Reyes
4.5.6 | Performance testing (large data volume) | Integration Build (Agile) | 2027-05-07 | 2027-05-10 | 2 | 0% | A. Reyes
4.5.7 | Integration test & Sprint 6 review | Integration Build (Agile) | 2027-05-11 | 2027-05-11 | 1 | 0% | A. Reyes
4.6 | Payment Processing Integration — Sprints 5-6 | Integration Build (Agile) | 2027-02-03 | 2027-03-02 | 20 | 0% | B. Sato
4.6.1 | Interface design & spec review | Integration Build (Agile) | 2027-02-03 | 2027-02-08 | 4 | 0% | B. Sato
4.6.2 | Build payment gateway connection | Integration Build (Agile) | 2027-02-09 | 2027-02-15 | 5 | 0% | B. Sato
4.6.3 | Build reconciliation/settlement logic | Integration Build (Agile) | 2027-02-16 | 2027-02-22 | 5 | 0% | B. Sato
4.6.4 | Unit test interface endpoints | Integration Build (Agile) | 2027-02-23 | 2027-02-24 | 2 | 0% | B. Sato
4.6.5 | Sprint 5 review/demo | Integration Build (Agile) | 2027-02-25 | 2027-02-25 | 1 | 0% | B. Sato
4.6.6 | Error handling & PCI compliance validation | Integration Build (Agile) | 2027-02-26 | 2027-03-01 | 2 | 0% | B. Sato
4.6.7 | Integration test & Sprint 6 review | Integration Build (Agile) | 2027-03-02 | 2027-03-02 | 1 | 0% | B. Sato
5 | Testing (Functional, System, UAT) | Testing (Functional, System, UAT) | 2027-01-06 | 2027-08-10 | 155 | 5% | R. Whitfield
5.1 | Functional Testing (ongoing, per sprint) | Testing (Functional, System, UAT) | 2027-01-06 | 2027-05-13 | 92 | 9% | R. Whitfield
5.1.0 | Offshore QA Team Onboarding & Coordination Setup | Testing (Functional, System, UAT) | 2027-01-06 | 2027-01-07 | 2 | 100% | P. Sundaram
5.1.1 | Functional test planning & test case development | Testing (Functional, System, UAT) | 2027-01-08 | 2027-01-21 | 10 | 60% | R. Whitfield
5.1.2 | Functional testing — Billing & Payment integrations | Testing (Functional, System, UAT) | 2027-01-22 | 2027-02-18 | 20 | 0% | P. Sundaram
5.1.3 | Functional testing — Underwriting & Commission integrations | Testing (Functional, System, UAT) | 2027-02-19 | 2027-03-18 | 20 | 0% | P. Sundaram
5.1.4 | Functional testing — Claims & Data Warehouse integrations | Testing (Functional, System, UAT) | 2027-03-19 | 2027-04-15 | 20 | 0% | P. Sundaram
5.1.5 | Functional defect triage & retest | Testing (Functional, System, UAT) | 2027-04-16 | 2027-05-13 | 20 | 0% | R. Whitfield
5.2 | System Testing (end-to-end) | Testing (Functional, System, UAT) | 2027-05-14 | 2027-06-03 | 15 | 0% | R. Whitfield
5.2.1 | System test planning & environment setup | Testing (Functional, System, UAT) | 2027-05-14 | 2027-05-17 | 2 | 0% | R. Whitfield
5.2.2 | End-to-end scenarios — enrollment to claims | Testing (Functional, System, UAT) | 2027-05-18 | 2027-05-21 | 4 | 0% | R. Whitfield
5.2.3 | End-to-end scenarios — billing to payment | Testing (Functional, System, UAT) | 2027-05-24 | 2027-05-27 | 4 | 0% | R. Whitfield
5.2.4 | End-to-end scenarios — reporting | Testing (Functional, System, UAT) | 2027-05-28 | 2027-06-01 | 3 | 0% | R. Whitfield
5.2.5 | System test defect triage | Testing (Functional, System, UAT) | 2027-06-02 | 2027-06-03 | 2 | 0% | R. Whitfield
5.2A | Security & Penetration Testing | Testing (Functional, System, UAT) | 2027-06-04 | 2027-06-10 | 5 | 0% | R. Whitfield
5.2A.1 | External penetration test (vendor-conducted) | Testing (Functional, System, UAT) | 2027-06-04 | 2027-06-08 | 3 | 0% | R. Whitfield
5.2A.2 | Vulnerability remediation & retest | Testing (Functional, System, UAT) | 2027-06-09 | 2027-06-09 | 1 | 0% | M. Alvarez
5.2A.3 | Security sign-off (Compliance/Legal) | Testing (Functional, System, UAT) | 2027-06-10 | 2027-06-10 | 1 | 0% | N. Sharma
5.2B | Performance & Load Testing (System-Wide) | Testing (Functional, System, UAT) | 2027-06-11 | 2027-06-17 | 5 | 0% | R. Whitfield
5.2B.1 | Define load profiles & performance targets | Testing (Functional, System, UAT) | 2027-06-11 | 2027-06-11 | 1 | 0% | R. Whitfield
5.2B.2 | Execute full-volume load test across platform & integrations | Testing (Functional, System, UAT) | 2027-06-14 | 2027-06-16 | 3 | 0% | M. Alvarez
5.2B.3 | Analyze results & tune performance bottlenecks | Testing (Functional, System, UAT) | 2027-06-17 | 2027-06-17 | 1 | 0% | M. Alvarez
5.2C | Disaster Recovery / Failover Testing | Testing (Functional, System, UAT) | 2027-06-18 | 2027-06-22 | 3 | 0% | M. Alvarez
5.2C.1 | Execute planned failover to DR environment | Testing (Functional, System, UAT) | 2027-06-18 | 2027-06-18 | 1 | 0% | M. Alvarez
5.2C.2 | Validate system functionality & data integrity on DR | Testing (Functional, System, UAT) | 2027-06-21 | 2027-06-21 | 1 | 0% | R. Whitfield
5.2C.3 | Failback to primary & DR test sign-off | Testing (Functional, System, UAT) | 2027-06-22 | 2027-06-22 | 1 | 0% | M. Alvarez
5.2D | SOX Compliance Testing & Sign-off | Testing (Functional, System, UAT) | 2027-06-23 | 2027-06-29 | 5 | 0% | G. Fenwick
5.2D.1 | Execute testing of updated SOX-relevant controls | Testing (Functional, System, UAT) | 2027-06-23 | 2027-06-25 | 3 | 0% | G. Fenwick
5.2D.2 | Internal Audit review of control testing results | Testing (Functional, System, UAT) | 2027-06-28 | 2027-06-28 | 1 | 0% | G. Fenwick
5.2D.3 | Formal SOX compliance sign-off | Testing (Functional, System, UAT) | 2027-06-29 | 2027-06-29 | 1 | 0% | G. Fenwick
5.3 | Defect Remediation Cycle | Testing (Functional, System, UAT) | 2027-06-30 | 2027-07-13 | 10 | 0% | R. Whitfield
5.3.1 | Prioritize defects (severity/priority) | Testing (Functional, System, UAT) | 2027-06-30 | 2027-06-30 | 1 | 0% | R. Whitfield
5.3.2 | Development fixes — critical/high defects | Testing (Functional, System, UAT) | 2027-07-01 | 2027-07-07 | 5 | 0% | R. Whitfield
5.3.3 | Regression retest of fixes | Testing (Functional, System, UAT) | 2027-07-08 | 2027-07-12 | 3 | 0% | R. Whitfield
5.3.4 | Defect closure sign-off | Testing (Functional, System, UAT) | 2027-07-13 | 2027-07-13 | 1 | 0% | R. Whitfield
5.4 | User Acceptance Testing (UAT) | Testing (Functional, System, UAT) | 2027-07-14 | 2027-08-03 | 15 | 0% | R. Whitfield
5.4.1 | UAT planning & test script development | Testing (Functional, System, UAT) | 2027-07-14 | 2027-07-16 | 3 | 0% | R. Whitfield
5.4.2 | UAT execution — Underwriting & New Business | Testing (Functional, System, UAT) | 2027-07-19 | 2027-07-21 | 3 | 0% | R. Whitfield
5.4.3 | UAT execution — Claims Administration | Testing (Functional, System, UAT) | 2027-07-22 | 2027-07-26 | 3 | 0% | R. Whitfield
5.4.4 | UAT execution — Billing & Payments | Testing (Functional, System, UAT) | 2027-07-27 | 2027-07-29 | 3 | 0% | R. Whitfield
5.4.5 | UAT defect triage & fixes | Testing (Functional, System, UAT) | 2027-07-30 | 2027-08-03 | 3 | 0% | R. Whitfield
5.5 | UAT Sign-off | Testing (Functional, System, UAT) | 2027-08-04 | 2027-08-10 | 5 | 0% | R. Whitfield
5.5.1 | Consolidate UAT results | Testing (Functional, System, UAT) | 2027-08-04 | 2027-08-04 | 1 | 0% | R. Whitfield
5.5.2 | Business stakeholder review | Testing (Functional, System, UAT) | 2027-08-05 | 2027-08-06 | 2 | 0% | R. Whitfield
5.5.3 | Formal UAT sign-off (Go/No-Go input) | Testing (Functional, System, UAT) | 2027-08-09 | 2027-08-10 | 2 | 0% | R. Whitfield
6 | Cutover & Hypercare | Cutover & Hypercare | 2027-08-11 | 2027-11-02 | 60 | 0% | C. Tyrrell
6.1 | Cutover Planning & Rehearsal | Cutover & Hypercare | 2027-08-11 | 2027-08-17 | 5 | 0% | C. Tyrrell
6.1.1 | Develop detailed cutover runbook | Cutover & Hypercare | 2027-08-11 | 2027-08-12 | 2 | 0% | C. Tyrrell
6.1.2 | Cutover rehearsal (dry run) | Cutover & Hypercare | 2027-08-13 | 2027-08-16 | 2 | 0% | C. Tyrrell
6.1.3 | Go/No-Go readiness review | Cutover & Hypercare | 2027-08-17 | 2027-08-17 | 1 | 0% | C. Tyrrell
6.2 | Go-Live / Production Cutover | Cutover & Hypercare | 2027-08-18 | 2027-08-24 | 5 | 0% | C. Tyrrell
6.2.1 | Final data conversion to production | Cutover & Hypercare | 2027-08-18 | 2027-08-18 | 1 | 0% | C. Tyrrell
6.2.2 | Production deployment — platform & integrations | Cutover & Hypercare | 2027-08-19 | 2027-08-20 | 2 | 0% | C. Tyrrell
6.2.3 | Post-deployment smoke testing | Cutover & Hypercare | 2027-08-23 | 2027-08-23 | 1 | 0% | C. Tyrrell
6.2.4 | Go-live communication & business sign-off | Cutover & Hypercare | 2027-08-24 | 2027-08-24 | 1 | 0% | C. Tyrrell
6.3 | Hypercare / Stabilization Monitoring | Cutover & Hypercare | 2027-08-25 | 2027-09-14 | 15 | 0% | C. Tyrrell
6.3.1 | Daily production monitoring & issue triage | Cutover & Hypercare | 2027-08-25 | 2027-09-07 | 10 | 0% | C. Tyrrell
6.3.2 | Priority defect fixes during hypercare | Cutover & Hypercare | 2027-09-08 | 2027-09-10 | 3 | 0% | C. Tyrrell
6.3.3 | Hypercare exit readiness review | Cutover & Hypercare | 2027-09-13 | 2027-09-14 | 2 | 0% | C. Tyrrell
6.3B | Post-Go-Live Customer Experience Monitoring & Feedback Collection | Cutover & Hypercare | 2027-08-25 | 2027-10-05 | 30 | 0% | V. Alaoui
6.3B.1 | Monitor customer satisfaction & support ticket sentiment | Cutover & Hypercare | 2027-08-25 | 2027-09-30 | 27 | 0% | V. Alaoui
6.3B.2 | Consolidate CX feedback & report to Steering Committee | Cutover & Hypercare | 2027-10-01 | 2027-10-05 | 3 | 0% | V. Alaoui
6.4 | Warranty Support Period (3-Week Vendor Warranty) | Cutover & Hypercare | 2027-09-15 | 2027-10-05 | 15 | 0% | W. Donnelly
6.4.1 | Vendor warranty support activation & SLA confirmation | Cutover & Hypercare | 2027-09-15 | 2027-09-15 | 1 | 0% | W. Donnelly
6.4.2 | Ongoing defect monitoring under vendor warranty | Cutover & Hypercare | 2027-09-16 | 2027-09-29 | 10 | 0% | M. Alvarez
6.4.3 | Warranty-period defect resolution tracking | Cutover & Hypercare | 2027-09-30 | 2027-10-04 | 3 | 0% | W. Donnelly
6.4.4 | Warranty exit review & sign-off | Cutover & Hypercare | 2027-10-05 | 2027-10-05 | 1 | 0% | C. Tyrrell
6.5 | Legacy System Decommissioning | Cutover & Hypercare | 2027-10-06 | 2027-10-19 | 10 | 0% | M. Alvarez
6.5.1 | Confirm data retention requirements & archive legacy data | Cutover & Hypercare | 2027-10-06 | 2027-10-11 | 4 | 0% | T. McCormick
6.5.2 | Terminate legacy vendor licenses & contracts | Cutover & Hypercare | 2027-10-12 | 2027-10-13 | 2 | 0% | W. Donnelly
6.5.3 | Decommission legacy infrastructure/environment | Cutover & Hypercare | 2027-10-14 | 2027-10-18 | 3 | 0% | M. Alvarez
6.5.4 | Decommissioning sign-off (Compliance/Legal) | Cutover & Hypercare | 2027-10-19 | 2027-10-19 | 1 | 0% | N. Sharma
6.6 | Production Support Transition | Cutover & Hypercare | 2027-10-20 | 2027-10-26 | 5 | 0% | E. Kowalski
6.6.1 | Finalize support runbooks & knowledge base | Cutover & Hypercare | 2027-10-20 | 2027-10-21 | 2 | 0% | M. Alvarez
6.6.2 | Knowledge transfer sessions with Production Support team | Cutover & Hypercare | 2027-10-22 | 2027-10-25 | 2 | 0% | E. Kowalski
6.6.3 | Formal handover & Production Support acceptance sign-off | Cutover & Hypercare | 2027-10-26 | 2027-10-26 | 1 | 0% | C. Tyrrell
6.7 | Project Closeout & Lessons Learned | Cutover & Hypercare | 2027-10-27 | 2027-11-02 | 5 | 0% | C. Tyrrell
6.7.1 | Finalize project documentation & handover to support | Cutover & Hypercare | 2027-10-27 | 2027-10-28 | 2 | 0% | C. Tyrrell
6.7.2 | Lessons learned session | Cutover & Hypercare | 2027-10-29 | 2027-10-29 | 1 | 0% | C. Tyrrell
6.7.3 | Formal project closure & sign-off | Cutover & Hypercare | 2027-11-01 | 2027-11-02 | 2 | 0% | C. Tyrrell
7 | Change Management & Training | Change Management & Training | 2026-09-16 | 2027-08-17 | 240 | 37% | L. Bergström
7.1 | Stakeholder Impact Assessment | Change Management & Training | 2026-09-16 | 2026-09-29 | 10 | 100% | L. Bergström
7.1.1 | Identify impacted roles & workflows | Change Management & Training | 2026-09-16 | 2026-09-21 | 4 | 100% | L. Bergström
7.1.2 | Assess change readiness by department | Change Management & Training | 2026-09-22 | 2026-09-25 | 4 | 100% | L. Bergström
7.1.3 | Document impact assessment findings | Change Management & Training | 2026-09-28 | 2026-09-29 | 2 | 100% | L. Bergström
7.2 | Communication Plan Development | Change Management & Training | 2026-09-30 | 2026-10-13 | 10 | 100% | L. Bergström
7.2.1 | Define communication audiences & channels | Change Management & Training | 2026-09-30 | 2026-10-02 | 3 | 100% | L. Bergström
7.2.2 | Build communication calendar & key messages | Change Management & Training | 2026-10-05 | 2026-10-08 | 4 | 100% | L. Bergström
7.2.3 | Sponsor review & approval | Change Management & Training | 2026-10-09 | 2026-10-13 | 3 | 100% | L. Bergström
7.3 | Training Needs Analysis | Change Management & Training | 2027-03-17 | 2027-03-30 | 10 | 0% | H. Osei
7.3.1 | Assess role-based training requirements | Change Management & Training | 2027-03-17 | 2027-03-23 | 5 | 0% | H. Osei
7.3.2 | Define training delivery approach (in-person/virtual) | Change Management & Training | 2027-03-24 | 2027-03-26 | 3 | 0% | H. Osei
7.3.3 | Finalize training curriculum outline | Change Management & Training | 2027-03-29 | 2027-03-30 | 2 | 0% | H. Osei
7.4 | Training Material Development | Change Management & Training | 2027-03-31 | 2027-04-27 | 20 | 0% | H. Osei
7.4.1 | Develop Underwriting & New Business training materials | Change Management & Training | 2027-03-31 | 2027-04-06 | 5 | 0% | H. Osei
7.4.2 | Develop Claims Administration training materials | Change Management & Training | 2027-04-07 | 2027-04-13 | 5 | 0% | H. Osei
7.4.3 | Develop Billing & Payments training materials | Change Management & Training | 2027-04-14 | 2027-04-20 | 5 | 0% | H. Osei
7.4.4 | Develop Compliance & Customer Service training materials | Change Management & Training | 2027-04-21 | 2027-04-27 | 5 | 0% | H. Osei
7.5 | End-User Training Delivery | Change Management & Training | 2027-06-16 | 2027-07-06 | 15 | 0% | H. Osei
7.5.1 | Train Underwriting & New Business users | Change Management & Training | 2027-06-16 | 2027-06-18 | 3 | 0% | H. Osei
7.5.2 | Train Claims Administration users | Change Management & Training | 2027-06-21 | 2027-06-23 | 3 | 0% | H. Osei
7.5.3 | Train Billing & Payments users | Change Management & Training | 2027-06-24 | 2027-06-28 | 3 | 0% | H. Osei
7.5.4 | Train Compliance & Customer Service users | Change Management & Training | 2027-06-29 | 2027-07-01 | 3 | 0% | H. Osei
7.5.5 | Training feedback collection & reinforcement sessions | Change Management & Training | 2027-07-02 | 2027-07-06 | 3 | 0% | H. Osei
7.6 | Go-Live Readiness Communications | Change Management & Training | 2027-07-14 | 2027-07-20 | 5 | 0% | L. Bergström
7.6.1 | Send go-live readiness notices to end users | Change Management & Training | 2027-07-14 | 2027-07-15 | 2 | 0% | L. Bergström
7.6.2 | Publish quick-reference guides & FAQs | Change Management & Training | 2027-07-16 | 2027-07-20 | 3 | 0% | L. Bergström
7.6B | External Customer Communications for Go-Live | Change Management & Training | 2027-07-14 | 2027-07-20 | 5 | 0% | V. Alaoui
7.6B.1 | Draft customer-facing notices (portal, billing, statements) | Change Management & Training | 2027-07-14 | 2027-07-16 | 3 | 0% | V. Alaoui
7.6B.2 | Distribute customer communications & update self-service channels | Change Management & Training | 2027-07-19 | 2027-07-20 | 2 | 0% | V. Alaoui
7.7 | Post-Go-Live Support Desk Setup | Change Management & Training | 2027-07-21 | 2027-08-17 | 20 | 0% | H. Osei
7.7.1 | Staff & train hypercare support desk | Change Management & Training | 2027-07-21 | 2027-07-27 | 5 | 0% | H. Osei
7.7.2 | Operate support desk during hypercare | Change Management & Training | 2027-07-28 | 2027-08-17 | 15 | 0% | H. Osei
8 | Program Governance & Risk Management | Program Governance & Risk Management | 2026-08-19 | 2027-08-17 | 260 | 42% | E. Kowalski
8.1 | Program Reporting & Steering Committee | Program Governance & Risk Management | 2026-08-19 | 2027-08-17 | 260 | 42% | E. Kowalski
8.1.1 | Establish steering committee & reporting cadence | Program Governance & Risk Management | 2026-08-19 | 2026-08-25 | 5 | 100% | E. Kowalski
8.1.2 | Weekly project status reporting | Program Governance & Risk Management | 2026-08-26 | 2027-08-10 | 250 | 41% | E. Kowalski
8.1.3 | Monthly steering committee reviews | Program Governance & Risk Management | 2026-08-26 | 2027-08-10 | 250 | 41% | E. Kowalski
8.2 | Risk & Issue Management | Program Governance & Risk Management | 2026-08-19 | 2027-08-17 | 260 | 42% | E. Kowalski
8.2.1 | Establish risk register & escalation process | Program Governance & Risk Management | 2026-08-19 | 2026-08-25 | 5 | 100% | E. Kowalski
8.2.2 | Ongoing risk & issue tracking | Program Governance & Risk Management | 2026-09-02 | 2027-08-10 | 245 | 40% | E. Kowalski
8.2.3 | Monthly risk mitigation plan reviews | Program Governance & Risk Management | 2026-09-02 | 2027-08-10 | 245 | 40% | E. Kowalski
8.3 | Budget & Resource Management | Program Governance & Risk Management | 2026-08-19 | 2027-08-13 | 258 | 42% | E. Kowalski
8.3.1 | Build resource plan & staffing model | Program Governance & Risk Management | 2026-08-19 | 2026-09-01 | 10 | 100% | E. Kowalski
8.3.1B | Establish Cost Baseline & Steering Committee Approval | Program Governance & Risk Management | 2026-09-02 | 2026-09-04 | 3 | 100% | E. Kowalski
8.3.2 | Ongoing budget tracking & variance reporting | Program Governance & Risk Management | 2026-09-07 | 2027-08-13 | 245 | 39% | E. Kowalski
8.3.3 | Vendor invoice management & reconciliation | Program Governance & Risk Management | 2026-10-05 | 2027-08-06 | 220 | 34% | W. Donnelly
All 315 line items (phases, sub-phases, and individual tasks) are shown here exactly as maintained in the Project Plan Console. Dates are calculated from the program's Day 0 (28 Jul 2026, the Tuesday preceding Project Kickoff on 04 Aug 2026), using working-day arithmetic. % Complete reflects a straight-line (linear) progress assumption between each task's start and finish date as of the 15 Jan 2027 status date — actual task-level progress may vary and should be confirmed with task owners.

## Phase Summary
Phase Summary
% Complete as of 15 Jan 2027 (straight-line progress assumption).
Phase | Start | Finish | Duration (d) | % Complete | Phase Owner
1 · Initiation & Requirements | 2026-07-28 | 2026-11-03 | 71 | 100% | C. Tyrrell
2 · System Upgrade | 2026-11-04 | 2027-01-05 | 45 | 100% | M. Alvarez
3 · Data Conversion | 2027-01-06 | 2027-03-16 | 50 | 16% | T. McCormick
4 · Integration Build (Agile) | 2027-01-06 | 2027-05-11 | 90 | 9% | C. Tyrrell
5 · Testing (Functional, System, UAT) | 2027-01-06 | 2027-08-10 | 155 | 5% | R. Whitfield
6 · Cutover & Hypercare | 2027-08-11 | 2027-11-02 | 60 | 0% | C. Tyrrell
7 · Change Management & Training | 2026-09-16 | 2027-08-17 | 240 | 37% | L. Bergström
8 · Program Governance & Risk Management | 2026-08-19 | 2027-08-17 | 260 | 42% | E. Kowalski