RACI Matrix

Enrollment & Claims Platform Modernization

This program tracks responsibility assignment in two complementary RACI matrices, deliberately kept separate rather than merged into one long table: Deliverable Sign-off covers work-product approvals; Governance-Process covers program-governance decisions (change requests, risk acceptance, exceptions), defined in full in the Project Governance Model §3.1. Neither duplicates the other.

R = Responsible (does the work)   ·   A = Accountable (owns the outcome)   ·   C = Consulted   ·   I = Informed

Deliverable Sign-off RACI

| Deliverable / Decision | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Requirements Sign-off | F. Jones | C. Tyrrell | Steering Committee, Business Units | N. Sharma |
| Vendor Selection & SOW | W. Donnelly | C. Tyrrell | Steering Committee | N. Sharma, J. Albert |
| System Upgrade Validation | M. Alvarez | C. Tyrrell | J. Albert | R. Whitfield |
| Data Conversion Sign-off | T. McCormick | C. Tyrrell | F. Jones | Business Data Owners |
| Integration Build (per track) | Track Developer | J. Albert | C. Tyrrell | R. Whitfield |
| Security & Pen Test Sign-off | R. Whitfield | N. Sharma | M. Alvarez | G. Fenwick |
| SOX Compliance Sign-off | G. Fenwick | N. Sharma | C. Tyrrell | Steering Committee |
| UAT Sign-off | R. Whitfield | C. Tyrrell | Business Units | Steering Committee |
| Go-Live / Cutover Decision | C. Tyrrell | Steering Committee | All Track Leads | All Stakeholders |

Source of record: PM Plan §9.2.

Governance-Process RACI

| Governance Activity | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Approve Tier 2 Change Request | PMO Director | Steering Committee | PM, affected Leads | All Stakeholders |
| Approve Tier 3 Change Request | PMO Director | Executive Sponsor | Steering Committee | All Stakeholders |
| Accept High-Scored Risk (≥7) | Program Manager | Steering Committee | Risk Owner, PMO | Executive Sponsor |
| Authorize SOX Exception | Chief Compliance Officer | Executive Sponsor | Steering Committee | Program Manager |
| Approve Vendor SOW Change | Vendor/Procurement Mgr | Steering Cmte / PM | PMO Director | Executive Sponsor |
| Quarterly Governance Review | PMO Director | Steering Committee | Program Manager | Executive Sponsor |

Source of record: Project Governance Model §3.1.

Illustrative program data — created to demonstrate PMBOK-standard program management practice, not a real client engagement.