## Risks
Risk Register
ID | Risk | Score | Owner | Status | Response
R-001 | Historical claims data quality issues could extend Data Conversion if root-cause cleansing proves insufficient | 9 (High/High) | T. McCormick | Watch | Early profiling & automated cleansing rules underway ahead of Dry Run 2; contingency reserved for a third Dry Run
R-002 | Offshore/onshore QA coordination gaps could reduce testing throughput | 4 (Medium/Medium) | R. Whitfield | Mitigated | Daily overlap-hour standup in place; Offshore QA Coordination Lead role added (CR-007)
R-003 | Vendor SOW negotiation delay could push back Environment Provisioning | 6 (Medium/High) | W. Donnelly | Mitigated | Backup vendor pre-qualified as contingency
R-004 | Mid-program state insurance filing/reporting requirement change could add unplanned compliance scope | 3 (Low/Medium) | N. Sharma | Monitoring | Compliance monitoring regulatory calendar; no action needed at this time
R-005 | Legacy system documentation gaps could complicate Decommissioning planning | 3 (Low/Medium) | M. Alvarez | Monitoring | Knowledge transfer sessions scheduled ahead of Phase 6
R-006 | Key resource attrition (particularly Solution Architect capacity) could disrupt technical continuity | 4 (Low/High) | C. Tyrrell | Mitigated | Cross-training as contingency, not prevention

## Assumptions
Assumptions
ID | Assumption | Owner
A-001 | Existing network and security infrastructure is sufficient to support the upgraded platform without separate capital investment | C. Tyrrell
A-002 | Named resources are available at their planned allocation; no extended unplanned absences are assumed | C. Tyrrell
A-003 | The platform vendor's proposed system upgrade approach will not require a change to the underlying database platform | M. Alvarez
A-004 | The program must complete Go-Live prior to the start of the next open-enrollment period | C. Tyrrell
A-005 | Historical claims data, once cleansed, will not require additional legal/compliance review beyond what's already scoped | N. Sharma

## Issues
Issue Log
ID | Issue | Owner | Status | Resolution
I-001 | Early data profiling revealed higher-than-expected duplicate member records in historical claims data | T. McCormick | Closed | Additional de-duplication pass added to conversion pipeline
I-002 | Initial vendor-provided test environment lacked production-representative data volume, delaying early integration testing | M. Alvarez | Closed | Vendor provisioned an expanded test environment
I-003 | Intermittent VPN connectivity to the offshore QA environment affecting testing throughput | P. Sundaram | Open | Tracking resolution with internal IT; interim workaround in place
I-004 | Discrepancy identified between Commission Management integration spec and legacy calculation logic | P. Novak | Closed | Resolved via joint review with Business Data Owners
I-005 | External penetration test finding: staging environment TLS configuration | M. Alvarez | Resolved | Patched and re-scanned clean

## Dependencies
Dependency Log
ID | Dependency | Owner | Status
DEP-001 | Data Warehouse/Reporting integration depends on Data Conversion Sign-off completing first | A. Reyes | On Track
DEP-002 | SOX compliance testing depends on Security & Penetration Testing completing first | G. Fenwick | On Track
DEP-003 | Platform vendor SOW must finalize before Environment Provisioning can begin | W. Donnelly | At Risk
DEP-004 | Training content development depends on final UAT-validated workflows | H. Osei | On Track
DEP-005 | Legacy System Decommissioning depends on the Warranty Support period completing | M. Alvarez | On Track

## Decisions
Decision Log
ID | Decision | Decided By | Date
D-001 | Adopt a hybrid waterfall/agile methodology — waterfall for requirements & vendor selection, agile sprints for integration build, gated phases for testing | Steering Committee | 04 Aug 2026
D-002 | Pre-approve contingency utilization of up to $150,000 for a third Data Conversion Dry Run cycle, should root-cause cleansing of R-001 prove insufficient | Steering Committee | 15 Jan 2027
D-003 | Adopt a dual-shore (onshore/offshore) QA model rather than onshore-only, ratified alongside CR-007 | Program Manager | 03 Sep 2026
D-004 | Engage an external firm for SOX compliance assessment rather than relying on internal audit alone, given program complexity | Steering Committee | 29 Aug 2026